## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Binpur-II | Jhargram Division | TALPUKHURIA AND IT'S ADJOINING MOUJAS PWSS | SM/17932 | New | 66 nos. Sinking of 125mm x 115mm x 200m Deep Tube wells by DTH method for installation of Submersible Pumping machinery for BHULAVEDA GP (TALPUPUKHURIA, RAGHUNATHPUR, GIDIGHATI, SHIYARBINDA PWSS) under Binpur-II Block under Jhargram Division, PHE dte. 2nd Call (Ref: 1st Call eNIT_38 of 2022-23, SL No.-2) | Assistant Engineer | Junior Engineer-II | ORD/000314/2023-2024 | 1834/JHD | 27/10/2023 | 22/02/2025 | SUNIL DULE | 108.48 | 19.1 | 17.61 | 80
2 | JHARGRAM | Binpur-II | Jhargram Division | TALPUKHURIA AND IT'S ADJOINING MOUJAS PWSS | SM/17932 | New | Four numbers (4) of yield test process need to be done at Chirugara urf Kuilapal & Chandbila of Bhulaveda GP of Binpur II Block, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000650/2023-2024 | 498/JRWS | 15/03/2024 | 14/04/2024 | SUNIL DULE | 0.72 | 0 | 0 | 0
3 | JHARGRAM | Binpur-II | Jhargram Division | TALPUKHURIA AND IT'S ADJOINING MOUJAS PWSS | SM/17932 | New | Four numbers (4) of yield test process need to be done at Baksol and Madhupur Mouza of Bhulaveda GP of Binpur II Block, under Jhargram division, PHE Dt | Assistant Engineer | Junior Engineer-II | ORD/000646/2023-2024 | 494/JRWS | 15/03/2024 | 14/04/2024 | SUNIL DULE | 0.72 | 0 | 0 | 0
4 | JHARGRAM | Binpur-II | Jhargram Division | TALPUKHURIA AND IT'S ADJOINING MOUJAS PWSS | SM/17932 | New | Four numbers (4) of yield test process need to be done at Talpukuhuria and Pukhuria Mouza of Bhulaveda GP of Binpur II Block, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000648/2023-2024 | 496/JRWS | 15/03/2024 | 14/04/2024 | SUNIL DULE | 0.72 | 0 | 0 | 0
5 | JHARGRAM | Binpur-II | Jhargram Division | TALPUKHURIA AND IT'S ADJOINING MOUJAS PWSS | SM/17932 | New | Four numbers (4) of yield test process need to be done at Charak pahari and Murgadabar Mouza of Bhulaveda GP of Binpur II Block, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000647/2023-2024 | 495/JRWS | 15/03/2024 | 14/04/2024 | SUNIL DULE | 0.72 | 0 | 0 | 0
6 | JHARGRAM | Binpur-II | Jhargram Division | TALPUKHURIA AND IT'S ADJOINING MOUJAS PWSS | SM/17932 | New | Four numbers (4) of yield test process need to be done at Kusbhula & Majugara of Bhulaveda GP of Binpur II Block, under Jhargram Division, PHE Dte | Assistant Engineer | Junior Engineer-II | ORD/000651/2023-2024 | 499/JRWS | 15/03/2024 | 14/04/2024 | SUNIL DULE | 0.72 | 0 | 0 | 0
7 | JHARGRAM | Binpur-II | Jhargram Division | TALPUKHURIA AND IT'S ADJOINING MOUJAS PWSS | SM/17932 | New | Four numbers (4) of yield test process need to be done at Bhula dhara and Gochgiri Mouza of Bhulaveda GP of Binpur II Block, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000649/2023-2024 | 497/JRWS | 15/03/2024 | 14/04/2024 | SUNIL DULE | 0.72 | 0 | 0 | 0
8 | JHARGRAM | Binpur-II | Jhargram Division | TALPUKHURIA AND IT'S ADJOINING MOUJAS PWSS | SM/17932 | New | New Service Connection Charges for Chirugara Talpupukhuria & Adjoining Moujas PWSS |  |  | BILL/00167/2024-2025 | BP-2024-25-111 | 10/07/2024 | 10/07/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
9 | JHARGRAM | Binpur-II | Jhargram Division | TALPUKHURIA AND IT'S ADJOINING MOUJAS PWSS | SM/17932 | New | New Service Connection Charges for Charakpahari Talpupukhuria & Adjoining Moujas PWSS |  |  | BILL/00168/2024-2025 | BP-2024-25-111 | 10/07/2024 | 10/07/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
10 | JHARGRAM | Binpur-II | Jhargram Division | TALPUKHURIA AND IT'S ADJOINING MOUJAS PWSS | SM/17932 | New | New Service Connection Charges for Madhupur, Talpupukhuria & Adjoining Moujas PWSS |  |  | BILL/00165/2024-2025 | BP-2024-25-111 | 10/07/2024 | 10/07/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
11 | JHARGRAM | Binpur-II | Jhargram Division | TALPUKHURIA AND IT'S ADJOINING MOUJAS PWSS | SM/17932 | New | New Service Connection Charges for Chandabila, Talpupukhuria & Adjoining Moujas PWSS |  |  | BILL/00162/2024-2025 | BP-2024-25-111 | 10/07/2024 | 10/07/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
12 | JHARGRAM | Binpur-II | Jhargram Division | TALPUKHURIA AND IT'S ADJOINING MOUJAS PWSS | SM/17932 | New | New Service Connection Charges for Baksol, Talpupukhuria & Adjoining Moujas PWSS |  |  | BILL/00164/2024-2025 | BP-2024-25-111 | 10/07/2024 | 10/07/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
13 | JHARGRAM | Binpur-II | Jhargram Division | TALPUKHURIA AND IT'S ADJOINING MOUJAS PWSS | SM/17932 | New | New Service Connection Charges for Talpukhuria, Talpupukhuria & Adjoining Moujas PWSS |  |  | BILL/00163/2024-2025 | BP-2024-25-111 | 10/07/2024 | 10/07/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
14 | JHARGRAM | Binpur-II | Jhargram Division | TALPUKHURIA AND IT'S ADJOINING MOUJAS PWSS | SM/17932 | New | New Service Connection Charges for Gochgiri, Talpupukhuria & Adjoining Moujas PWSS |  |  | BILL/00161/2024-2025 | BP-2024-25-111 | 10/07/2024 | 10/07/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
15 | JHARGRAM | Binpur-II | Jhargram Division | TALPUKHURIA AND IT'S ADJOINING MOUJAS PWSS | SM/17932 | New | New Service Connection Charges for Kushbhula Talpupukhuria & Adjoining Moujas PWSS |  |  | BILL/00166/2024-2025 | BP-2024-25-111 | 10/07/2024 | 10/07/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
16 | JHARGRAM | Binpur-II | Jhargram Division | TALPUKHURIA AND IT'S ADJOINING MOUJAS PWSS | SM/17932 | New | 33 nos. Stand Alone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for BHULAVEDA GP ( TALPUPUKHURIA ,RAGHUNATHPUR ,GIDIGHATI ,SHIYARBINDA PWSS) under Binpur-II Block under Jhargram Division, PHE dte. (2nd Call Ref eNIT_36 of 2022-23 , SL No.-2 ) | Assistant Engineer | Junior Engineer-II | ORD/000190/2023-2024 | 1531/JHD | 06/09/2023 | 30/04/2025 | ASIS KUMAR SARANGI | 910.58 | 105.51 | 11.59 | 80
17 | JHARGRAM | Binpur-II | Jhargram Division | TALPUKHURIA AND IT'S ADJOINING MOUJAS PWSS | SM/17932 | New | Preparation of documents for uploading in Parivesh portal for clearance of forest land proposed for PWSS under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000838/2023-2024 | 378/JRWS | 31/01/2024 | 01/03/2024 | MESAURE LAND | 0.82 | 0 | 0 | 50
18 | JHARGRAM | Binpur-II | Jhargram Division | TALPUKHURIA AND IT'S ADJOINING MOUJAS PWSS | SM/17932 | New | Preparation of documents for uploading in Parivesh portal for clearance of forest land proposed for PWSS under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000834/2023-2024 | 342/JRWS | 08/01/2024 | 07/02/2024 | MESAURE LAND | 0.82 | 0 | 0 | 100
19 | JHARGRAM | Binpur-II | Jhargram Division | TALPUKHURIA AND IT'S ADJOINING MOUJAS PWSS | SM/17932 | New | Preparation of documents for uploading in Parivesh portal for clearance of forest land proposed for PWSS under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000839/2023-2024 | 379/JRWS | 31/01/2024 | 01/03/2024 | CARTO | 0.82 | 0 | 0 | 100
Total | [13 empty] | 1027.52 | 124.62 | 12.13