## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Jhargram Division | Retrofitting(Phase-III) to accomodate FHTC under JJM in Balibandh PWSS within Jamboni Block, Jhargram District under Jhargram Division, PHE Dte. | SM/17945 | Augmentation | SINKING OF 250 X 150 mm dia. X 150 Mtr. DEPTH RIG BORED TUBE WELL ( REPLACEMENT) & PIPE LINE FOR RETROFITTING (Phase-III) OF BALIBUNDH WATER SUPPLY SCHEME WITH IN JAMBONI BLOCK UNDER JHARGRAM DIVISION, P.H.E. DTE. | Assistant Engineer | Junior Engineer-I | ORD/000011/2023-2024 | 648/JHD | 11/05/2023 | 25/06/2023 | NRIPENDRA NATH SINGHA | 8.12 | 0 | 0 | 70
2 | JHARGRAM |  | Jhargram Mechanical Division | Retrofitting(Phase-III) to accomodate FHTC under JJM in Balibandh PWSS within Jamboni Block, Jhargram District under Jhargram Division, PHE Dte. | SM/17945 | Augmentation | Supply, delivery, installation & commissioning of submersible pumping machinery and other electro-mechanical accessories for proposed additional T/Well at head work site as part of augmentation of Balibandh W/S scheme under Jhargram Mechanical Division, PHE. Dte in the dist. of Jhargram. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000021/2023-2024 | 1128/JMD | 18/05/2023 | 15/09/2023 | SAMARPITA ENGINEERING | 10.42 | 0 | 0 | 100
Total | [13 empty] | 18.55 | 0 | 0