## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Jhargram Mechanical Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Providing UPVC materials including other drilling related works for construction of (125 mm X 115 mm X 200 mtr) RBTW by DTH Method by departmental rig unit under JJM programme at Dakisole SSK ( T/W-2) water supply scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000795/2022-2023 | 80/JMD | 03/01/2023 | 06/01/2023 | DEBJYOTI BASU | 0.75 | 0 | 0 | 0
2 | JHARGRAM |  | Jhargram Mechanical Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Providing different manpower for construction of (125 mm X 115 mm X 200 mtr) RBTW by DTH Method by departmental rig unit under JJM programme at Dakisole SSK ( T/W-2) water supply scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000815/2022-2023 | 81/JMD | 03/01/2023 | 06/01/2023 | DEBJYOTI BASU | 0.15 | 0 | 0 | 0
3 | JHARGRAM |  | Jhargram Mechanical Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other Electro-Mechanical accessories for newly sunk tube well no.-II under JJM programme at Natundihi W/S scheme in the dist. of Jhargram under Jhargram Mechanical Division, PHE Dte. | Assistant Engineer | JE (M) | ORD/000177/2023-2024 | 2096/JMD | 03/08/2023 | 01/11/2023 | RMD TRADING | 1.23 | 0 | 0 | 0
4 | JHARGRAM |  | Jhargram Mechanical Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other Electro-Mechanical accessories for newly sunk tube well no.-II under JJM programme at Amlagura W/S scheme in the dist. of Jhargram under Jhargram Mechanical Division, PHE Dte. | Assistant Engineer | JE (M) | ORD/000175/2023-2024 | 2101/JMD | 03/08/2023 | 01/11/2023 | MONORANJAN DEY | 1.23 | 0 | 0 | 0
5 | JHARGRAM |  | Jhargram Mechanical Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other Electro-Mechanical accessories for newly sunk tube well no. II under JJM programme at Telidanga W/S scheme in the dist. of Jhargram under Jhargram Mechanical Division, PHE Dte. | Assistant Engineer | JE (M) | ORD/000174/2023-2024 | 2100/JMD | 03/08/2023 | 01/11/2023 | JAGANNATH ENTERPRISE | 1.23 | 0 | 0 | 0
6 | JHARGRAM |  | Jhargram Mechanical Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other Electro-Mechanical accessories for newly sunk tube well no.-II under JJM programme at Bhaliadiha W/S scheme in the dist. of Jhargram under Jhargram Mechanical Division, PHE Dte. | Assistant Engineer | JE (M) | ORD/000176/2023-2024 | 2102/JMD | 03/08/2023 | 01/11/2023 | DEBJYOTI BASU | 1.23 | 0 | 0 | 0
7 | JHARGRAM |  | Jhargram Mechanical Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other Electro-Mechanical accessories for newly sunk tube well no.-II under JJM programme at Dakisole SSK W/S scheme in the dist. of Jhargram under Jhargram Mechanical Division, PHE Dte. | Assistant Engineer | JE (M) | ORD/000299/2023-2024 | 2640/JMD | 29/08/2023 | 27/11/2023 | BHABANI PRASAD MANNA | 1.23 | 0 | 0 | 0
8 | JHARGRAM |  | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Sinking 2 nos rig bored tubewells(recplacement),reconstruction of boundary walls and interconnection pipelines from new tubewells to existing distribution pipe lines of Hatipata w/s scheme(under 45 Mini pwss) and Tapsia w/s scheme(under 45 Mini pwss). 4th Call (Ref: 1st Call eNIT_22 of 2022-23 , SL No.-3, and 2nd Call eNIT_08 of 2023-24, SL No.- 7, 3rd Call eNIT_13 of 2023-24, SL No.-3 ) | Assistant Engineer | Junior Engineer-III | ORD/000019/2024-2025 | 1040/JHD | 22/07/2024 | 05/09/2024 | JAYANTA SAHOO | 13.13 | 0 | 0 | 0
9 | JHARGRAM |  | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Sinking of 200 mm dia. X 165 mm dia. X 200 M depth Rig Bored Tube-well (Replacement) by D.T.H. Method for Augmentation of Source of Dakaisole PWSS under 45 Mini PWSS at Binpur-II Block under Jhargram Sub-Division within Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000033/2024-2025 | 738JSD | 02/08/2024 | 23/08/2024 | BIDYUT KUMAR SANTRA | 4.05 | 0 | 0 | 0
10 | JHARGRAM |  | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | 01 nos I.E.P (size 10 cum/hr) with platfrom, with masonary drain of Chandabila W/S Scheme(under 45 nos Mini scheme) at Binpur-I Dev. Block under Jhargram Sub division within Jhargram Division ,PHE Dte. | Assistant Engineer | Junior Engineer Binpur-I block,Junior Engineer-III | ORD/000062/2023-2024 | 1091/JHD | 14/07/2023 | 28/08/2023 | EFFLUENT AND WATER TREATMENT ENGINEERS PVT. LTD. | 9.9 | 4.36 | 44.06 | 90
11 | JHARGRAM |  | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Sinking of 200 mm dia. X 165 mm dia. X 200 M depth Rig Bored Tube-well (Replacement) by D.T.H. Method for Augmentation of Source of Telidanga PWSS under 45 Mini PWSS at Binpur-II Block under Jhargram Sub-Division within Jhargram Division, P.H.E. Dte. |  | Junior Engineer-II | ORD/000032/2024-2025 | 737/JSD | 02/08/2024 | 23/08/2024 | BIDYUT KUMAR SANTRA | 4.05 | 0 | 0 | 100
Total | [13 empty] | 38.17 | 4.36 | 11.43