## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Jhargram Division | Augmentation of Pond Water Based Silda Pipe Water Supply Scheme under Jhargram Division, Block : Binpur-II, District : Jhargram | SM/17953 | Augmentation | Construction of 50 Cum/Hr Capacity WTP,Installation of MS Structural Intake Jetty(Floating Type including Intake pipe carriage way) , Laying of Distribution System,to Accommodate FHTC (1880 Nos) For Augmentation of Silda Pond Based PWSS Under Binpur-II Block under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000404/2023-2024 | 45/JHD | 09/01/2024 | 11/08/2025 | EFFLUENT AND WATER TREATMENT ENGINEERS PVT. LTD. | 369 | 85.85 | 23.27 | 60
2 | JHARGRAM |  | Jhargram Mechanical Division | Augmentation of Pond Water Based Silda Pipe Water Supply Scheme under Jhargram Division, Block : Binpur-II, District : Jhargram | SM/17953 | Augmentation | Supply, delivery and installation of pumping machineries and allied electro-mechanical accessories for Low lift and High lift pumping operations for augmentation of pond based Silda and its adjoining moujas surface water based piped water supply scheme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | Driller-In-Charge | Junior Engineer | ORD/001048/2024-2025 | 480/JMD | 20/03/2025 | 17/08/2025 | B. T. PROJECTS PVT. LTD. | 86.7 | 0 | 0 | 0
Total | [13 empty] | 455.7 | 85.85 | 18.84