## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Jhargram Mechanical Division | Rejuvenation of Ground Water Based Rohini PWSS to Accommodate FHTC under JJM at Sankrail Block within Jhargram District under Jhargram Division, PHE Dte. | SM/17956 | Augmentation | Supply, delivery, installation, commissioning & trial run operation of electro-mechanical components at T/W no. III & IV as part of augmentation of Rohini W/S scheme under Jhargram Mechanical Division, PHE Dte. in the dist. of Jhargram. | Assistant Engineer | JE (M) | ORD/000171/2023-2024 | 2095/JMD | 03/08/2023 | 30/01/2024 | WEST BENGAL ENGINEERING CO. | 19.76 | 0 | 0 | 0
2 | JHARGRAM |  | Jhargram Division | Rejuvenation of Ground Water Based Rohini PWSS to Accommodate FHTC under JJM at Sankrail Block within Jhargram District under Jhargram Division, PHE Dte. | SM/17956 | Augmentation | SINKING OF 250 X 150 mm dia. X 150 Mtr. DEPTH RIG BORED TUBE WELL, BOUNDARY WALL & CONSTRUCTION OF SWITCH ROOM FOR REJUVENATION OF ROHINI WATER SUPPLY SCHEME WITH IN SANKRAIL BLOCK UNDER JHARGRAM DIVISION, P.H.E. DTE. 2nd Call (Ref eNIT_21 of 2022-23 , SL No.-1 ) | Assistant Engineer | Junior Engineer-II,Junior Engineer-III | ORD/000297/2023-2024 | 1716/JHD | 29/09/2023 | 22/07/2025 | ASIS KUMAR SARANGI | 30.87 | 0 | 0 | 90
3 | JHARGRAM |  | Jhargram Mechanical Division | Rejuvenation of Ground Water Based Rohini PWSS to Accommodate FHTC under JJM at Sankrail Block within Jhargram District under Jhargram Division, PHE Dte. | SM/17956 | Augmentation | New Service Connection Charges for Rohini T/W-IV PWSS |  |  | BILL/00920/2025-2026 |  | 22/08/2025 | 22/08/2025 | WBSEDCL | 4.38 | 0 | 0 | 0
4 | JHARGRAM |  | Jhargram Mechanical Division | Rejuvenation of Ground Water Based Rohini PWSS to Accommodate FHTC under JJM at Sankrail Block within Jhargram District under Jhargram Division, PHE Dte. | SM/17956 | Augmentation | New Service Connection Charges for Rohini-III PWSS |  |  | BILL/00922/2025-2026 |  | 22/08/2025 | 22/08/2025 | WBSEDCL | 3.95 | 0 | 0 | 0
Total | [13 empty] | 58.97 | 0 | 0