## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Jhargram Division | Rejuvenation of Ground Water Based Dhamro Water Supply Scheme to Accommodate FHTC under JJM at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | SM/17959 | Augmentation | Extension of distribution pipeline and providing the pending FHTCs at Binpur-I block under Dhamro PWSS under Jhargram Sub-division within Jhargram Division,PHE Dte. | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000061/2023-2024 | 1096/JHD | 14/07/2023 | 28/08/2023 | SAIKAT DANDAPAT | 23.97 | 0 | 0 | 80
2 | JHARGRAM |  | Jhargram Division | Rejuvenation of Ground Water Based Dhamro Water Supply Scheme to Accommodate FHTC under JJM at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | SM/17959 | Augmentation | construction of boundary wall of 1st tubewell site,repairing boundary wall of 2nd tubewell site at Binpur-I block under Dhamro PWSS under Jhargram Sub-division within Jhargram Division,PHE Dte. | Assistant Engineer | Junior Engineer Binpur-I block | ORD/000184/2023-2024 | 1397/JHD | 18/08/2023 | 02/10/2023 | RABINDRANATH MANDAL | 11.03 | 0 | 0 | 90
Total | [13 empty] | 35 | 0 | 0