## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Jhargram Division | Retrofitting incl. Augmentation of Source(Phase-II) and Installation of IEP & related works to Accommodate FHTC under JJM in Ground water based Rantua Water Supply Scheme at Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte | SM/17964 | Augmentation | Providing pending FHTC (200 nos)of Rantua W/S scheme at Gopiballavpur-II block under Jhargram Sub Division within Jhargram Division,PHE Dte | Assistant Engineer | Junior Engineer-III | ORD/000033/2023-2024 | 879/JHD | 08/06/2023 | 08/07/2023 | TAPAS KUMAR JANA | 8.7 | 0 | 0 | 0
2 | JHARGRAM |  | Jhargram Division | Retrofitting incl. Augmentation of Source(Phase-II) and Installation of IEP & related works to Accommodate FHTC under JJM in Ground water based Rantua Water Supply Scheme at Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte | SM/17964 | Augmentation | 03 nos I.E.Ps [2 nos of size 20 cum/hr.(at proposed sites),35 cum/hr.(at head work site)] with platfroms, blower with compressor rooms, Pump house with blower, compressor room of Rantua w/s scheme. | Assistant Engineer | Junior Engineer-III | ORD/000032/2023-2024 | 878/JHD | 08/06/2023 | 07/08/2023 | MONDAL PRECISION PRIVATE LIMITED | 39.84 | 9.19 | 23.05 | 25
3 | JHARGRAM |  | Jhargram Division | Retrofitting incl. Augmentation of Source(Phase-II) and Installation of IEP & related works to Accommodate FHTC under JJM in Ground water based Rantua Water Supply Scheme at Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte | SM/17964 | Augmentation | 02 nos Sinking of 250x150 mm dia x 150 mtr.rig bored tubewell at prposed sites (Jarakusum Mouza & Askola Mouza), replacement of distribution pipe line(part)and extension of distribution pipeline, construction chain link fencing at 3 nos sites for Rantua w/s scheme at Gopiballavpur-II block under Jhargram Sub-division within Jhargram Division, PHE Dte. 3rd Call (Ref: 1st Call eNIT_28 of EE/JHD of 2022-23, SL No.-9, 2nd Call eNIT_11 of EE/JHD of 2023-24, SL No.-1) | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division | Junior Engineer-II,Junior Engineer-III | ORD/000575/2023-2024 | 448/JHD | 14/03/2024 | 01/04/2025 | DEBASISH DOGRA | 57.49 | 10.99 | 19.11 | 50
4 | JHARGRAM |  | Jhargram Division | Retrofitting incl. Augmentation of Source(Phase-II) and Installation of IEP & related works to Accommodate FHTC under JJM in Ground water based Rantua Water Supply Scheme at Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte | SM/17964 | Augmentation | Construction of Pump house (inner size 3.6m x 3.00m width) at proposed tube-well site at Askola mouza & Jarakusum mouza with chain link fencing 60.00mtr each site of Rantua W/S Scheme at Gopiballavpur-II Block under Jhargram sub-division, PHE Dte. 2nd Call (Ref eNIT_28 of 2022-23 , SL No.-8 ) | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division | Junior Engineer-III | ORD/000160/2023-2024 | 1402/JHD | 18/08/2023 | 17/10/2023 | TAPAS PAL | 15.78 | 0 | 0 | 15
5 | JHARGRAM |  | Jhargram Division | Retrofitting incl. Augmentation of Source(Phase-II) and Installation of IEP & related works to Accommodate FHTC under JJM in Ground water based Rantua Water Supply Scheme at Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte | SM/17964 | Augmentation | Repair and renovation of Pump house no 2 at Rantua w/s Scheme within Jhargram Sub Division, PHE Dte. . (3rd Call) [Ref. eNIT 07 OF AE/JSD OF 2024-2025, SL No. 02] | Assistant Engineer | Junior Engineer-III | ORD/000174/2024-2025 | 1068/JSD | 26/11/2024 | 10/12/2024 | S.R. ENTERPRISE | 2.23 | 0 | 0 | 85
6 | JHARGRAM |  | Jhargram Mechanical Division | Retrofitting incl. Augmentation of Source(Phase-II) and Installation of IEP & related works to Accommodate FHTC under JJM in Ground water based Rantua Water Supply Scheme at Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte | SM/17964 | Augmentation | New Service Connection Charges for Rantua (Ashkola) T/W - IV PWSS |  |  | BILL/01575/2024-2025 | 451/JMD | 21/01/2025 | 21/01/2025 | WBSEDCL | 3.54 | 0 | 0 | 0
7 | JHARGRAM |  | Jhargram Mechanical Division | Retrofitting incl. Augmentation of Source(Phase-II) and Installation of IEP & related works to Accommodate FHTC under JJM in Ground water based Rantua Water Supply Scheme at Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte | SM/17964 | Augmentation | New Service Connection Charges for Rantua Jorakusma T/W-III PWSS |  |  | BILL/01576/2024-2025 | 452/JMD | 21/01/2025 | 21/01/2025 | WBSEDCL | 8.81 | 0 | 0 | 0
Total | [13 empty] | 136.38 | 20.17 | 14.79