## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Jhargram Division | Retrofitting incl. Augmentation of Source (Phase-II) and Installation of IEP & related works to Accommodate FHTC under JJM in Ground Water based Lakat Water Supply Scheme at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | SM/17965 | Augmentation | Replacement of distribution pipe line(part) of Lakat w/s scheme at Binpur-I Dev. Block under Jhargram Sub division within Jhargram Division ,PHE Dte. | Assistant Engineer | Junior Engineer-III | ORD/000025/2023-2024 | 875/JHD | 08/06/2023 | 08/07/2023 | MAA LAXMI ENTERPRISE | 7.96 | 0 | 0 | 0
2 | JHARGRAM |  | Jhargram Division | Retrofitting incl. Augmentation of Source (Phase-II) and Installation of IEP & related works to Accommodate FHTC under JJM in Ground Water based Lakat Water Supply Scheme at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | SM/17965 | Augmentation | 01 nos I.E.P (size 10 cum/hr) with platfrom, blower with compressor room of Lakat W/S Scheme at Binpur-I Dev. Block under Jhargram Sub division within Jhargram Division ,PHE Dte. | Assistant Engineer | Junior Engineer-III | ORD/000029/2023-2024 | 874/JHD | 08/06/2023 | 23/07/2023 | NEER UDYOG | 12.58 | 0 | 0 | 60
3 | JHARGRAM |  | Jhargram Mechanical Division | Retrofitting incl. Augmentation of Source (Phase-II) and Installation of IEP & related works to Accommodate FHTC under JJM in Ground Water based Lakat Water Supply Scheme at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | SM/17965 | Augmentation | Supply, delivery, installation & commissioning of submersible pumping machinery and other electro-mechanical accessories at replacement T/W no. II of Lakat W/S scheme under Jhargram Mechanical Division, PHE. Dte in the dist. of Jhargram. | Assistant Engineer | Junior Engineer | ORD/000183/2023-2024 | 2107/JMD | 03/08/2023 | 02/09/2023 | DEBJYOTI BASU | 9.62 | 0 | 0 | 100
4 | JHARGRAM |  | Jhargram Division | Retrofitting incl. Augmentation of Source (Phase-II) and Installation of IEP & related works to Accommodate FHTC under JJM in Ground Water based Lakat Water Supply Scheme at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | SM/17965 | Augmentation | Sinking of 200 X150mm diaX150 mtr. rig bored tubewell(replacement) and interconnection pipeline from propose tubewell to rising main pipeline and construction damaged boudary wall (length-7.5) and colour painting total length boundary wall of Lakat PWSS within Binpur-1 Block, under Jhargram Division, PHE Dte. 2 nd Call (Ref eNIT_28 of 2022-23, SL No.-14) | Assistant Engineer | Junior Engineer-III | ORD/000282/2023-2024 | 1669/JHD | 21/09/2023 | 05/11/2023 | M/S ANKITA CONSTRUCTION | 7.88 | 0 | 0 | 100
Total | [13 empty] | 38.04 | 0 | 0