## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Jhargram Division | Rejuvenation(Phase-II) of Ground Water Based Chandal Bandh PWSS and Installation of IEP & related works to Accommodate FHTC at Nayagram Block within Jhargram District under Jhargram Division, PHE Dte. | SM/17966 | Augmentation | 01 nos I.E.Ps[size 30 cum/hr] with platfroms,blower with compressor rooms etc. of Chandalbundh w/s scheme. | Assistant Engineer | Junior Engineer-III | ORD/000277/2023-2024 | 1645/JHD | 14/09/2023 | 29/10/2023 | KANAN CONSTRUCTION ENTERPRISE | 16.58 | 0 | 0 | 0
2 | JHARGRAM |  | Jhargram Division | Rejuvenation(Phase-II) of Ground Water Based Chandal Bandh PWSS and Installation of IEP & related works to Accommodate FHTC at Nayagram Block within Jhargram District under Jhargram Division, PHE Dte. | SM/17966 | Augmentation | Sinking of 250x150mm dia x150mtr rig bored tubewell,const.of pumhouse,const. of brick masonary drain and cons. ground water recharge structure of Chandalbundh W/s schme in Nayagram block under Jhargram District within Jhargram Division,PHE Dte. | Assistant Engineer | Junior Engineer-III | ORD/000139/2023-2024 | 1331/JHD | 10/08/2023 | 24/09/2023 | BRAJENDRANATH SENAPATI | 17.37 | 5.72 | 32.92 | 70
Total | [13 empty] | 33.95 | 5.72 | 16.84