## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Jhargram Mechanical Division | Rejuvenation of Ground Water Based Kantapahari PWSS and Installation of IEP & related works to Accommodate FHTC at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | SM/18002 | Augmentation | Supply, delivery, installation & commissioning of submersible pumping machinery and other electro-mechanical accessories at replacement T/W no. I of Kantapahari W/S scheme under Jhargram Mechanical Division, PHE. Dte in the dist. of Jhargram. | Assistant Engineer | JE (M),Junior Engineer | ORD/000182/2023-2024 | 2106/JMD | 03/08/2023 | 02/09/2023 | SUBHASIS ROY | 9.62 | 0 | 0 | 100
2 | JHARGRAM |  | Jhargram Division | Rejuvenation of Ground Water Based Kantapahari PWSS and Installation of IEP & related works to Accommodate FHTC at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | SM/18002 | Augmentation | Sinking of 250x150 mm dai x 150 mtr. Rig bored tubewell(replacement), laying of drainage pipeline for I I backwash water from IEP, construction brick masonary drain, I I replacement of distribution pipe line(partly)and extension of I I distribution pipeline for Kantapahari w/s scheme at Binpur-1 block I I under Jhargram Sub-division within Jhargram Division, PHE Dte. I 13 rd Call (Ref: 1st Call eNIT 21 of 2022-23, 2022-23, SL No.-8, and 2nd I I Call eNIT 08 of 2023-24, SL No.- 5) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000343/2023-2024 | 1884/JHD | 03/11/2023 | 02/01/2024 | SUJOY RANJAN BHOWMICK | 31.11 | 26.27 | 84.46 | 90
3 | JHARGRAM |  | Jhargram Division | Rejuvenation of Ground Water Based Kantapahari PWSS and Installation of IEP & related works to Accommodate FHTC at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | SM/18002 | Augmentation | replacement of Distribution pipe line(part) of Kantapahari w/s scheme at Binpur-I Block under Jhargram Sub Division within Jhargram Division,PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram Sub-Division | ORD/000691/2023-2024 | 194/JSD | 11/03/2024 | 18/03/2024 | SAMIR PATRA | 0.96 | 0 | 0 | 100
4 | JHARGRAM |  | Jhargram Division | Rejuvenation of Ground Water Based Kantapahari PWSS and Installation of IEP & related works to Accommodate FHTC at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | SM/18002 | Augmentation | Providing FHTCs (80 nos) in the uncovered pocktes of Kantapahari W/S scheme under Jhargram Sub Division within Jhargram Division,PHE Dte | Assistant Engineer | Junior Engineer Binpur-I block,Junior Engineer-II | ORD/000096/2023-2024 | 652/JSD | 18/07/2023 | 17/08/2023 | SAMIR PATRA | 4.13 | 2.87 | 69.54 | 100
5 | JHARGRAM |  | Jhargram Division | Rejuvenation of Ground Water Based Kantapahari PWSS and Installation of IEP & related works to Accommodate FHTC at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | SM/18002 | Augmentation | Providing pending FHTC (70 nos) of Kantapahari W/S scheme under Jhargram Sub Division within Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer Binpur-I block | ORD/000115/2023-2024 | 671/JSD | 25/07/2023 | 24/08/2023 | GOURMOHAN DAS | 3.39 | 2.45 | 72.28 | 95
6 | JHARGRAM |  | Jhargram Division | Rejuvenation of Ground Water Based Kantapahari PWSS and Installation of IEP & related works to Accommodate FHTC at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | SM/18002 | Augmentation | Sinking of Replacement Tube Well No 2 ( 250 x150 mm ) including interconnection work with the existing Rising Main line and Special Repair and Renovation of Boundary Wall and Pump House No 2 of Kantapahari PWSS under Jhargram Sub Division under Jhargram Sub Division PHE Dte. | Assistant Engineer | Junior Engineer Binpur-I block | ORD/000262/2024-2025 | 73/JHD | 10/01/2025 | 24/02/2025 | SUJOY RANJAN BHOWMICK | 8.93 | 0 | 0 | 90
7 | JHARGRAM |  | Jhargram Division | Rejuvenation of Ground Water Based Kantapahari PWSS and Installation of IEP & related works to Accommodate FHTC at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | SM/18002 | Augmentation | 01 nos I.E.P (size 20 cum/hr) with platfrom, blower with compressor room of Kantapahari W/S Scheme at Binpur-I Dev. Block under Jhargram Sub division within Jhargram Division ,PHE Dte. | Assistant Engineer | Junior Engineer Binpur-I block,Junior Engineer-III | ORD/000296/2023-2024 | 1720/JHD | 29/09/2023 | 29/07/2025 | KANAN CONSTRUCTION ENTERPRISE | 14.3 | 7.82 | 54.72 | 95
Total | [13 empty] | 72.45 | 39.42 | 54.42