## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Midnapore Division | Rejuvenation (Phase-II) of Ground Water Based Jhitka PWSS and Installation of IEP & related works to Accommodate FHTC at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | SM/18008 | Augmentation | Retrofitting to accommodate FHTC under JJM in Jhitka PWSS of Binpur-I Block under Jhargram Division, PHE Dte. |  |  | ORD/000283/2020-2021 | 1582/MD | 11/12/2020 | 09/06/2021 | RAMENDRA NATH KAR | 15.06 | 0 | 0 | 80
2 | JHARGRAM |  | Jhargram Division | Rejuvenation (Phase-II) of Ground Water Based Jhitka PWSS and Installation of IEP & related works to Accommodate FHTC at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | SM/18008 | Augmentation | Sinking of 200X150mm diaX150 mtr rig bored tubewell,replacement of distribution pipeline(part),cons. brick masonary drain,cons. boundary wall of Jitka w/s scheme at Binpur-I block under Jhargram Sub-division within Jhargram Division,PHE Dte. | Assistant Engineer | Junior Engineer-III | ORD/000016/2023-2024 | 725/JHD | 18/05/2023 | 02/07/2023 | RAMENDRA NATH KAR | 23.71 | 0 | 0 | 100
3 | JHARGRAM |  | Jhargram Division | Rejuvenation (Phase-II) of Ground Water Based Jhitka PWSS and Installation of IEP & related works to Accommodate FHTC at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | SM/18008 | Augmentation | 01 nos I.E.P (size 20 cum/hr) with platfrom, blower with compressor room of Jitka W/S Scheme at Binpur-I Dev. Block under Jhargram Sub division within Jhargram Division ,PHE Dte. | Assistant Engineer | Junior Engineer Binpur-I block,Junior Engineer-III | ORD/000276/2023-2024 | 1647/JHD | 14/09/2023 | 02/05/2025 | KANAN CONSTRUCTION ENTERPRISE | 14.45 | 0 | 0 | 100
Total | [13 empty] | 53.22 | 0 | 0