## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Jhargram Division | Rejuvenation(Phase-II) of Ground Water Based Naupara PWSS and Installation of IEP & related works to Accommodate FHTC at Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | SM/18010 | Augmentation | Providing pending FHTC (120nos) of Naupara W/S scheme under Jhargram Sub Division within Jhargram Division,PHE Dte | Assistant Engineer | Junior Engineer-III | ORD/000035/2023-2024 | 880/JHD | 08/06/2023 | 08/07/2023 | KRISHNA CHANDRA DAS | 5.86 | 0 | 0 | 0
2 | JHARGRAM |  | Jhargram Division | Rejuvenation(Phase-II) of Ground Water Based Naupara PWSS and Installation of IEP & related works to Accommodate FHTC at Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | SM/18010 | Augmentation | 01 nos I.E.Ps[size 30 cum/hr.(at head work site)] with platfrom,blower with compressor room etc. of Naupara w/s scheme under Gopiballavpur Dev. Block with Jhargram Sub Division ,PHE Dte | Assistant Engineer | Junior Engineer-III | ORD/000036/2023-2024 | 881/JHD | 08/06/2023 | 23/07/2023 | MONDAL PRECISION PRIVATE LIMITED | 16.44 | 8.85 | 53.83 | 55
3 | JHARGRAM |  | Jhargram Division | Rejuvenation(Phase-II) of Ground Water Based Naupara PWSS and Installation of IEP & related works to Accommodate FHTC at Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | SM/18010 | Augmentation | Sinking of 250 X 150 mm dia. X 150 mtr.rig bored tubewell (replacement)with inter connection with Raising main at head work site of Naupara w/s scheme.within Gopiballavpur-II Block, within Jhargram Sub Division, PHE Dte. 2nd Call (Ref eNIT_28 of 2022-23 , SL No.-3 ) | Assistant Engineer | Junior Engineer-III | ORD/000174/2023-2024 | 1414/JHD | 22/08/2023 | 21/09/2023 | KARTIK DUTTA | 7.05 | 3.26 | 46.23 | 100
4 | JHARGRAM |  | Jhargram Division | Rejuvenation(Phase-II) of Ground Water Based Naupara PWSS and Installation of IEP & related works to Accommodate FHTC at Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | SM/18010 | Augmentation | replacement of distribution pipe line(part) and Construction boundary wall ( Length 160 mtr. ,Height-2.45,including 4 mtr width gate) at head work site of Naupara w/s scheme under Gopiballavpur-II Dev. Block within Jhargram Sub Division ,PHE Dte. | Assistant Engineer | Junior Engineer-III | ORD/000175/2023-2024 | 1393/JHD | 18/08/2023 | 16/11/2023 | SUNIL DULE | 33.6 | 17.39 | 51.74 | 100
Total | [13 empty] | 62.95 | 29.49 | 46.85