## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Jhargram Division | Rejuvenation (Phase-II) of Ground Water Based Birkanar PWSS and Installation of IEP & related works to Accommodate FHTC at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | SM/18012 | Augmentation | Extension of distribution pipeline,providing pending FHTC,construction of boundary walls at 1st tubewell site and 2nd tubewell site,brick masonary drain,ground water recharge structure of Birkarnar w/s scheme at Binpur-I block under Jhargram Sub-division within Jhargram Division,PHE Dte. | Assistant Engineer | Junior Engineer-III | ORD/000007/2023-2024 | 606/JHD | 04/05/2023 | 03/07/2023 | DHUMKETU ENGINEERING PRIVATE LIMITED | 30.84 | 27.79 | 90.1 | 31
2 | JHARGRAM |  | Jhargram Division | Rejuvenation (Phase-II) of Ground Water Based Birkanar PWSS and Installation of IEP & related works to Accommodate FHTC at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | SM/18012 | Augmentation | 01 nos I.E.P (size 20 cum/hr) with platfrom, blower with compressor room of Birkarnar W/S Scheme at Binpur-I Dev. Block under Jhargram Sub division within Jhargram Division ,PHE Dte. | Assistant Engineer | Junior Engineer Binpur-I block,Junior Engineer-III | ORD/000275/2023-2024 | 1646/JHD | 14/09/2023 | 29/07/2025 | KANAN CONSTRUCTION ENTERPRISE | 14.45 | 5.14 | 35.57 | 100
3 | JHARGRAM |  | Jhargram Division | Rejuvenation (Phase-II) of Ground Water Based Birkanar PWSS and Installation of IEP & related works to Accommodate FHTC at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | SM/18012 | Augmentation | Re-Laying of Rising Main [100 mm DI (K9)] and Distribution Line (Partly) of Birkarnar Piped Water Supply Scheme within Jhargram Sub-Division under Jhargram Division, PHE Dte.; i.c.w. Strengthening of Lalgarh-Ramgarh Road and Construction of Wide Culverts by Replacing Existing Narrow Culverts under Jhargram Highway Division, PW (Roads) Dte. | Assistant Engineer | Junior Engineer, Jhargram Sub-Division | ORD/000293/2024-2025 | 46/JSD | 13/01/2025 | 03/02/2025 | DHUMKETU ENGINEERING PRIVATE LIMITED | 4.01 | 0 | 0 | 0
Total | [13 empty] | 49.3 | 32.93 | 66.8