## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Jhargram Division | Rejuvenation(Phase-II) of Ground Water Based Ramgarh PWSS(Zone-I & II) PWSS and Installation of IEP & related works to Accommodate FHTC at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | SM/18014 | Augmentation | Providing FHTCs (250 nos)in the uncovered pocktes of of Ramagarh W/S scheme(Zone-I & II) under Jhargram Sub Division within Jhargram Division, PHE Dte | Assistant Engineer | Junior Engineer-III | ORD/000026/2023-2024 | 876/JHD | 08/06/2023 | 23/07/2023 | TAPAS KUMAR JANA | 11.11 | 0 | 0 | 0
2 | JHARGRAM |  | Jhargram Division | Rejuvenation(Phase-II) of Ground Water Based Ramgarh PWSS(Zone-I & II) PWSS and Installation of IEP & related works to Accommodate FHTC at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | SM/18014 | Augmentation | 03 nos I.E.Ps[size 15 cum/hr.(at propose site under Zone-I),25 cum/hr.(at head work site of Zone-I),30 cum/hr.(at head work site of Zone-II)] with platfroms,blower with compressor rooms,Pump house with blower,compressor room of Ramgarh w/s(Zone-I & II) scheme. | Assistant Engineer | Junior Engineer-III | ORD/000031/2023-2024 | 877/JHD | 08/06/2023 | 07/08/2023 | MONDAL PRECISION PRIVATE LIMITED | 46.94 | 0 | 0 | 40
3 | JHARGRAM |  | Jhargram Division | Rejuvenation(Phase-II) of Ground Water Based Ramgarh PWSS(Zone-I & II) PWSS and Installation of IEP & related works to Accommodate FHTC at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | SM/18014 | Augmentation | Repair and renovation of RCC O.H.R (Zone-I)of capacity 50000 gallon with staging height of 20 mtr.with allied works of Ramgarh Piped water supply Scheme at Binpur-I block under Jhargram Sub Division within Jhargram Division. | Assistant Engineer | Junior Engineer-III | ORD/000005/2023-2024 | 570/JHD | 25/04/2023 | 24/06/2023 | SUNIL DULE | 14.91 | 0 | 0 | 100
4 | JHARGRAM |  | Jhargram Mechanical Division | Rejuvenation(Phase-II) of Ground Water Based Ramgarh PWSS(Zone-I & II) PWSS and Installation of IEP & related works to Accommodate FHTC at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | SM/18014 | Augmentation | Supply, delivery, installation & commissioning of submersible pumping machinery and other electro-mechanical accessories at replacement T/W no. I (Zone-II) of Ramgarh W/S scheme under Jhargram Mechanical Division, PHE. Dte in the dist. of Jhargram. | Assistant Engineer | JE (M),Junior Engineer | ORD/000180/2023-2024 | 2104/JMD | 03/08/2023 | 02/09/2023 | A.K. INDUSTRIES | 9.61 | 0 | 0 | 100
5 | JHARGRAM |  | Jhargram Division | Rejuvenation(Phase-II) of Ground Water Based Ramgarh PWSS(Zone-I & II) PWSS and Installation of IEP & related works to Accommodate FHTC at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | SM/18014 | Augmentation | Sinking of 2 nos of 250 X 150 mm dia. X 150 mtr.rig bored tubewells(1 nos at proposed tubewell site & 1 nos replacement tube well at head work site of Zone-II ), Construction of brick masonry drain of 300 mm X 250 mm inner section (length-20 m),laying of drainage pipe line for backwash water from 3nos IEPs,replacement of distribution pipe line(part), extension of distribution pipeline and providing 50 nos of pending FHTC of Ramgarh W/S(Zone-I & II) scheme at Binpur-I Block under Jhargram Sub Division within Jhargram Division, PHE Dte. | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division | Junior Engineer Binpur-I block,Junior Engineer-III | ORD/000010/2023-2024 | 647/JHD | 11/05/2023 | 09/08/2023 | SUNIL DULE | 77.74 | 0 | 0 | 60
6 | JHARGRAM |  | Jhargram Mechanical Division | Rejuvenation(Phase-II) of Ground Water Based Ramgarh PWSS(Zone-I & II) PWSS and Installation of IEP & related works to Accommodate FHTC at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | SM/18014 | Augmentation | Supply, delivery, installation of pumping machinery and other electro-mechanical components at replacement T/W no. I of Zone-1 at Ramgarh water supply scheme in Binpur-1 Block under Jhargram Mechanical Division, PHE Dte. in the dist. of Jhargram. | Assistant Engineer | Junior Engineer | ORD/000015/2025-2026 | 925/JMD | 13/05/2025 | 01/09/2025 | M/S. CHANDRANATH MUKHERJEE | 3.27 | 0 | 0 | 100
Total | [13 empty] | 163.59 | 0 | 0