## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Jhargram Division | Retrofitting(Phase-III) to accomodate FHTC under JJM in Junsola PWSS within Gopiballavpur-II Block, Jhargram District under Jhargram Division, PHE Dte. | SM/18190 | Augmentation | Providing pending FHTC (85 nos)of Junsola W/S scheme at Gopiballavpur-II Block under Jhargram Sub Division within Jhargram Division,PHE Dte | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division,Junior Engineer-II | ORD/000095/2023-2024 | 649/JSD | 14/07/2023 | 13/08/2023 | S.R. ENTERPRISE | 3.87 | 2.91 | 75.18 | 95
2 | JHARGRAM |  | Jhargram Mechanical Division | Retrofitting(Phase-III) to accomodate FHTC under JJM in Junsola PWSS within Gopiballavpur-II Block, Jhargram District under Jhargram Division, PHE Dte. | SM/18190 | Augmentation | Supply, delivery, installation & commissioning of submersible pumping machinery and other electro-mechanical accessories at proposed additional T/Well as part of augmentation of Junsola W/S scheme in the dist. of Jhargram under Jhargram Mechanical Division, PHE Dte. | Assistant Engineer | JE (M) | ORD/000172/2023-2024 | 2098/JMD | 03/08/2023 | 02/09/2023 | DAS CONSTRUCTION | 9.41 | 0 | 0 | 0
3 | JHARGRAM |  | Jhargram Division | Retrofitting(Phase-III) to accomodate FHTC under JJM in Junsola PWSS within Gopiballavpur-II Block, Jhargram District under Jhargram Division, PHE Dte. | SM/18190 | Augmentation | Sinkingof 200 X150mm diaX150 mtr. rig bored tubewell(replacement),interconnection pipeline from propose tubewell to rising main pipeline and construction damged boudary wall of Junsola PWSS within Gopiballavpur-II Block, under Jhargram Division, PHE Dte. 2nd Call (Ref eNIT_28 of 2022-23 , SL No.-2 ) | Assistant Engineer | Junior Engineer-III | ORD/000199/2023-2024 | 1464/JHD | 31/08/2023 | 30/09/2023 | SHREE ENGINEERING | 8.57 | 0 | 0 | 0
4 | JHARGRAM |  | Jhargram Division | Retrofitting(Phase-III) to accomodate FHTC under JJM in Junsola PWSS within Gopiballavpur-II Block, Jhargram District under Jhargram Division, PHE Dte. | SM/18190 | Augmentation | Replacement rising main & distribution pipe line(part) of Junsola W/S scheme.within Gopiballavpur-II Block, under Jhargram Division, PHE Dte. 2nd Call (Ref eNIT_28 of 2022-23 , SL No.-1 ) | Assistant Engineer | Junior Engineer-III | ORD/000122/2023-2024 | 1329/JHD | 10/08/2023 | 09/09/2023 | ENVOTECH INFRA SOLUTION | 13.14 | 13.13 | 99.94 | 100
Total | [13 empty] | 34.99 | 16.04 | 45.84