## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Jhargram Division | AUGMENTATION OF POND WATER BASED BELPAHARI PIPE WATER SUPPLY SCHEME TO ACCOMMODATE FHTC AT BINPUR-II- BLOCKWITHIN JHARGRAM-DISTRICT, UNDER JHARGRAM DIVISION, PHE DTE. | SM/18428 | Augmentation | Construction of 600 Cum OHR(Intze type solid raft) ,Laying of Distribution ,clear Water & Raw Water Raising main to accommodate FHTC (7292 Nos) for Augmentation of Belpahari Water Supply Scheme within Binpur-II Block under Jhargram District under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer RWS, Binpur-II Devlopment Block. | ORD/000189/2023-2024 | 1463/JHD | 31/08/2023 | 21/06/2025 | M/S A.R ENTERPRISE | 929.37 | 384.87 | 41.41 | 70
2 | JHARGRAM |  | Jhargram Division | AUGMENTATION OF POND WATER BASED BELPAHARI PIPE WATER SUPPLY SCHEME TO ACCOMMODATE FHTC AT BINPUR-II- BLOCKWITHIN JHARGRAM-DISTRICT, UNDER JHARGRAM DIVISION, PHE DTE. | SM/18428 | Augmentation | Laying of Pipe Line for uncovered habitation of Muransole Mouza under Belpahari WS Scheme within Binpur-II Block under Jhargram Division, P.H.E. Dte | Assistant Engineer | Junior Engineer-II | ORD/000346/2023-2024 | 967/JSD | 10/11/2023 | 01/12/2023 | SUNIL DULE | 3.07 | 3.07 | 100 | 100
3 | JHARGRAM |  | Jhargram Division | AUGMENTATION OF POND WATER BASED BELPAHARI PIPE WATER SUPPLY SCHEME TO ACCOMMODATE FHTC AT BINPUR-II- BLOCKWITHIN JHARGRAM-DISTRICT, UNDER JHARGRAM DIVISION, PHE DTE. | SM/18428 | Augmentation | Installation of 1000 Litres capacity PVC Water Tank and allied construction at Different Places under Belpahari W/S Scheme within Jhargram Sub-Division under Jhargram Division P.H.E.Dte. | Assistant Engineer | Junior Engineer-II | ORD/000345/2023-2024 | 966/JSD | 10/11/2023 | 01/12/2023 | SAIKAT DANDAPAT | 1.15 | 1.15 | 100 | 100
4 | JHARGRAM |  | Jhargram Division | AUGMENTATION OF POND WATER BASED BELPAHARI PIPE WATER SUPPLY SCHEME TO ACCOMMODATE FHTC AT BINPUR-II- BLOCKWITHIN JHARGRAM-DISTRICT, UNDER JHARGRAM DIVISION, PHE DTE. | SM/18428 | Augmentation | Supply of CIDF Sluice Valve for Belpahari PWSS within Augmentation of Belpaharai W/S Scheme under Jhargram Sub Division under Jhargram Division P.H.E. Dte. . (2nd Call) [Ref: 1st Call of e-NIQ-03 of AE/JSD of 2024-2025, SL. No.-01] | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division | Junior Engineer RWS, Binpur-II Devlopment Block. | ORD/000205/2024-2025 | 1101/JSD | 03/12/2024 | 17/12/2024 | M/S A.R ENTERPRISE | 3.23 | 0 | 0 | 100
5 | JHARGRAM |  | Jhargram Division | AUGMENTATION OF POND WATER BASED BELPAHARI PIPE WATER SUPPLY SCHEME TO ACCOMMODATE FHTC AT BINPUR-II- BLOCKWITHIN JHARGRAM-DISTRICT, UNDER JHARGRAM DIVISION, PHE DTE. | SM/18428 | Augmentation | Laying of Distribution Pipe Line due to damage in existing pipeline during Construction of Concrete Road from Merasuli to Sahari Rana Para & Adibasipara under Belpahari Water Supply Scheme. | Assistant Engineer | Junior Engineer-II | ORD/000434/2023-2024 | 148/JHD | 29/01/2024 | 13/02/2024 | SAIKAT DANDAPAT | 5.78 | 5.47 | 94.61 | 100
6 | JHARGRAM |  | Jhargram Division | AUGMENTATION OF POND WATER BASED BELPAHARI PIPE WATER SUPPLY SCHEME TO ACCOMMODATE FHTC AT BINPUR-II- BLOCKWITHIN JHARGRAM-DISTRICT, UNDER JHARGRAM DIVISION, PHE DTE. | SM/18428 | Augmentation | Continuation Work for Functional Household Tap Connection data uploading charges of different PWSS under Jhargram District in JJM_IMIS portal under Jal Jeevan Mission for 1st March 2024 to 15th March 2024 under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000697/2023-2024 | 451/JRWS | 27/02/2024 | 13/03/2024 | JAGOMOHAN SETUA | 0.63 | 0.63 | 99.58 | 100
7 | JHARGRAM |  | Jhargram Division | AUGMENTATION OF POND WATER BASED BELPAHARI PIPE WATER SUPPLY SCHEME TO ACCOMMODATE FHTC AT BINPUR-II- BLOCKWITHIN JHARGRAM-DISTRICT, UNDER JHARGRAM DIVISION, PHE DTE. | SM/18428 | Augmentation | CLEANING COMPOUND PREMISES OF TARAFENI INTAKE POND WITHIN BELPAHARI PWSS UNDER JHARGRAM SUB DIVISION UNDER JHARGRAM DIVISION P.H.E. DTE. | Assistant Engineer | Junior Engineer RWS, Binpur-II Devlopment Block. | ORD/000143/2024-2025 | 975/JSD | 03/10/2024 | 17/10/2024 | RAMENDRA NATH KAR | 0.94 | 0 | 0 | 100
8 | JHARGRAM |  | Jhargram Division | AUGMENTATION OF POND WATER BASED BELPAHARI PIPE WATER SUPPLY SCHEME TO ACCOMMODATE FHTC AT BINPUR-II- BLOCKWITHIN JHARGRAM-DISTRICT, UNDER JHARGRAM DIVISION, PHE DTE. | SM/18428 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000114/2023-2024 | 279/JHD | 20/02/2024 | 20/02/2024 | Resource Division | 3.98 | 0 | 0 | 0
9 | JHARGRAM |  | Jhargram Division | AUGMENTATION OF POND WATER BASED BELPAHARI PIPE WATER SUPPLY SCHEME TO ACCOMMODATE FHTC AT BINPUR-II- BLOCKWITHIN JHARGRAM-DISTRICT, UNDER JHARGRAM DIVISION, PHE DTE. | SM/18428 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000002/2024-2025 | 2236/JHD | 29/11/2024 | 29/11/2024 | Resource Division | 44.92 | 0 | 0 | 0
10 | JHARGRAM |  | Jhargram Division | AUGMENTATION OF POND WATER BASED BELPAHARI PIPE WATER SUPPLY SCHEME TO ACCOMMODATE FHTC AT BINPUR-II- BLOCKWITHIN JHARGRAM-DISTRICT, UNDER JHARGRAM DIVISION, PHE DTE. | SM/18428 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000001/2024-2025 | 1094/JHD | 30/07/2024 | 30/07/2024 | Resource Division | 184.4 | 0 | 0 | 0
11 | JHARGRAM |  | Jhargram Division | AUGMENTATION OF POND WATER BASED BELPAHARI PIPE WATER SUPPLY SCHEME TO ACCOMMODATE FHTC AT BINPUR-II- BLOCKWITHIN JHARGRAM-DISTRICT, UNDER JHARGRAM DIVISION, PHE DTE. | SM/18428 | Augmentation | Repairing of Existing OHR of Capacity 90 Cum at WTP Site and Painting work of existing Boundary Wall including Minor Repairing work of PH & Boundary Wall of Belpahari PWSS situated at Naynagora within Binpur Il Block under Jhargram Sub Division under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer RWS, Binpur-II Devlopment Block.,Junior Engineer Binpur-I block | ORD/000261/2024-2025 | 72/JHD | 10/01/2025 | 24/02/2025 | RAMENDRA NATH KAR | 6.59 | 0 | 0 | 95
12 | JHARGRAM |  | Jhargram Division | AUGMENTATION OF POND WATER BASED BELPAHARI PIPE WATER SUPPLY SCHEME TO ACCOMMODATE FHTC AT BINPUR-II- BLOCKWITHIN JHARGRAM-DISTRICT, UNDER JHARGRAM DIVISION, PHE DTE. | SM/18428 | Augmentation | Repairing of Existing OHR of Capacity 450 Cum at Head Work Site of Belpahari PWSS situated at Hodra within Binpur II Block under Jhargram Sub Division under Midnapore Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram Sub-Division | ORD/000322/2024-2025 | 415/JHD | 25/02/2025 | 25/06/2025 | ANKITA ENTERPRISE | 20 | 0 | 0 | 0
13 | JHARGRAM |  | Jhargram Division | AUGMENTATION OF POND WATER BASED BELPAHARI PIPE WATER SUPPLY SCHEME TO ACCOMMODATE FHTC AT BINPUR-II- BLOCKWITHIN JHARGRAM-DISTRICT, UNDER JHARGRAM DIVISION, PHE DTE. | SM/18428 | Augmentation | Special Repair and Renovation of Pump House at Tarafeni intake pond for Augmentation of Belpahari Water Supply Scheme, Block: - Binpur II within Jhargram Sub Division under Jhargram Division, PHE Dte. ) [Ref. eNIT 05 OF AE/JSD OF 2024-2025, SL No. 04] | Assistant Engineer | Junior Engineer RWS, Binpur-II Devlopment Block. | ORD/000292/2024-2025 | 45/JSD | 13/01/2025 | 27/01/2025 | SAURABH KAR | 1.72 | 0 | 0 | 100
Total | [13 empty] | 1205.79 | 395.19 | 32.77