## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | CHIANBERA ZONE-IV (MALABATI) AND IT'S ADJOINING MOUJAS PWSS | SM/18604 | New | Supply, delivery and installation of horizontal split casing type centrifugal pumping machineries with suitable rated horizontal foot mounted Induction motor sets and allied electro-mechanical accessories for low lift and high lift pumping operations at Chianbera Zone-IV (Malabati) and its adjoining moujas surface water based piped water supply scheme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | Assistant Engineer | JE (M) | ORD/000214/2023-2024 | 2280/JMD | 10/08/2023 | 06/02/2024 | DIPALI CONSTRUCTION | 62.3 | 0 | 0 | 0
2 | JHARGRAM | Binpur-II | Jhargram Division | CHIANBERA ZONE-IV (MALABATI) AND IT'S ADJOINING MOUJAS PWSS | SM/18604 | New | Surveying, planning, designing ,delivery, erection, construction, commissioning and completion in all respect of all Civil, Electrical and Mechanical Works including all allied, related and enabling works for the proposed Chianbera (Malabati) Zone-IV Piped water supply Scheme based on surface water of Open Cast Stone Mine /pond at Chianbera, Block -Binpur-II district of Jhargram | Assistant Engineer | Junior Engineer-II | ORD/000310/2023-2024 | 1830/JHD | 27/10/2023 | 22/06/2026 | EFFLUENT AND WATER TREATMENT ENGINEERS PVT. LTD. | 789.8 | 0 | 0 | 0
3 | JHARGRAM | Binpur-II | Jhargram Division | CHIANBERA ZONE-IV (MALABATI) AND IT'S ADJOINING MOUJAS PWSS | SM/18604 | New | Laying of Distribution pipe line , Community Water Tank, Street Stand post & Inter Connection at Malaboti Village in Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000607/2023-2024 | 940/JSD | 02/11/2023 | 23/11/2023 | SAIKAT DANDAPAT | 2.52 | 0 | 0 | 100
Total | [13 empty] | 854.62 | 0 | 0