## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Binpur-I,Binpur-II | Jhargram Mechanical Division | CHAINBERA ZONE-III JOYPUR & ADJOINING MOUJAS PWSS | SM/18746 | New | Erection & commissioning of 30 (thirty) nos. standalone piped water supply schemes by constructing pump house, community tank, laying of distribution pipeline for providing FHTC with supply, delivery and installation of pumping machineries & allied Electro-Mechanical accessories at Ergoda G.P. in place of (Chainbera Zone-III Joypur (TSM/015566), Dharampur Zone-II Barbasuli (TSM/015892) w/s schemes under Binpur- II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | Driller-In-Charge | Junior Engineer | ORD/000228/2023-2024 | 2304/JMD | 14/08/2023 | 22/09/2025 | CONCORD ENGINEERING | 810.97 | 64.19 | 7.92 | 10
2 | JHARGRAM | Binpur-I,Binpur-II | Jhargram Mechanical Division | CHAINBERA ZONE-III JOYPUR & ADJOINING MOUJAS PWSS | SM/18746 | New | Conducting Geophysical investigation of twenty two (22) nos. sites in Bhelaidiha GP in Binpur-2 Block of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Driller-In-Charge | Junior Engineer | ORD/000222/2023-2024 | 2288/JMD | 10/08/2023 | 23/09/2023 | SUBHASIS ROY | 4.12 | 3.93 | 95.45 | 97
3 | JHARGRAM | Binpur-I,Binpur-II | Jhargram Mechanical Division | CHAINBERA ZONE-III JOYPUR & ADJOINING MOUJAS PWSS | SM/18746 | New | Erection & commissioning of 37 (thirty seven) nos. standalone piped water supply schemes by constructing pump house, community tank, laying of distribution pipeline for providing FHTC with supply, delivery and installation of pumping machineries & allied Electro-Mechanical accessories at Sandapara G.P. in place of (Chainbera Zone-I Darra (TSM/015763), Chainbera Zone-II Jarda (TSM/015919) and Chainbera Zone-III Joypur (TSM/015566) w/s schemes under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | Driller-In-Charge | Junior Engineer | ORD/000227/2023-2024 | 2303/JMD | 14/08/2023 | 31/12/2025 | CONCORD ENGINEERING | 1025.92 | 0 | 0 | 12
4 | JHARGRAM | Binpur-I,Binpur-II | Jhargram Division | CHAINBERA ZONE-III JOYPUR & ADJOINING MOUJAS PWSS | SM/18746 | New | 16 nos. Sinking of 125mm x 115mm x 200m Deep Tube wells by DTH method for installation of Submersible Pumping machinery for SILDA GP ( CHAINBERA ZONE-III JOYPUR PWSS) under Binpur-II Block under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000148/2023-2024 | 1406/JHD | 18/08/2023 | 17/09/2023 | SAIKAT DANDAPAT | 26.27 | 9.85 | 37.49 | 50
5 | JHARGRAM | Binpur-I,Binpur-II | Jhargram Mechanical Division | CHAINBERA ZONE-III JOYPUR & ADJOINING MOUJAS PWSS | SM/18746 | New | Supply & delivery of upvc consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicle for Dept. Rig unit for sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH / combination method at Srinathpur & its adjacent nine (09) nos. villages under ¿Ergoda¿ G.P. in place of {Chainbera Zone-III Joypur (TSM/015566)} w/s scheme under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | Driller-In-Charge | Junior Engineer | ORD/000373/2023-2024 | 2790/JMD | 08/09/2023 | 22/01/2025 | RSA ENTERPRISE | 22 | 18.45 | 83.87 | 91
6 | JHARGRAM | Binpur-I,Binpur-II | Jhargram Mechanical Division | CHAINBERA ZONE-III JOYPUR & ADJOINING MOUJAS PWSS | SM/18746 | New | Erection & commissioning of 22 (twenty two) nos. standalone piped water supply schemes by constructing pump house, community tank, laying of distribution pipeline for providing FHTC with supply, delivery and installation of pumping machineries & allied Electro-Mechanical accessories at Bhelaidiha G.P. in place of (Chainbera Zone-III Joypur (TSM/015566), Hijla (TSM/014334) and Banksol (TSM/015563) w/s schemes under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | DIC(D)_MMSD(D) | Junior Engineer | ORD/000322/2023-2024 | 3015/JMD | 20/10/2023 | 22/12/2025 | CONCORD ENGINEERING | 621.67 | 0 | 0 | 25
7 | JHARGRAM | Binpur-I,Binpur-II | Jhargram Division | CHAINBERA ZONE-III JOYPUR & ADJOINING MOUJAS PWSS | SM/18746 | New | 8 nos. Stand Alone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for SILDA GP ( CHAINBERA ZONE-III JOYPUR PWSS) under Binpur-II Block under Jhargram Division, PHE dte. (2nd Call Ref eNIT_36 of 2022-23 , SL No.-3 ) | Assistant Engineer | Junior Engineer-II | ORD/000362/2023-2024 | 1951/JHD | 22/11/2023 | 20/02/2024 | MONDAL PRECISION PRIVATE LIMITED | 194.87 | 40.2 | 20.63 | 25
8 | JHARGRAM | Binpur-I,Binpur-II | Jhargram Mechanical Division | CHAINBERA ZONE-III JOYPUR & ADJOINING MOUJAS PWSS | SM/18746 | New | Construction of (125 mm X 115 mm X 200 mtr.) RBTW by DTH/ combination method for providing FHTC at SITAPUR & its adjacent Seventy Three (73) nos. villages under Sandapara G.P. in place of (Chainbera Zone-I Darra (TSM/015763), Chainbera Zone-II Jarda (TSM/015919) and Chainbera Zone-III Joypur (TSM/015566) w/s schemes under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | Driller-In-Charge | Junior Engineer | ORD/000223/2023-2024 | 2297/JMD | 11/08/2023 | 06/01/2024 | MONDAL PRECISION PRIVATE LIMITED | 163.47 | 0 | 0 | 100
9 | JHARGRAM | Binpur-I,Binpur-II | Jhargram Mechanical Division | CHAINBERA ZONE-III JOYPUR & ADJOINING MOUJAS PWSS | SM/18746 | New | New service connection charges |  |  | BILL/00869/2023-2024 | 42/JMD | 29/12/2023 | 29/12/2023 | WBSEDCL | 0.21 | 0 | 0 | 0
10 | JHARGRAM | Binpur-I,Binpur-II | Jhargram Division | CHAINBERA ZONE-III JOYPUR & ADJOINING MOUJAS PWSS | SM/18746 | New | New Service Connection Charges for Hetyasol Chianbera Zone-III Joypur& Adjoining Moujas PWSS |  |  | BILL/00156/2024-2025 |  | 18/06/2024 | 18/06/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
11 | JHARGRAM | Binpur-I,Binpur-II | Jhargram Mechanical Division | CHAINBERA ZONE-III JOYPUR & ADJOINING MOUJAS PWSS | SM/18746 | New | Supply of diesel and lubricants for KLR/DR/DTH-500 unit during PWSS works under JJM.(scheme code -TSM/015566 ) |  |  | BILL/01023/2024-2025 | 355/JMD | 13/09/2024 | 13/09/2024 | SURAJ SERVICE STATION | 0.53 | 0 | 0 | 0
12 | JHARGRAM | Binpur-I,Binpur-II | Jhargram Mechanical Division | CHAINBERA ZONE-III JOYPUR & ADJOINING MOUJAS PWSS | SM/18746 | New | Providing fuel & lubricant for sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH / combination method at Jamirdiha & its adjacent nine (09) nos. villages under ¿Ergoda¿ G.P. in place of {Chainbera Zone-III Joypur (TSM/015566)} w/s scheme under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. |  |  | BILL/01135/2023-2024 | 16/JMD | 10/01/2024 | 10/01/2024 | SURAJ SERVICE STATION | 5 | 0 | 0 | 0
13 | JHARGRAM | Binpur-I,Binpur-II | Jhargram Division | CHAINBERA ZONE-III JOYPUR & ADJOINING MOUJAS PWSS | SM/18746 | New | New Service Connection Charges for Hizli, Chianbera Zone-III Joypur& Adjoining Moujas PWSS |  |  | BILL/00138/2024-2025 |  | 18/06/2024 | 18/06/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
14 | JHARGRAM | Binpur-I,Binpur-II | Jhargram Mechanical Division | CHAINBERA ZONE-III JOYPUR & ADJOINING MOUJAS PWSS | SM/18746 | New | New Service Connection Charges for Srinathpur PWSS. CHAINBERA ZONE-III JOYPUR & ADJOINING MOUJAS PWSS |  |  | BILL/01354/2024-2025 | 418/JMD | 22/11/2024 | 22/11/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
15 | JHARGRAM | Binpur-I,Binpur-II | Jhargram Mechanical Division | CHAINBERA ZONE-III JOYPUR & ADJOINING MOUJAS PWSS | SM/18746 | New | New Service Connection Charges for Baramsol PWSS. CHAINBERA ZONE-III JOYPUR & ADJOINING MOUJAS PWSS |  |  | BILL/01351/2024-2025 | 415/JMD | 22/11/2024 | 22/11/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
16 | JHARGRAM | Binpur-I,Binpur-II | Jhargram Mechanical Division | CHAINBERA ZONE-III JOYPUR & ADJOINING MOUJAS PWSS | SM/18746 | New | New Service Connection Charges for Jhatiara PWSS |  |  | BILL/01353/2024-2025 | 417/JMD | 22/11/2024 | 22/11/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
17 | JHARGRAM | Binpur-I,Binpur-II | Jhargram Mechanical Division | CHAINBERA ZONE-III JOYPUR & ADJOINING MOUJAS PWSS | SM/18746 | New | New Service Connection Charges for Pakurasol PWSS.CHAINBERA ZONE-III JOYPUR & ADJOINING MOUJAS PWSS |  |  | BILL/01352/2024-2025 | 416/JMD | 22/11/2024 | 22/11/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
18 | JHARGRAM | Binpur-I,Binpur-II | Jhargram Division | CHAINBERA ZONE-III JOYPUR & ADJOINING MOUJAS PWSS | SM/18746 | New | New Service Connection Charges for Chianbera zone-III joypur & Adjoining Moujas PWSS Pankanali |  |  | BILL/00803/2024-2025 |  | 18/06/2024 | 18/06/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
19 | JHARGRAM | Binpur-I,Binpur-II | Jhargram Mechanical Division | CHAINBERA ZONE-III JOYPUR & ADJOINING MOUJAS PWSS | SM/18746 | New | New Service connection charges. |  |  | BILL/01148/2023-2024 | 31/JMD | 18/01/2024 | 18/01/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
20 | JHARGRAM | Binpur-I,Binpur-II | Jhargram Mechanical Division | CHAINBERA ZONE-III JOYPUR & ADJOINING MOUJAS PWSS | SM/18746 | New | New Service connection charges. |  |  | BILL/01346/2023-2024 | 9/JMD | 01/03/2024 | 01/03/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
21 | JHARGRAM | Binpur-I,Binpur-II | Jhargram Mechanical Division | CHAINBERA ZONE-III JOYPUR & ADJOINING MOUJAS PWSS | SM/18746 | New | New service connection |  |  | BILL/01297/2023-2024 | 68/JMD | 12/02/2024 | 12/02/2024 | WBSEDCL | 0.84 | 0 | 0 | 0
22 | JHARGRAM | Binpur-I,Binpur-II | Jhargram Mechanical Division | CHAINBERA ZONE-III JOYPUR & ADJOINING MOUJAS PWSS | SM/18746 | New | Supply delivery of UPVC consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (125 mm x 115 mm x 200 mtr.) RBTW by DTH / Combination method at Sandapara G.P. in place of (Chainbera, Zone-I Darra (SM/17930), Chainbera, Zone-II Jarda (SM/17925) and Chainbera, Zone-III Joypur (SM/18746) w/s schemes under Binpur-II Block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | Driller-In-Charge | JE (M) | ORD/000961/2024-2025 | 193/JMD | 30/01/2025 | 12/07/2026 | MONDAL PRECISION PRIVATE LIMITED | 58.26 | 0 | 0 | 20
Total | [13 empty] | 2936 | 136.62 | 4.65