## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at Ramgarh, Zone-I w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | SM/16707 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Dahamunda and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | Assistant Engineer,DIC(D)_MMSD(D) | Junior Engineer | ORD/000290/2023-2024 | 2507/JMD | 25/08/2023 | 01/01/2026 | DAS CONSTRUCTION | 37.56 | 0 | 0 | 45
2 | JHARGRAM |  | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at Ramgarh, Zone-I w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | SM/16707 | Solarisation | Quotation for meter installation for solar power plant for Ramgarh zone-1 T/W-1. |  |  | BILL/01263/2024-2025 | 399/JMD | 25/10/2024 | 25/10/2024 | WBSEDCL | 0.01 | 0 | 0 | 0
3 | JHARGRAM |  | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at Ramgarh, Zone-I w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | SM/16707 | Solarisation | Quotation for meter installation for solar power plant for Ramgarh zone-2 T/W-1. |  |  | BILL/01264/2024-2025 | 400/JMD | 25/10/2024 | 25/10/2024 | WBSEDCL | 0.01 | 0 | 0 | 0
4 | JHARGRAM |  | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at Ramgarh, Zone-I w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | SM/16707 | Solarisation | Qutation for meter installation for solar power plant at Binpur 1 . |  |  | BILL/01594/2024-2025 | 460/JMD | 21/01/2025 | 21/01/2025 | WBSEDCL | 0.15 | 0 | 0 | 0
Total | [13 empty] | 37.72 | 0 | 0