## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Jhargram Mechanical Division | providing solarization of WBSEDCL energised pumping installation at Balishira And Adjoining Moujas piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram | SM/16709 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Bandarbani and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000327/2023-2024 | 2774/JMD | 05/09/2023 | 03/03/2024 | SWITCHING AVO ELECTRO POWER LTD | 64.39 | 0 | 0 | 0
Total | [13 empty] | 64.39 | 0 | 0