## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at KAPGARI AND IT'S ADJOINING MOUJAS piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | SM/17056 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Parihati and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | DIC(D)_MMSD(D) | JE (M) | ORD/000326/2023-2024 | 2773/JMD | 05/09/2023 | 03/03/2024 | SWITCHING AVO ELECTRO POWER LTD | 77.27 | 0 | 0 | 0
Total | [13 empty] | 77.27 | 0 | 0