## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at BELIA AND ADJOINING MOUJAS piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | SM/17076 | Solarisation | Providing solarization of WBSEDCL energised pumping installation at Parihati and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | DIC(D)_MMSD(D) | JE (M) | ORD/000326/2023-2024 | 2773/JMD | 05/09/2023 | 03/03/2024 | SWITCHING AVO ELECTRO POWER LTD | 77.27 | 0 | 0 | 0
2 | JHARGRAM |  | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at BELIA AND ADJOINING MOUJAS piped water supply scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | SM/17076 | Solarisation | Supply, delivery and installation of Vinyl Sign board for depicting the scheme details of Belia and adjacent water supply schemes for ongoing Solarisation works for the purpose of Geotagging in JJM under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer | JE (M) | ORD/001380/2023-2024 | 3062/JMD | 14/03/2024 | 24/03/2024 | MUKHERJEE ART CENTRE | 5.28 | 5.17 | 97.84 | 100
Total | [13 empty] | 82.55 | 5.17 | 6.26