## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Providing FHTC through Retrofitting at Metaldhaora, Booth No. 05, Vill - Kendra, Block - Pandabeswar of Kendra Khottamdih Water Supply Scheme under RCFA Division-I PHE Dte. (Part-B) | Assistant Engineer 2 | Junior Engineer | ORD/000105/2020-2021 | 1159/RCD I | 23/12/2020 | 12/01/2021 | VISUVIOUS | 4.47 | 6.17 | 138.06 | 0
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Providing FHTC through Retrofitting at Salanpur Mouza, Vill-Salanpur, Block-Salanpur of Salanpur Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000215/2020-2021 | 432 /RCD-I | 04/03/2021 | 18/04/2021 | GITA CONSTRUCTION | 46.13 | 75.61 | 163.9 | 0
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Providing FHTC through Retrofitting at Metaldhaora, Booth No. 05, Vill - Kendra, Block - Pandabeswar of Kendra Khottamdih Water Supply Scheme under RCFA Division-I PHE Dte. (Part-A) | Assistant Engineer 2 | Junior Engineer | ORD/000104/2020-2021 | 1158/RCD I | 23/12/2020 | 12/01/2021 | M/S MONDAL CONSTRUCTION | 4.44 | 6.17 | 139.07 | 0
4 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Providing FHTC through Retrofitting at Chatadhawra, Booth No. 02, Vill - Kendra, Block - Pandabeswar of Kendra Khottamdih Water Supply Scheme under RCFA Division-I PHE Dte. (Part-C) | Assistant Engineer 2 | Junior Engineer | ORD/000103/2020-2021 | 1157/RCD I | 23/12/2020 | 12/01/2021 | DHRUBA ENTERPRISE | 4.45 | 6.13 | 137.94 | 0
5 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Providing FHTC through Retrofitting at Chatadhawra, Booth No. 02, Vill - Kendra, Block - Pandabeswar of Kendra Khottamdih Water Supply Scheme under RCFA Division-I PHE Dte. (Part-A) | Assistant Engineer 2 | Junior Engineer | ORD/000122/2020-2021 | 1155/RCD I | 23/12/2020 | 12/01/2021 | ZEROTH CONTROL SYSTEM | 4.4 | 5.68 | 129.05 | 0
6 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Providing FHTC through Retrofitting at Metaldhaora, Booth No. 05, Vill - Kendra, Block - Pandabeswar of Kendra Khottamdih Water Supply Scheme under RCFA Division-I PHE Dte. (Part-C) | Assistant Engineer 2 | Junior Engineer | ORD/000106/2020-2021 | 1160/RCD I | 23/12/2020 | 12/01/2021 | MS KALYAN ENTERPRISE | 4.45 | 6.37 | 142.98 | 0
7 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Providing FHTC through Retrofitting at Chatadhawra, Booth No. 02, Vill - Kendra, Block - Pandabeswar of Kendra Khottamdih Water Supply Scheme under RCFA Division-I PHE Dte. (Part-B) | Assistant Engineer 2 | Junior Engineer | ORD/000102/2020-2021 | 1156 /RCD I | 23/12/2020 | 12/01/2021 | A.K.CONSTRUCTION | 4.43 | 6.18 | 139.51 | 0
8 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Providing FHTC through retrofitting at Dhandardihi Mouza, vill-Madanpur, Block -Andal of Dhandadihi Water supply scheme under RCFA Div-I PHE Dte. |  |  | VCH/000832/2020-2021 | 45/21-22 | 15/07/2021 | 15/07/2021 | MACHINO TECHNO | 25.79 | 0 | 0 | 0
9 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Continuation work order for Providing FHTC through Retrofitting at Salanpur Mouza, Vill-Salanpur, Block-Salanpur of Salanpur Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000098/2021-2022 | 816/RCD-I | 19/04/2021 | 03/06/2021 | GITA CONSTRUCTION | 11.84 | 9.17 | 77.44 | 0
10 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Acceptance cum work order for Laying of different dia UPVC/HDPE pipe line for extension of distribution system regarding FHTC work at Kumardiha mouza of Ratibati water supply scheme under RCFA Div-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000160/2021-2022 | 1585/RCD-I | 07/09/2021 | 07/10/2021 | M/S B.K. CONSTRUCTION | 14.42 | 13.73 | 95.24 | 0
11 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Sinking of 3 (Three) nos 200 mm dia River Bed Tube Wells including repairing work of 100 mm dia Collecting Mains which were damaged due to flood in the month of July - August & etc. allied works at River Damodar under Ratibati Water Supply Scheme under RCFA Div-I PHE Dte. (sl no 05) |  |  | ORD/000278/2021-2022 | 1937/RCD I | 09/11/2021 | 29/11/2021 | M/S PIONEER CONSTRUCTION | 3.17 | 2.92 | 92.12 | 0
12 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Hard rock cutting, laying of different dia UPVC pipe line for extension of distribution system regarding FHTC work at Chelod mouza of Ratibati W/S Scheme under RCFA Div-I PHE Dte.(Sl no 10) | Assistant Engineer 2 | Junior Engineer | ORD/000464/2021-2022 | 2467/RCD I | 31/12/2021 | 15/01/2022 | MACHINO TECHNO | 3.06 | 2.82 | 91.89 | 0
13 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Laying of different dia UPVC pipeline for extension system regarding FHTC work at Chelod village of Ratibati W/S Scheme under RCFA Div-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000488/2021-2022 | 2464/RCD-I | 31/12/2021 | 15/01/2022 | MOTIONMASS TECHNO (OPC) PRIVATE LIMITED | 4.81 | 2.35 | 48.81 | 0
14 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Providing FHTC through retrofitting at Kumardiha village area of Chold mouza, GP -Ratibati Block Raniganj of Ratibati water supply scheme under RCFA Division-I PHE Dte.(Sl no 08) | Assistant Engineer 2 | Junior Engineer | ORD/000462/2021-2022 | 2465/RCD I | 31/12/2021 | 07/01/2022 | D.S.C. CONCERN | 4.81 | 4.81 | 99.9 | 0
15 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Laying UPVC pipeline for FHTC work for Dhandadihi W/S Scheme under RCFA Div-I, PHE Dte.(Sl no 01) | Assistant Engineer 2 | Junior Engineer | ORD/000456/2021-2022 | 2458/RCD I | 31/12/2021 | 10/01/2022 | MACHINO TECHNO | 3.83 | 3.82 | 99.61 | 0
16 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Laying of 50 mm dia PVC pipe line and construction of different dia valve chamber, FHTC work and etc. allied works at Kendra area under RCFA Division-I PHE Dte. (Sl No. 03) | Assistant Engineer 2 | Junior Engineer | ORD/000326/2021-2022 | 2175/RCD I | 06/12/2021 | 16/12/2021 | MS KALYAN ENTERPRISE | 4.57 | 4.47 | 97.79 | 0
17 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Acceptance cum work order for Laying of different dia PVC/HDPE pipe line for extension of distribution system regarding FHTC work at Ratibati Mouza of Ratibati Water Supply Scheme under RCFA Div-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000558/2021-2022 | 581/RCD-I | 02/03/2022 | 17/03/2022 | SOMNATH SAMANTA | 9.58 | 9.55 | 99.64 | 0
18 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Supplying, aligning and laying of HDPE pipe line for byepass water supply arrangement to Chapui village under Ratibati Water Supply Scheme under RCFA Division-I PHE Dte. (Part-A)(Sl no 02) | Assistant Engineer 2 | Junior Engineer | ORD/000608/2021-2022 | 631/RCD-1 | 09/03/2022 | 24/03/2022 | SWATI CORPORATION | 4.75 | 4.75 | 100 | 0
19 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Acceptance cum work order for Emergency supplying aligning and laying of different dia HDPE pipe line for by pass water supply arrangement to Roypara, Singhapara and adjacent areas under Ratibati Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000007/2022-2023 | 937/RCD-I | 26/04/2022 | 26/05/2022 | M/S MONDAL ENTERPRISE | 24.23 | 24.17 | 99.79 | 0
20 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Emergency supplying. Aligning and laying of HDPE pipe line for bypass water supply arrangement to Chapui village under Ratibati water supply scheme under RCFA Division-I PHE Dte. (Part-C)(Sl no 04) | Assistant Engineer 2 | Junior Engineer | ORD/000610/2021-2022 | 633/RCD 1 | 09/03/2022 | 24/03/2022 | SWATI CORPORATION | 4.84 | 4.82 | 99.59 | 0
21 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Emergency supplying. Aligning and laying of HDPE pipe line for bypass water supply arrangement to Chapui village under Ratibati water supply scheme under RCFA Division-I PHE Dte. (Part-B)(Sl no 3) | Assistant Engineer 2 | Junior Engineer | ORD/000609/2021-2022 | 632/RCD 1 | 09/03/2022 | 24/03/2022 | SWATI CORPORATION | 4.76 | 4.72 | 99.27 | 0
22 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Laying of Different dia UPVC /PVC pipeline for extention of distribution system regarding FHTC work at Saora Mouza of Ratibati Water supply Scheme under RCFA Div-I PHE Dte. (Sl No 17) | Assistant Engineer 2 | Junior Engineer | ORD/000602/2021-2022 | 280/RCD-I | 01/02/2022 | 03/03/2022 | A. CONSTRUCTION CO. | 4.81 | 4.81 | 100 | 0
23 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Laying of HDPE pipe line and other repairing work of distribution at Ratibati Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 15) | Assistant Engineer 2 | Junior Engineer | ORD/000152/2022-2023 | 1446/RCD I | 27/06/2022 | 11/08/2022 | M/S MONDAL ENTERPRISE | 2.54 | 2.49 | 98.16 | 0
24 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Additional laying of different dia UPVC pipeline for extension of distribution system regarding FHTC work at Chelod mouza of Ratibati W/S Scheme under RCFA Div-I PHE Dte.(Sl no 09) | Assistant Engineer 2 | Junior Engineer | ORD/000463/2021-2022 | 2466/RCD I | 31/12/2021 | 15/01/2022 | MACHINO TECHNO | 4.78 | 4.55 | 95.04 | 0
25 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Repairing of 6 (Six) nos panel board, panel board wiring, Supply and installation of 10 HP submersible pump & motor & cable laying & other allied works at Ratibati river bed pump house site of Ratibati W/S Scheme under RCFA Division-I PHE Dte. (Sl No. 02) |  |  | VCH/000069/2022-2023 | 172/22-23 | 13/06/2022 | 13/06/2022 | M/S PIONEER CONSTRUCTION | 4.67 | 0 | 0 | 0
26 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Dhandardihi Mouza, Vill-Madanpur, Block-Andal of Dhandardihi Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000357/2020-2021 | 1032/RCD-I | 05/11/2020 | 05/12/2020 | MACHINO TECHNO | 43.84 | 13.66 | 31.16 | 0
27 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at ECL 3 Nos Colliery area, Vill - Kendra, Block - Pandabeswar of Kendra Khottamdih Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 05) | Assistant Engineer 2 | Junior Engineer | ORD/000118/2020-2021 | 1193/RCD-I | 24/12/2020 | 23/01/2021 | RELIABLE ENGINEERS CO-OP CONSTRUCTION SOCIETY LTD. | 16.09 | 22.19 | 137.88 | 0
28 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Acceptance cum work order Providing FHTC of retrofitting at Kumardihi village (Left out portion) of kumardiha Mouza, GP-Ratibati, Block Raniganj of Ratibati Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 12) | Assistant Engineer 2 | Junior Engineer | ORD/000057/2023-2024 | 1742/RCD I | 11/05/2023 | 26/05/2023 | D.S.C. CONCERN | 7.9 | 7.51 | 95.03 | 0
29 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Chapui (CT) Mouza, G.P.-Ratibati, Block-Raniganj of Ratibati Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 02) | Assistant Engineer 2 | Junior Engineer | ORD/000110/2020-2021 | 1185/RCD-I | 24/12/2020 | 23/01/2021 | SWATI CORPORATION | 39.19 | 58.25 | 148.65 | 0
30 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Acceptance cum Work Order for Providing FHTC through Retrofitting at Kumardiha Mouza, G.P.-Ratibati, Block-Raniganj of Ratibati Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 03) | Assistant Engineer 2 | Junior Engineer | ORD/000111/2020-2021 | 1186/RCD-I | 24/12/2020 | 23/01/2021 | M/S B.K. CONSTRUCTION | 19.63 | 35.64 | 181.5 | 0
31 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Seora Mouza, G.P.- Ratibati, Block- Raniganj of Ratibati Water supply scheme under RCFA Division-I, P.H.E. Dte. (Sl No. 05) | Assistant Engineer 2 | Junior Engineer | ORD/000112/2020-2021 | 1187/RCD-I | 24/12/2020 | 23/01/2021 | A. CONSTRUCTION CO. | 20.48 | 39.53 | 193.02 | 0
32 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Acceptance cum Work Order for Providing FHTC through Retrofitting at Chelod Mouza, G.P.-Tirat, Block-Raniganj of Ratibati Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 01) | Assistant Engineer 2 | Junior Engineer | ORD/000108/2020-2021 | 1167/RCD-I | 23/12/2020 | 22/01/2021 | MRITYUNJOY MUKHERJEE & CO. | 37.97 | 31.34 | 82.54 | 0
33 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Kendra Mouza, Booth No. 1 (Kendra Gram), Vill - Kendra, Block - Pandabeswar of Kendra Khottamdih Water Supply Scheme under RCFA Division-I PHE Dte. (Part-A) (Sl No. 06) | Assistant Engineer 2 | Junior Engineer | ORD/000119/2020-2021 | 1194/RCD-I | 24/12/2020 | 23/01/2021 | DURGADAS MONDAL | 9.08 | 10.62 | 116.96 | 0
34 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Mines Quarter Booth No. 3, Vill - Kendra, Block - Pandabeswar of Kendra Khottamdih Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 02) | Assistant Engineer 2 | Junior Engineer | ORD/000115/2020-2021 | 1190/RCD-I | 24/12/2020 | 23/01/2021 | SIMA ENTERPRISE | 9.93 | 12.38 | 124.61 | 0
35 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Khottamdih Village, Vill - Kendra, Block - Pandabeswar of Kendra Khottamdih Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 04) | Assistant Engineer 2 | Junior Engineer | ORD/000117/2020-2021 | 1192/RCD-I | 24/12/2020 | 23/01/2021 | M/S MONI TRADERS | 14.1 | 19.45 | 137.95 | 0
36 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Kendra Mouza, Booth No. 1 (Kendra Gram), Vill - Kendra, Block - Pandabeswar of Kendra Khottamdih Water Supply Scheme under RCFA Division-I PHE Dte. (Part-B) (Sl No. 07) | Assistant Engineer 2 | Junior Engineer | ORD/000120/2020-2021 | 1195/RCD-I | 24/12/2020 | 23/01/2021 | UNITED CONSTRUCTION | 9.15 | 13.54 | 148 | 0
37 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Ratibati (Part-II), G.P.- Ratibati, Block- Raniganj of Ratibati Water supply scheme under RCFA Division-I, P.H.E. Dte. (Sl No. 06) | Assistant Engineer 2 | Junior Engineer | ORD/000113/2020-2021 | 1188/RCD-I | 24/12/2020 | 23/01/2021 | SOMNATH SAMANTA | 22.88 | 40 | 174.86 | 0
38 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Acceptance cum work order for Supplying, aligning and laying of DI & HDPE pipe line for water supply arrangement to Kumardiha village under Ratibati W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000156/2021-2022 | 1584/RCD-I | 07/09/2021 | 07/10/2021 | M/S MONDAL ENTERPRISE | 20.03 | 19.9 | 99.37 | 0
39 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Acceptance cum work order for Supplying, Aligning and laying of HDPE pipe line for FHTC work at Chapui mouzas of Ratibati W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000162/2021-2022 | 1587/RCD-I | 07/09/2021 | 07/10/2021 | SWATI CORPORATION | 25.46 | 17.1 | 67.18 | 0
40 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Acceptance cum work order for Supply and laying of 16 sqmm x 4 core Al armored PVC power cable and 10 HP Submersible Pump at Ratibati river bed pump house site damaged due to spreading of fire of Ratibati Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000298/2021-2022 | 2030/RCD-I | 24/11/2021 | 04/12/2021 | M/S PIONEER CONSTRUCTION | 11.72 | 11.72 | 100 | 0
41 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Acceptance cum work order for Supplying, laying and aligning distribution branch main from distribution main including providing FHTC work at Bilpahari General Para (Re-habilitated village) under Kendra Khottamdihi Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000295/2021-2022 | 2027/RCD-I | 24/11/2021 | 24/12/2021 | SWATI CORPORATION | 39.08 | 31.16 | 79.74 | 0
42 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Acceptance cum work order for Supplying, laying and aligning distribution branch main from distribution main including providing FHTC work at Bilpahari Bauri Para (Re-habilitated village) under Kendra Khottamdihi Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000294/2021-2022 | 2026/RCD-I | 24/11/2021 | 24/12/2021 | RANJIB GHATAK | 26.95 | 22.7 | 84.23 | 0
43 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Providing FHTC through retrofitting at Damra rural and adjacent area of Chelod mouza, G.P, Tirat , GP Block Raniganj of Ratibati water supply scheme under RCFA Division-I PHE Dte.(Sl no 11) |  |  | ORD/000465/2021-2022 | 2468/RCD I | 31/12/2021 | 10/01/2022 | GOPAL CONSTRUCTION | 4.68 | 4.68 | 100.01 | 0
44 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Supply, fitting fixing railling, grill, painting of pump house, CWR, chlorine room etc and allied works at Ratibati H/W and Tirat Colliery H/W site under RCFA Division-I PHE Dte. (Sl No. 03) |  |  | ORD/000359/2021-2022 | 2203/RCD I | 06/12/2021 | 27/12/2021 | SOMNATH SAMANTA | 3.53 | 2.97 | 84.16 | 0
45 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Providing FHTC through retrofitting at Chelod village area (Part-A) of Chelod mouza, GP Ratibati, Block-Raniganj of Ratibati Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 15) | Assistant Engineer 2 | Junior Engineer | ORD/000601/2021-2022 | 278/RCD-I | 01/02/2022 | 03/03/2022 | M/S MONDAL CONSTRUCTION | 4.84 | 4.55 | 94.03 | 0
46 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at ECL 2 Nos Colliery area, Vill - Kendra, Block - Pandabeswar of Kendra Khottamdih Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 01) | Assistant Engineer 2 | Junior Engineer | ORD/000114/2020-2021 | 1189/RCD-I | 24/12/2020 | 23/01/2021 | GITASHREE FABRICATION | 12.68 | 19.38 | 152.82 | 0
47 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000009/2021-2022 | 439/RCD-I | 21/02/2022 | 21/02/2022 | Resource Division | 11 | 0 | 0 | 0
48 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Hiring of Maxi Cab (Non Air- conditioned ) bharatstage - III/BS-III purchased on after 01.05.2008 with Diesel / LPG/CNG Engine. as when required basis for supervision of FHTC related works under JJM) of RCFA Div-I, PHE Dte Govt, of West Bengal ( w.e.f 16.08.2023 to 15.02.2024) | Assistant Engineer 2 | Junior Engineer | ORD/000354/2023-2024 | 2420/RCD-I | 11/08/2023 | 11/02/2024 | PRAMIT CHATTERJEE | 0.9 | 2.37 | 263.55 | 100
49 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Dom Para Both No. 4, Vill - Kendra, Block - Pandabeswar of Kendra Khottamdih Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 03) | Assistant Engineer 2 | Junior Engineer | ORD/000116/2020-2021 | 1191/RCD-I | 24/12/2020 | 23/01/2021 | DAWN CONSTRUCTION | 18.7 | 7.57 | 40.5 | 0
50 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Supply of 10 mm NB Gun-metal ferrule for Providing FHTC through Retrofitting at Chapui (CT) Mouza, G.P.- Ratibati, Block- Raniganj of Ratibati Water supply scheme under RCFA Division-I, P.H.E. Dte. (Sl No 17) | Assistant Engineer 2 | Junior Engineer | ORD/000339/2020-2021 | 363/RCD I | 26/02/2021 | 05/03/2021 | SWATI CORPORATION | 4.68 | 9.36 | 200 | 0
51 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Supply of 10 mm NB Gun-metal ferrule for Providing FHTC through Retrofitting at Chelod Mouza, G.P.- Tirat, Block- Raniganj of Ratibati Water supply scheme under RCFA Division-I, P.H.E. Dte.(SL NO 18) | Assistant Engineer 2 | Junior Engineer | ORD/000341/2020-2021 | 364/RCD I | 26/02/2021 | 05/03/2021 | MRITYUNJOY MUKHERJEE & CO. | 4.66 | 9.33 | 200 | 0
52 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Annual Maintenance Contract (AMC) for Computers, Prnters, UPS & other related peripherals installed at office chamber of the Assistant Engineer, Junior Engineers, DPMU, IEC under of the Executive Engineer, RCFA Division-I PHE Dte. (Period from 01.07.2023 to 31.12.2023) | Assistant Engineer 2 | Junior Engineer | ORD/000308/2023-2024 | 2039/RCD-I | 30/06/2023 | 31/12/2023 | SHARMA ENGINEERING WORKS | 0.9 | 0.9 | 100 | 100
53 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Arrangement of breakfast and lunch box for DWSM meeting held on 13.01.2024 at ADDA Conference hall |  |  | BILL/01309/2023-2024 | 494/23-24 | 25/01/2024 | 25/01/2024 | SHARMA ENGINEERING WORKS | 0.1 | 0 | 0 | 0
54 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Supply of it peripherals |  |  | BILL/01741/2023-2024 | 497/23-24 | 25/01/2024 | 25/01/2024 | MUKHERJEE TRADERS | 0.43 | 0 | 0 | 0
55 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Hiring charge of Maxi cab (non conditioned) stage II / BS III for ofice use Veh WB 37 D 9526 |  |  | BILL/01746/2023-2024 | 553/23-24 | 27/02/2024 | 27/02/2024 | NIRMALA TRADERS | 0.06 | 0 | 0 | 0
56 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Arrangemen of breakfast and lunch box for DWSM meeting held on 13.01.2024 at ADDA Conferenc hall |  |  | BILL/01310/2023-2024 | 495/23-24 | 25/01/2024 | 25/01/2024 | SHARMA ENGINEERING WORKS | 0.09 | 0 | 0 | 0
57 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Supply of computer desktop |  |  | BILL/01742/2023-2024 | 498/23-24 | 25/01/2024 | 25/01/2024 | MUKHERJEE TRADERS | 0.42 | 0 | 0 | 0
58 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Hirig of maxi cab state II/BS III for the office use of the Assistant Engineer |  |  | BILL/01747/2023-2024 | 554/23-24 | 27/02/2024 | 27/02/2024 | NIRMALA TRADERS | 0.06 | 0 | 0 | 0
59 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Vehicle bill for the month of Dec 2023 |  |  | BILL/01750/2023-2024 | 529/23-24 | 06/02/2024 | 06/02/2024 | SHYAMAL MAJI | 0.15 | 0 | 0 | 0
60 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Repair & maintenance on contract basis of computers and local area network under SERCFA Div-I PHE Dte. |  |  | BILL/01745/2023-2024 | 499/23-24 | 01/02/2024 | 01/02/2024 | KALPANA ENTERPRISE | 0.46 | 0 | 0 | 0
61 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Fuel bill of Ranajit Auto vehicle no WB 37 D 0482 |  |  | BILL/01749/2023-2024 | 571/23-24 | 27/02/2024 | 27/02/2024 | RANAJIT AUTO | 0.19 | 0 | 0 | 0
62 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Hire charges bill for vehicle no WB 37 D0482 for the month of January |  |  | BILL/01748/2023-2024 | 570/23-24 | 27/02/2024 | 27/02/2024 | SHYAMAL MAJI | 0.15 | 0 | 0 | 0
63 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | AMC for xerox machine |  |  | BILL/01743/2023-2024 | 455/23-24 | 04/01/2024 | 04/01/2024 | WORK CHARGE BILL | 0.21 | 0 | 0 | 0
64 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Fuel bill for shyamal Maji for the month of Dec 23 |  |  | BILL/01751/2023-2024 | 530/23-24 | 08/02/2024 | 08/02/2024 | RANAJIT AUTO | 0.17 | 0 | 0 | 0
65 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Acceptance cum work order for Providing FHTC through retrofitting at Saheb Bangla & allied areas at Khottamdihi Block Pandabeswar of Kendra Khottamdihi Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer 4 | Junior Engineer | ORD/000039/2021-2022 | 978/RCD-I | 17/06/2021 | 14/09/2025 | A.K. SIKDAR | 19.13 | 26.36 | 137.79 | 100
66 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Acceptance cum work order for Interconnection work including Augurboring, supply of value, construction of valve, construction of valve chamber within command under Dabor OHR under Retrofitting of 4 Nos. PWSS for providing FHTC under RCFA Division-I PHE Dte (sl. no-6). | Assistant Engineer 2 | Junior Engineer | ORD/000772/2022-2023 | 804/RCD-I | 06/03/2023 | 16/03/2023 | RELIABLE ENGINEERS CO-OP CONSTRUCTION SOCIETY LTD. | 12.51 | 12.28 | 98.14 | 0
67 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Acceptance cum work order Supplying Laying 90 mm dia HDPE pipe line, sluice valve chamber, Street Stand Post and other allied works within Amritnagar Rising Main & Distribution of Tirat Colliery W/S Scheme Zone under Improvement Part-II W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000943/2022-2023 | 1279/RCD-I | 27/03/2023 | 11/04/2023 | MS KALYAN ENTERPRISE | 4.81 | 4.8 | 99.83 | 0
68 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Acceptance cum work order Additional work for sinking 3 nos 200 mm dia river bed tube wells and allied repairing work in river Damodar including surging of tube wells at Damalia H/W site under Tirat Mouza W/S Scheme under RCFA Division-I PHE Dte. (Sl No. 11) | Assistant Engineer 2 | Junior Engineer | ORD/000002/2023-2024 | 1387/RCD-I | 11/04/2023 | 23/04/2023 | D.S.C. CONCERN | 6.88 | 6.87 | 99.92 | 0
69 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Acceptance cum work order Construction of Street Stand Post, Sluice Valve Chamber and Aligning Laying HDPE pipe in different places (Nimcha, Damra, Chelod Bouripara, Tirat Hospital Etc.) under Tirat Colliery W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000944/2022-2023 | 1281/RCD-I | 27/03/2023 | 11/04/2023 | MS KALYAN ENTERPRISE | 4.57 | 4.57 | 99.97 | 80
70 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Acceptance cum work order Emergency repairing of damaged collecting main in river Damodar and allied works at Surjanagar H/W site of Surjanagar W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000924/2022-2023 | 1257/RCD-I | 27/03/2023 | 11/04/2023 | MD. JAWED KHAN | 4.31 | 4.15 | 96.2 | 0
71 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Providing FHTC through retrofitting at Chelod village area (Part-B) of Chelod mouza, GP Ratibati, Block-Raniganj of Ratibati Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 16) | Assistant Engineer 2 | Junior Engineer | ORD/000606/2021-2022 | 279/RCD-I | 01/02/2022 | 03/03/2022 | M/S U.G. ENTERPRISE | 4.84 | 4.84 | 100 | 100
72 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Acceptance cum work order 300 mm dia MS Bye pass line and interconnection work at Khandra OHR site and allied works of Dakhin Khandra and Mahira adjacent area under Retrofitting of 4 Nos. Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000957/2022-2023 | 1056/RCD-I | 23/03/2023 | 07/04/2023 | UNITED CONSTRUCTION | 15.47 | 15.47 | 99.99 | 0
73 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000011/2025-2026 | 2533/RCD-I | 01/09/2025 | 01/09/2025 | Resource Division | 17.96 | 0 | 0 | 0
Total | [13 empty] | 747.06 | 763.39 | 102.19