## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Chotkara Kanskuli PWSS (Zone-I) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District | SM/07558 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Chotkara Kanskuli PWSS (Zone-I), Block- Salanpur & Barabani of Chotkara- Kanskuli Water supply scheme under RCFA Division-I, P.H.E. Dte. [Part-A] | Assistant Engineer 1 | Junior Engineer | ORD/000015/2021-2022 | 952/RCD-I | 07/06/2021 | 07/07/2021 | DIP CONSTRUCTION | 23.01 | 4.1 | 17.82 | 0
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Chotkara Kanskuli PWSS (Zone-I) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District | SM/07558 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Chotkara Kanskuli PWSS (Zone-I), Block- Salanpur & Barabani of Chotkara- Kanskuli Water supply scheme under RCFA Division-I, P.H.E. Dte. [Part-D] | Assistant Engineer 1 | Junior Engineer | ORD/000018/2021-2022 | 955/RCD-I | 07/06/2021 | 07/07/2021 | MD AAMIR KHAN | 22.98 | 45.44 | 197.76 | 0
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Chotkara Kanskuli PWSS (Zone-I) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District | SM/07558 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Chotkara Kanskuli PWSS (Zone-I), Block- Salanpur & Barabani of Chotkara- Kanskuli Water supply scheme under RCFA Division-I, P.H.E. Dte. [Part-B] | Assistant Engineer 1 | Junior Engineer | ORD/000016/2021-2022 | 953/RCD-I | 07/06/2021 | 07/07/2021 | TARA MA ENTERPRISE | 23.02 | 45.17 | 196.22 | 0
4 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Chotkara Kanskuli PWSS (Zone-I) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District | SM/07558 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Chotkara Kanskuli PWSS (Zone-I), Block- Salanpur & Barabani of Chotkara- Kanskuli Water supply scheme under RCFA Division-I, P.H.E. Dte. [Part-C] | Assistant Engineer 1 | Junior Engineer | ORD/000017/2021-2022 | 954/RCD-I | 07/06/2021 | 07/07/2021 | PINKI ENTERPRISE | 23.02 | 39.98 | 173.72 | 0
5 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Chotkara Kanskuli PWSS (Zone-I) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District | SM/07558 | Retrofitting | Supplying, aligning and laying of 90 mm dia HDPE pipe line (Parallel to main distribution) at village Kalya (part) and Siakulberia and Chotkara (Part) village for providing FHTC work under Chotkara Kanskuli Water Supply Scheme under RCFA Division-I PHE Dte. (Sl 12) | Assistant Engineer 1 | Junior Engineer | ORD/000573/2021-2022 | 255/RCD-I | 01/02/2022 | 21/02/2022 | JAYANTA DATTA | 4.99 | 4.64 | 93.07 | 0
6 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Chotkara Kanskuli PWSS (Zone-I) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District | SM/07558 | Retrofitting | Extension of HDPE pipe line (Parallel to main distribution) at village Kirtansala and Dharaspur village (Part) for providing FHTC work under Chotkara Kanskuli Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 18) | Assistant Engineer 1 | Junior Engineer | ORD/000578/2021-2022 | 260/RCD-I | 01/02/2022 | 21/02/2022 | DIP CONSTRUCTION | 4.98 | 4.64 | 93.27 | 0
7 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Chotkara Kanskuli PWSS (Zone-I) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District | SM/07558 | Retrofitting | Supplying, aligning & Laying of different dia HDPE pipe line for providing FHTC to Manahora, Kanskuli (Part) and Kalisanko villages under Chotkara Kanskuli W/S Scheme under RCFA Division-I PHE Dte. (Sl No. 02) | Assistant Engineer 1 | Junior Engineer | ORD/000139/2022-2023 | 1433/RCD I | 27/06/2022 | 11/08/2022 | GITASREE FABRICATION | 1.97 | 1.76 | 89.48 | 0
8 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Chotkara Kanskuli PWSS (Zone-I) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District | SM/07558 | Retrofitting | Extension of UPVC pipe line (Parallel to main distribution) at village Ghiadoba and Kusumdanali West side for providing FHTC under Chotkara Kanskuli Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 20) | Assistant Engineer 1 | Junior Engineer | ORD/000580/2021-2022 | 262/RCD-I | 01/02/2022 | 21/02/2022 | GITA CONSTRUCTION | 3.58 | 2.79 | 77.82 | 0
9 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Chotkara Kanskuli PWSS (Zone-I) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District | SM/07558 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000015/2025-2026 | 2537/RCD-I | 01/09/2025 | 01/09/2025 | Resource Division | 3.7 | 0 | 0 | 0
Total | [13 empty] | 111.24 | 148.53 | 133.52