## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Chotkara Kanskuli PWSS (Zone-II) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District | SM/07559 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Chotkara Kanskuli PWSS (Zone-II), Block- Salanpur & Barabani of Chotkara- Kanskuli Water supply scheme under RCFA Division-I, P.H.E. Dte. [Part-A] | Assistant Engineer 1 | Junior Engineer | ORD/000019/2021-2022 | 956/RCD-I | 07/06/2021 | 07/07/2021 | SUMIT BANERJEE | 23.02 | 24.28 | 105.47 | 0
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Chotkara Kanskuli PWSS (Zone-II) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District | SM/07559 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Chotkara Kanskuli PWSS (Zone-II), Block- Salanpur & Barabani of Chotkara- Kanskuli Water supply scheme under RCFA Division-I, P.H.E. Dte. [Part-B] | Assistant Engineer 1 | Junior Engineer | ORD/000020/2021-2022 | 957/RCD-I | 07/06/2021 | 07/07/2021 | BABA LOKNATH ENTERPRISE | 23.01 | 24.84 | 107.92 | 0
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Chotkara Kanskuli PWSS (Zone-II) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District | SM/07559 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Chotkara Kanskuli PWSS (Zone-II), Block- Salanpur & Barabani of Chotkara- Kanskuli Water supply scheme under RCFA Division-I, P.H.E. Dte. [Part-D] | Assistant Engineer 1 | Junior Engineer | ORD/000021/2021-2022 | 958/RCD-I | 07/06/2021 | 07/07/2021 | KHEPI MAA TRADERS | 22.98 | 5.31 | 23.11 | 0
4 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Chotkara Kanskuli PWSS (Zone-II) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District | SM/07559 | Retrofitting | Acceptance cum work order for Additional work of Morum cutting, concrete cutting, Hard rock cutting, Bituminus Road cutting different dia DI (K-7) & HDPE pipe line with other allied works from Dabor OHR Zone-II (Pahargara, Mohanpur, Partabpur, Bolkundi etc) distribution under Retrofitting Chotkara-Kanskuli W/S Scheme Zone II under RCFA Division-I PHE Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000161/2021-2022 | 1586/RCD-I | 07/09/2021 | 07/10/2021 | DAS & CHAKRABORTY | 11.29 | 10.88 | 96.4 | 0
5 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Chotkara Kanskuli PWSS (Zone-II) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District | SM/07559 | Retrofitting | Supplying, aligning and laying of 90 mm dia HDPE pipe line (Parallel to main distribution) at village Chotkara (Part) for providing FHTC under Chotkara Kanskuli Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 16) | Assistant Engineer 1 | Junior Engineer | ORD/000576/2021-2022 | 258/RCD-I | 01/02/2022 | 16/02/2022 | JAYANTA DATTA | 2.59 | 2.48 | 95.91 | 0
6 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Chotkara Kanskuli PWSS (Zone-II) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District | SM/07559 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Chotkara Kanskuli PWSS (Zone-II), Block- Salanpur & Barabani of Chotkara- Kanskuli Water supply scheme under RCFA Division-I, P.H.E. Dte. [Part-C] (3rd Call) | Assistant Engineer 2 | Junior Engineer | ORD/000061/2021-2022 | 1147/RCD-I | 22/07/2021 | 21/08/2021 | GITASHREE FABRICATION | 21.97 | 21.9 | 99.68 | 0
Total | [13 empty] | 104.86 | 89.68 | 85.53