## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Chotkara Kanskuli PWSS (Zone-III) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District | SM/07560 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Chotkara Kanskuli PWSS (Zone-III), Block- Salanpur & Barabani of Chotkara- Kanskuli Water supply scheme under RCFA Division-I, P.H.E. Dte. [Part-B] | Assistant Engineer 1 | Junior Engineer | ORD/000023/2021-2022 | 960/RCD-I | 07/06/2021 | 07/07/2021 | M/S MONDAL ENTERPRISE | 23 | 16.7 | 72.59 | 0
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Chotkara Kanskuli PWSS (Zone-III) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District | SM/07560 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Chotkara Kanskuli PWSS (Zone-III), Block- Salanpur & Barabani of Chotkara- Kanskuli Water supply scheme under RCFA Division-I, P.H.E. Dte. [Part-A] | Assistant Engineer 1 | Junior Engineer | ORD/000022/2021-2022 | 959/RCD-I | 07/06/2021 | 07/07/2021 | JAYANTA DATTA | 23.01 | 0 | 0 | 0
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Chotkara Kanskuli PWSS (Zone-III) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District | SM/07560 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Chotkara Kanskuli PWSS (Zone-III), Block- Salanpur & Barabani of Chotkara- Kanskuli Water supply scheme under RCFA Division-I, P.H.E. Dte. [Part-C] (3rd Call) | Assistant Engineer 1 | Junior Engineer | ORD/000062/2021-2022 | 1148/RCD-I | 22/07/2021 | 21/08/2021 | GITA CONSTRUCTION | 22.58 | 20.63 | 91.36 | 0
4 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Chotkara Kanskuli PWSS (Zone-III) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District | SM/07560 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Chotkara Kanskuli PWSS (Zone-III), Block- Salanpur & Barabani of Chotkara- Kanskuli Water supply scheme under RCFA Division-I, P.H.E. Dte. [Part-D] | Assistant Engineer 1 | Junior Engineer | ORD/000024/2021-2022 | 961/RCD-I | 07/06/2021 | 07/07/2021 | S. CHAKRABORTY & CO. | 22.97 | 21.46 | 93.42 | 0
5 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Chotkara Kanskuli PWSS (Zone-III) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District | SM/07560 | Retrofitting | Supplying, aligning and laying of 90 mm dia HDPE pipe line (Parallel to main distribution) at village Kirtansala (part) and Dharaspur village for providing FHTC work under Chotkara Kanskuli Water Supply Scheme under RCFA Division-I PHE Dte. (Sl 11) | Assistant Engineer 1 | Junior Engineer | ORD/000572/2021-2022 | 254/RCD-I | 01/02/2022 | 21/02/2022 | DIP CONSTRUCTION | 4.95 | 0 | 0 | 0
6 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Chotkara Kanskuli PWSS (Zone-III) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District | SM/07560 | Retrofitting | Emergency for providing balance FHTC through retrofitting at Shamdi G.P. area and Chayanpur and adjacent villages under Chotkara Kanskuli W/S Scheme under RCFA Division-I PHE Dte.(Sl no 03) | Assistant Engineer 2 | Junior Engineer | ORD/000211/2022-2023 | 1980/RCD I | 24/08/2022 | 08/09/2022 | KHEPI MAA TRADERS | 4.54 | 0 | 0 | 0
7 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Chotkara Kanskuli PWSS (Zone-III) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District | SM/07560 | Retrofitting | Formal Work Order for Pipe line crossing by adopting trench less technology (e.g. Jack Pushing Method etc) near Kanskuli DAM for dedicated pipe line towards Kanskuli village under Chotkara Kanskuli Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000078/2023-2024 | 1772/RCD-I | 18/05/2023 | 02/06/2023 | SRI KRISHNA ENTERPRISE | 4.37 | 0 | 0 | 0
Total | [13 empty] | 105.43 | 58.78 | 55.76