## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Chotkara Kanskuli PWSS (Zone-IV) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District | SM/07561 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Chotkara Kanskuli PWSS (Zone-IV), Block- Salanpur & Barabani of Chotkara- Kanskuli Water supply scheme under RCFA Division-I, P.H.E. Dte. [Part-B] | Assistant Engineer 1 | Junior Engineer | ORD/000026/2021-2022 | 963/RCD-I | 07/06/2021 | 07/07/2021 | DAS & CHAKRABORTY | 45.92 | 10.12 | 22.03 | 0
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Chotkara Kanskuli PWSS (Zone-IV) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District | SM/07561 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Chotkara Kanskuli PWSS (Zone-IV), Block- Salanpur & Barabani of Chotkara- Kanskuli Water supply scheme under RCFA Division-I, P.H.E. Dte. [Part-A] | Assistant Engineer 1 | Junior Engineer | ORD/000025/2021-2022 | 962/RCD-I | 07/06/2021 | 07/07/2021 | ASHA CONSTRUCTION | 45.95 | 83.29 | 181.27 | 0
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Chotkara Kanskuli PWSS (Zone-IV) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District | SM/07561 | Retrofitting | Supplying, aligning and laying of HDPE line (parallel to main distribution) at Ghidoba, Kushum Danali and extension of pipe line at Ghiadoba village for providing FHTC under Chotkara Kanskuli water supply scheme under RCFA Division-I PHE Dte.(Sl no 07) | Assistant Engineer 1 | Junior Engineer | ORD/000613/2021-2022 | 636/RCD 1 | 09/03/2022 | 24/03/2022 | DAS & CHAKRABORTY | 3.01 | 2.45 | 81.15 | 0
4 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Chotkara Kanskuli PWSS (Zone-IV) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District | SM/07561 | Retrofitting | Supplying, aligning and laying of UPVC line (parallel to main distribution) at Malladihi Hospital para towards Chayanpur for providing FHTC work under Chotkara Kanskuli water supply scheme under RCFA Division-I PHE Dte. (Sl no 09) | Assistant Engineer 1 | Junior Engineer | ORD/000615/2021-2022 | 638/RCD 1 | 09/03/2022 | 24/03/2022 | MD AAMIR KHAN | 2.82 | 0 | 0 | 0
5 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Chotkara Kanskuli PWSS (Zone-IV) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District | SM/07561 | Retrofitting | Additional work for laying of different dia DI (K7) & HDPE pipe line with other allied work from Dabor OHR Zone-II (Lohat, Phulberiya, Patal, Sadhana, Madhaichak, Shyamdihi etc.) distribution Chotkara Kanskuli Water Supply Scheme under RCFA Division-I PHE Dte. (Part-B) (Sl No. 08) | Assistant Engineer 1 | Junior Engineer | ORD/000552/2021-2022 | 251/RCD-I | 01/02/2022 | 16/02/2022 | ASHA CONSTRUCTION | 2.18 | 1.96 | 89.76 | 0
6 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Chotkara Kanskuli PWSS (Zone-IV) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District | SM/07561 | Retrofitting | Supplying, aligning and laying of HDPE line (Parallel to main distribution) for Ghidoba village & Kushum Danali West side for providing FHTC work under Chotkara Kanskuli Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 09) | Assistant Engineer 1 | Junior Engineer | ORD/000553/2021-2022 | 252/RCD-I | 01/02/2022 | 21/02/2022 | GITA CONSTRUCTION | 4.98 | 4.71 | 94.68 | 0
7 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Chotkara Kanskuli PWSS (Zone-IV) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District | SM/07561 | Retrofitting | Supplying, aligning and laying of 90 mm dia HDPE pipe line (Parallel to main distribution) at village Kushum Danali more towords Ghidoba West side for providing FHTC work under Chotkara Kanskuli Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 10) | Assistant Engineer 1 | Junior Engineer | ORD/000554/2021-2022 | 253/RCD-I | 01/02/2022 | 21/02/2022 | GITA CONSTRUCTION | 4.99 | 4.71 | 94.32 | 0
8 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Chotkara Kanskuli PWSS (Zone-IV) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District | SM/07561 | Retrofitting | Supplying, aligning and laying of 90 mm dia HDPE pipe line (Parallel to main distribution) at village Kushum Danali more towords Ghidoba East side under Chotkara Kanskuli Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 15) | Assistant Engineer 1 | Junior Engineer | ORD/000575/2021-2022 | 257/RCD-I | 01/02/2022 | 21/02/2022 | B.T.M CONCERN | 4.98 | 4.75 | 95.28 | 0
9 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Chotkara Kanskuli PWSS (Zone-IV) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District | SM/07561 | Retrofitting | Extension of UPVC Pipe line at Uttarrampur and Part of Kalisanko including connection to different ICDS & FP Schools for providing FHTC under Chotkara Kanskuli Water Supply Scheme under RCFA Division-I PHE Dte. (Sl no 01) | Assistant Engineer 1 | Junior Engineer | ORD/000607/2021-2022 | 630/ RCD I | 09/03/2022 | 24/03/2022 | KHEPI MAA TRADERS | 4.18 | 2.74 | 65.6 | 0
10 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Chotkara Kanskuli PWSS (Zone-IV) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District | SM/07561 | Retrofitting | Additional work of supplying, aligning and laying of 160 mm dia HDPE pipe line for distribution line at Bolkundi village under Chotkara Kanskuli Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 07) | Assistant Engineer 1 | Junior Engineer | ORD/000551/2021-2022 | 250/RCD-I | 01/02/2022 | 16/02/2022 | DAS & CHAKRABORTY | 2.05 | 2.05 | 99.56 | 0
11 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Chotkara Kanskuli PWSS (Zone-IV) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District | SM/07561 | Retrofitting | Sinking of 4 (Four) nos river bed tube wells including collecting main at Runakuraghat for Flood damaged at river Ajoy under Chotkara Kanskuli water supply scheme under RCFA Division-I PHE Dte. (Sl No. 14) | Assistant Engineer 2 | Junior Engineer | ORD/000034/2022-2023 | 1093/RCD I | 13/05/2022 | 12/06/2022 | RELIABLE ENGINEERS CO-OP CONSTRUCTION SOCIETY LTD. | 4.99 | 4.73 | 94.9 | 100
12 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Chotkara Kanskuli PWSS (Zone-IV) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District | SM/07561 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000018/2025-2026 | 2534/RCD-I | 01/09/2025 | 01/09/2025 | Resource Division | 5.45 | 0 | 0 | 0
Total | [13 empty] | 131.51 | 121.49 | 92.38