## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Improvement of Babani Zone PWSS for Providing FHTC Within Barabani Block of Paschim Bardhaman District | SM/07562 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Barabani Zone PWSS, Block- Barabani of Improvement of Barabani Water supply scheme under RCFA Division-I, P.H.E. Dte. [Part-B] | Assistant Engineer 1 | Junior Engineer | ORD/000014/2021-2022 | 951/RCD-I | 07/06/2021 | 07/07/2021 | TARAPRASAD SARKAR | 30.12 | 24.47 | 81.25 | 0
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Improvement of Babani Zone PWSS for Providing FHTC Within Barabani Block of Paschim Bardhaman District | SM/07562 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Barabani Zone PWSS, Block- Barabani of Improvement of Barabani Water supply scheme under RCFA Division-I, P.H.E. Dte. [Part-A] | Assistant Engineer 1 | Junior Engineer | ORD/000013/2021-2022 | 950/RCD-I | 07/06/2021 | 07/07/2021 | UMA ENTERPRISE | 30.02 | 30.7 | 102.26 | 0
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Improvement of Babani Zone PWSS for Providing FHTC Within Barabani Block of Paschim Bardhaman District | SM/07562 | Retrofitting | Block Level Orientation Programme involving PRI functionaries on Jal Jeevan Mission and its components at Barabani, Salanpur, Jamuria, Pandabeswar, Raniganj, Andal, Kansha & Durgapur Faridpur Block in the Districts of Paschim Bardhaman under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000718/2023-2024 | Camp_02_8_Nos_Block_AE_II | 26/09/2023 | 26/10/2023 | MUKHERJEE TRADERS | 3.79 | 3.79 | 100 | 100
Total | [13 empty] | 63.92 | 58.95 | 92.23