## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | Resource | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Paschim Barddhaman District. | SM/08984 | Support-M&E | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Paschim Bardhaman |  |  | ORD/000719/2022-2023 | 5774/RS | 09/11/2022 | 09/11/2023 | UTTAR DINAJPUR ANKUR GRAM UNNAYAN SOCIETY | 172.07 | 0 | 0 | 74
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Paschim Barddhaman District. | SM/08984 | Support-M&E | Margdarshika colour print with spiral binding (62 nos) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000253/2023-2024 | 2291/RCD-I | 20/07/2023 | 22/07/2023 | MUKHERJEE TRADERS | 0.68 | 0 | 0 | 100
Total | [13 empty] | 172.76 | 0 | 0