## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) | SM/09059 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Suri Para, Bisakhalakhi Tala (Sansad-VI) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000261/2021-2022 | 1870/RCD-I | 28/10/2021 | 27/11/2021 | JAYANTA DATTA | 18.06 | 18.06 | 100 | 0
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) | SM/09059 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Subhas Para & Chunari Para (Sansad-III) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000258/2021-2022 | 1867/RCD-I | 28/10/2021 | 27/11/2021 | DAS & CHAKRABORTY | 18.1 | 18.09 | 99.98 | 0
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) | SM/09059 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Puratan Mushlim Para & Dhibarpara (Sansad-VII) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000262/2021-2022 | 1871/RCD-I | 28/10/2021 | 27/11/2021 | RUBY CONSTRUCTION | 15.67 | 15.67 | 100 | 0
4 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) | SM/09059 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Kankardanga (Sansad-VIII) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000263/2021-2022 | 1872/RCD-I | 28/10/2021 | 27/11/2021 | MS KALYAN ENTERPRISE | 10.6 | 10.6 | 99.97 | 0
5 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) | SM/09059 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Dangal Para (Sansad-XI) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000264/2021-2022 | 1873/RCD-I | 28/10/2021 | 27/11/2021 | SNEHA ELECTRIC | 13.31 | 13.3 | 99.98 | 0
6 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) | SM/09059 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Sukho Para (Sansad-XX) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000270/2021-2022 | 1879/RCD-I | 28/10/2021 | 27/11/2021 | SOMNATH SAMANTA | 15.63 | 15.63 | 99.98 | 0
7 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) | SM/09059 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Asthalpara (Sansad-XIV) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000266/2021-2022 | 1875/RCD-I | 28/10/2021 | 27/11/2021 | UNITED CONSTRUCTION | 13.32 | 13.32 | 100 | 0
8 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) | SM/09059 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Mulimpara & Ruidaspara (Sansad-XIII) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000265/2021-2022 | 1874/RCD-I | 28/10/2021 | 27/11/2021 | MD. JAWED KHAN | 18.16 | 18.15 | 99.96 | 0
9 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) | SM/09059 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Mukherjeepara & Khad Para (Sansad-XVII) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000268/2021-2022 | 1877/RCD-I | 28/10/2021 | 27/11/2021 | SIMA ENTERPRISE | 15.72 | 15.71 | 99.94 | 0
10 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) | SM/09059 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Pathakpara (Sansad-XV) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000267/2021-2022 | 1876/RCD-I | 28/10/2021 | 27/11/2021 | B.T.M CONCERN | 15.25 | 15.25 | 99.99 | 0
11 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) | SM/09059 | Retrofitting | Acceptance cum work order Laying of different dia distribution pipe line at Sukopara (Part), Bauripara (Part) etc adjacent area at Ukhra Gram Panchayet (Sansad-XX) Augmentation of RCFA Part-II (Zone-2A) W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000939/2022-2023 | 1275/RCD-I | 27/03/2023 | 11/04/2023 | SOMNATH SAMANTA | 3.25 | 2.95 | 90.55 | 0
12 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) | SM/09059 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Ukhra Bazar Area (Sansad-V) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000260/2021-2022 | 1869/RCD-I | 28/10/2021 | 27/11/2021 | UMA ENTERPRISE | 21.3 | 6.08 | 28.53 | 0
13 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) | SM/09059 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Teli Para (Sansad-XVIII) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000269/2021-2022 | 1878/RCD-I | 28/10/2021 | 27/11/2021 | M/S K & KONAR CONSTRUCTION | 17.13 | 11.64 | 67.99 | 0
14 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) | SM/09059 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Hanuman Danga & Saradapally (Sansad-IV) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000259/2021-2022 | 1868/RCD-I | 28/10/2021 | 27/11/2021 | DAWN CONSTRUCTION | 26.54 | 20.57 | 77.5 | 0
15 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) | SM/09059 | Retrofitting | hire charges & fuel bill of Ranajit Auto |  |  | BILL/00612/2023-2024 | 220/23-24 | 22/08/2023 | 22/08/2023 | SHYAMAL MAJI | 0.15 | 0 | 0 | 0
16 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) | SM/09059 | Retrofitting | Spiral Binding |  |  | BILL/00610/2023-2024 | 185/23-24 | 10/08/2023 | 10/08/2023 | MUKHERJEE TRADERS | 0.68 | 0 | 0 | 0
17 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) | SM/09059 | Retrofitting | Hire charge and fuel bill for the month o June 2023 to August 2023 |  |  | BILL/00759/2023-2024 | 323/23-24 | 17/10/2023 | 17/10/2023 | KHEPI MAA TRADERS | 1.19 | 0 | 0 | 0
18 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) | SM/09059 | Retrofitting | Submissin of quarterly revised return for non salary return Bill no 7236 to 7339 |  |  | BILL/00774/2023-2024 | 367/23-24 | 10/11/2023 | 10/11/2023 | SHRESTHA & ASSOCIATES | 0.36 | 0 | 0 | 0
19 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) | SM/09059 | Retrofitting | Transporting loading and unloading of jackets Banners etc for pump operator and valve operation at sites under JJM |  |  | BILL/00611/2023-2024 | 179/23-24 | 08/08/2023 | 08/08/2023 | SHARMA ENGINEERING WORKS | 0.18 | 0 | 0 | 0
20 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) | SM/09059 | Retrofitting | fuel bill shyamal maji jyly 2023 |  |  | BILL/00613/2023-2024 | 220/23-24 | 24/08/2023 | 24/08/2023 | RANAJIT AUTO | 0.16 | 0 | 0 | 0
21 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) | SM/09059 | Retrofitting | Fuel bill for WB 37 D 0482 for Oct 23 and Nov 23 |  |  | BILL/01145/2023-2024 | 430/23-24 | 20/12/2023 | 20/12/2023 | RANAJIT AUTO | 0.29 | 0 | 0 | 0
22 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) | SM/09059 | Retrofitting | Fuel and vehicle bill for Feb 2023 to June 23 |  |  | BILL/00511/2023-2024 | 234/23-24 | 04/09/2023 | 04/09/2023 | NIRMALA TRADERS | 1.19 | 0 | 0 | 0
23 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) | SM/09059 | Retrofitting | Khepi Maa Traders |  |  | BILL/00614/2023-2024 | 215/23-24 | 22/08/2023 | 22/08/2023 | KHEPI MAA TRADERS | 1.16 | 0 | 0 | 0
24 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) | SM/09059 | Retrofitting | Vehicle bill for 37 D 0482 Oct 2023 and nov 2023 |  |  | BILL/01144/2023-2024 | 429/23-24 | 20/12/2023 | 20/12/2023 | SHYAMAL MAJI | 0.3 | 0 | 0 | 0
25 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) | SM/09059 | Retrofitting | Supply of it periphersls under sub district laboratory |  |  | BILL/00211/2024-2025 | 92/24-25 | 13/06/2024 | 13/06/2024 | SHARMA ENGINEERING WORKS | 0.02 | 0 | 0 | 0
26 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) | SM/09059 | Retrofitting | Acceptance cum work order Laying of different dia HDPE pipe line and allied works at Kankardanga Part (Sansad-VIII) at Ukhra area under Augmentation of RCFA Part-II (Zone-2A) PWSS under RCFA Division-I PHE Dte. (Sl No. 18) | Assistant Engineer 2 | Junior Engineer | ORD/000906/2022-2023 | 1162/RCD-I | 24/03/2023 | 08/04/2023 | SHILPA UDDOYG ENGINEERING CO-OP SOCIETY LTD. | 1.42 | 1.29 | 90.79 | 100
27 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) | SM/09059 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Ukhra Area (Phase-II) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. (Part-E) | Assistant Engineer 2 | Junior Engineer | ORD/000373/2021-2022 | 2333/RCD-I | 17/12/2021 | 16/01/2022 | TARAPRASAD SARKAR | 14.37 | 2.26 | 15.75 | 100
Total | [13 empty] | 243.5 | 198.56 | 81.54