## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) | SM/09059 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Suri Para, Bisakhalakhi Tala (Sansad-VI) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000261/2021-2022 | 1870/RCD-I | 28/10/2021 | 27/11/2021 | JAYANTA DATTA | 18.06 | 0 | 0 | 0
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) | SM/09059 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Subhas Para & Chunari Para (Sansad-III) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000258/2021-2022 | 1867/RCD-I | 28/10/2021 | 27/11/2021 | DAS & CHAKRABORTY | 18.1 | 0 | 0 | 0
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) | SM/09059 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Puratan Mushlim Para & Dhibarpara (Sansad-VII) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000262/2021-2022 | 1871/RCD-I | 28/10/2021 | 27/11/2021 | RUBY CONSTRUCTION | 15.67 | 0 | 0 | 0
4 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) | SM/09059 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Kankardanga (Sansad-VIII) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000263/2021-2022 | 1872/RCD-I | 28/10/2021 | 27/11/2021 | MS KALYAN ENTERPRISE | 10.6 | 0 | 0 | 0
5 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) | SM/09059 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Dangal Para (Sansad-XI) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000264/2021-2022 | 1873/RCD-I | 28/10/2021 | 27/11/2021 | SNEHA ELECTRIC | 13.31 | 0 | 0 | 0
6 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) | SM/09059 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Sukho Para (Sansad-XX) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000270/2021-2022 | 1879/RCD-I | 28/10/2021 | 27/11/2021 | SOMNATH SAMANTA | 15.63 | 0 | 0 | 0
7 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) | SM/09059 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Asthalpara (Sansad-XIV) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000266/2021-2022 | 1875/RCD-I | 28/10/2021 | 27/11/2021 | UNITED CONSTRUCTION | 13.32 | 0 | 0 | 0
8 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) | SM/09059 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Mulimpara & Ruidaspara (Sansad-XIII) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000265/2021-2022 | 1874/RCD-I | 28/10/2021 | 27/11/2021 | MD. JAWED KHAN | 18.16 | 0 | 0 | 0
9 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) | SM/09059 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Mukherjeepara & Khad Para (Sansad-XVII) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000268/2021-2022 | 1877/RCD-I | 28/10/2021 | 27/11/2021 | SIMA ENTERPRISE | 15.72 | 0 | 0 | 0
10 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) | SM/09059 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Pathakpara (Sansad-XV) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000267/2021-2022 | 1876/RCD-I | 28/10/2021 | 27/11/2021 | B.T.M CONCERN | 15.25 | 0 | 0 | 0
11 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) | SM/09059 | Retrofitting | Acceptance cum work order Laying of different dia distribution pipe line at Sukopara (Part), Bauripara (Part) etc adjacent area at Ukhra Gram Panchayet (Sansad-XX) Augmentation of RCFA Part-II (Zone-2A) W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000939/2022-2023 | 1275/RCD-I | 27/03/2023 | 11/04/2023 | SOMNATH SAMANTA | 3.25 | 0 | 0 | 0
12 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) | SM/09059 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Ukhra Bazar Area (Sansad-V) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000260/2021-2022 | 1869/RCD-I | 28/10/2021 | 27/11/2021 | UMA ENTERPRISE | 21.3 | 0 | 0 | 0
13 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) | SM/09059 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Teli Para (Sansad-XVIII) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000269/2021-2022 | 1878/RCD-I | 28/10/2021 | 27/11/2021 | M/S K & KONAR CONSTRUCTION | 17.13 | 0 | 0 | 0
14 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) | SM/09059 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Hanuman Danga & Saradapally (Sansad-IV) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000259/2021-2022 | 1868/RCD-I | 28/10/2021 | 27/11/2021 | DAWN CONSTRUCTION | 26.54 | 0 | 0 | 0
15 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) | SM/09059 | Retrofitting | hire charges & fuel bill of Ranajit Auto |  |  | BILL/00612/2023-2024 | 220/23-24 | 22/08/2023 | 22/08/2023 | SHYAMAL MAJI | 0.15 | 0 | 0 | 0
16 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) | SM/09059 | Retrofitting | Spiral Binding |  |  | BILL/00610/2023-2024 | 185/23-24 | 10/08/2023 | 10/08/2023 | MUKHERJEE TRADERS | 0.68 | 0 | 0 | 0
17 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) | SM/09059 | Retrofitting | Hire charge and fuel bill for the month o June 2023 to August 2023 |  |  | BILL/00759/2023-2024 | 323/23-24 | 17/10/2023 | 17/10/2023 | KHEPI MAA TRADERS | 1.19 | 0 | 0 | 0
18 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) | SM/09059 | Retrofitting | Submissin of quarterly revised return for non salary return Bill no 7236 to 7339 |  |  | BILL/00774/2023-2024 | 367/23-24 | 10/11/2023 | 10/11/2023 | SHRESTHA & ASSOCIATES | 0.36 | 0 | 0 | 0
19 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) | SM/09059 | Retrofitting | Transporting loading and unloading of jackets Banners etc for pump operator and valve operation at sites under JJM |  |  | BILL/00611/2023-2024 | 179/23-24 | 08/08/2023 | 08/08/2023 | SHARMA ENGINEERING WORKS | 0.18 | 0 | 0 | 0
20 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) | SM/09059 | Retrofitting | fuel bill shyamal maji jyly 2023 |  |  | BILL/00613/2023-2024 | 220/23-24 | 24/08/2023 | 24/08/2023 | RANAJIT AUTO | 0.16 | 0 | 0 | 0
21 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) | SM/09059 | Retrofitting | Fuel bill for WB 37 D 0482 for Oct 23 and Nov 23 |  |  | BILL/01145/2023-2024 | 430/23-24 | 20/12/2023 | 20/12/2023 | RANAJIT AUTO | 0.29 | 0 | 0 | 0
22 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) | SM/09059 | Retrofitting | Fuel and vehicle bill for Feb 2023 to June 23 |  |  | BILL/00511/2023-2024 | 234/23-24 | 04/09/2023 | 04/09/2023 | NIRMALA TRADERS | 1.19 | 0 | 0 | 0
23 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) | SM/09059 | Retrofitting | Khepi Maa Traders |  |  | BILL/00614/2023-2024 | 215/23-24 | 22/08/2023 | 22/08/2023 | KHEPI MAA TRADERS | 1.16 | 0 | 0 | 0
24 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) | SM/09059 | Retrofitting | Vehicle bill for 37 D 0482 Oct 2023 and nov 2023 |  |  | BILL/01144/2023-2024 | 429/23-24 | 20/12/2023 | 20/12/2023 | SHYAMAL MAJI | 0.3 | 0 | 0 | 0
25 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) | SM/09059 | Retrofitting | Supply of it periphersls under sub district laboratory |  |  | BILL/00211/2024-2025 | 92/24-25 | 13/06/2024 | 13/06/2024 | SHARMA ENGINEERING WORKS | 0.02 | 0 | 0 | 0
26 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) | SM/09059 | Retrofitting | Acceptance cum work order Laying of different dia HDPE pipe line and allied works at Kankardanga Part (Sansad-VIII) at Ukhra area under Augmentation of RCFA Part-II (Zone-2A) PWSS under RCFA Division-I PHE Dte. (Sl No. 18) | Assistant Engineer 2 | Junior Engineer | ORD/000906/2022-2023 | 1162/RCD-I | 24/03/2023 | 08/04/2023 | SHILPA UDDOYG ENGINEERING CO-OP SOCIETY LTD. | 1.42 | 0 | 0 | 100
27 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) | SM/09059 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Ukhra Area (Phase-II) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. (Part-E) | Assistant Engineer 2 | Junior Engineer | ORD/000373/2021-2022 | 2333/RCD-I | 17/12/2021 | 16/01/2022 | TARAPRASAD SARKAR | 14.37 | 0 | 0 | 100
28 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) | SM/09059 | Retrofitting | Acceptance cum work order for Construction of 150 cum capacity 20 mtr staging height RCC Over Head Reservoir (pipe connection and cost of pipes, specials at Augmentation of Jamuria Rural (Zone-II) Piped Water Supply Scheme under RCFA Division-I PHE Dte. (2nd Call) | Assistant Engineer 2 | Junior Engineer | ORD/000033/2023-2024 | 1631/RCD-I | 26/04/2023 | 26/04/2024 | UNITED CONSTRUCTION | 69.15 | 0 | 0 | 100
29 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) | SM/09059 | Retrofitting | Acceptance cum work order for Sinking of 02 (Two) nos. river bed tube wells including collecting main and other allied works at Narayankuri H/W site at Damodar river under Narayankuri Water Supply Scheme under RCFA Division-I PHE Dte. (Part-A) | Assistant Engineer 2 | Junior Engineer | ORD/000211/2023-2024 | 2242/RCD-I | 17/07/2023 | 16/08/2023 | MS KALYAN ENTERPRISE | 12.81 | 0 | 0 | 100
Total | [13 empty] | 325.47 | 0 | 0