## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-B) | SM/09060 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Safique Nagar (Sansad-XXII) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000272/2021-2022 | 1881/RCD-I | 28/10/2021 | 27/11/2021 | A. CONSTRUCTION CO. | 18.11 | 18.11 | 99.99 | 0
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-B) | SM/09060 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Huchukpara (Sansad-II) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000366/2021-2022 | 2324/RCD-I | 16/12/2021 | 15/01/2022 | A. CONSTRUCTION CO. | 15.53 | 15.53 | 99.99 | 0
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-B) | SM/09060 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Asthana (Sansad-IX) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. 2nd Call | Assistant Engineer 2 | Junior Engineer | ORD/000498/2021-2022 | 198/RCD-I | 28/01/2022 | 27/02/2022 | B M SARKAR | 13.04 | 10.18 | 78.07 | 0
4 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-B) | SM/09060 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Sanyasi Kalitala (Sansad-XVI) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000496/2021-2022 | 2491/RCD-I | 31/12/2021 | 30/01/2022 | TARA CONSTRUCTION | 11.24 | 10.92 | 97.15 | 0
5 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-B) | SM/09060 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Guzarbagh (Sansad-XXI) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000271/2021-2022 | 1880/RCD-I | 28/10/2021 | 27/11/2021 | R B ENTERPRISE | 13.3 | 13.3 | 99.97 | 0
6 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-B) | SM/09060 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Bibirbandh Para and Santipara (Sansad-I) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000365/2021-2022 | 2323/RCD-I | 16/12/2021 | 15/01/2022 | GITASHREE FABRICATION | 18.16 | 18.16 | 100 | 0
7 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-B) | SM/09060 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Das Para (Sansad-XIX) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000367/2021-2022 | 2325/RCD-I | 16/12/2021 | 15/01/2022 | JYOGOMAYA ENTERPRISE | 12.46 | 10.43 | 83.75 | 0
8 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-B) | SM/09060 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Chanchani (Sansad-X) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000369/2021-2022 | 2327/RCD-I | 16/12/2021 | 15/01/2022 | ASHA CONSTRUCTION | 27.72 | 18.23 | 65.78 | 0
9 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-B) | SM/09060 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Ukhra Bazar Area (Sansad-V) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000260/2021-2022 | 1869/RCD-I | 28/10/2021 | 27/11/2021 | UMA ENTERPRISE | 21.3 | 15.22 | 71.46 | 0
10 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-B) | SM/09060 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Teli Para (Sansad-XVIII) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000269/2021-2022 | 1878/RCD-I | 28/10/2021 | 27/11/2021 | M/S K & KONAR CONSTRUCTION | 17.13 | 5.48 | 32.01 | 0
11 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-B) | SM/09060 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Ukhra Area (Phase-II) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. (Part-C) 2nd Call | Assistant Engineer 2 | Junior Engineer | ORD/000491/2021-2022 | 120/RCD-I | 20/01/2022 | 19/02/2022 | GLOBAL CONSTRUCTION | 14.23 | 13.36 | 93.89 | 0
12 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-B) | SM/09060 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Ukhra Area (Phase-II) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. (Part-A) | Assistant Engineer 2 | Junior Engineer | ORD/000370/2021-2022 | 2328/RCD-I | 16/12/2021 | 15/01/2022 | MD AAMIR KHAN | 14.42 | 14.42 | 99.99 | 0
13 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-B) | SM/09060 | Retrofitting | Supply of 10 mm into female 15 mm outer male reducer Brass Bush at Searsole Store to provide interconnection work in between maniflod and ferrule under Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 02) | Assistant Engineer 2 | Junior Engineer | ORD/000208/2022-2023 | 1909/RCD-I | 12/08/2022 | 19/08/2022 | SNEHA ELECTRIC | 4.69 | 4.69 | 100 | 0
14 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-B) | SM/09060 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Ukhra Area (Phase-II) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. (Part-D) | Assistant Engineer 2 | Junior Engineer | ORD/000851/2021-2022 | 2332/RCD-1 | 17/12/2021 | 16/01/2022 | RELIABLE ENGINEERS CO-OP CONSTRUCTION SOCIETY LTD. | 14.44 | 4.03 | 27.91 | 0
15 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-B) | SM/09060 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Hanuman Danga & Saradapally (Sansad-IV) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000259/2021-2022 | 1868/RCD-I | 28/10/2021 | 27/11/2021 | DAWN CONSTRUCTION | 26.54 | 5.97 | 22.5 | 0
16 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-B) | SM/09060 | Retrofitting | hirting of maxi cab for date 27.7.2023 to 28.07.2023 us of AE RCFA Div WB37D 9526 |  |  | BILL/00532/2023-2024 | 256/23-24 | 11/09/2023 | 11/09/2023 | NIRMALA TRADERS | 0.06 | 0 | 0 | 0
17 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-B) | SM/09060 | Retrofitting | Acceptance cum work order for Laying of 110 mm dia HDPE Pipe line including concrete cutting mending etc allied works towards Pathakpara (Sansad-XV) Block Andal & Pandabeswar of Improvement of Ukhra Piped Water Supply Scheme under RCFA Division-I PHE Dte. |  |  | BILL/01008/2023-2024 | 372/23-24 | 21/11/2023 | 21/11/2023 | B.T.M. CONCERN | 2.14 | 0 | 0 | 0
18 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-B) | SM/09060 | Retrofitting | Supply of chair for SE/RCFA Circle |  |  | BILL/00330/2023-2024 | 151/23-24 | 25/07/2023 | 25/07/2023 | GLOBAL LOGISTIC CO | 0.23 | 0 | 0 | 0
19 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-B) | SM/09060 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Ukhra Area (Phase-II) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. (Part-B) | Assistant Engineer 2 | Junior Engineer | ORD/000371/2021-2022 | 2329/RCD-I | 16/12/2021 | 15/01/2022 | SHILPA UDDOYG ENGINEERING CO-OP SOCIETY LTD. | 14.4 | 10.71 | 74.37 | 0
20 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-B) | SM/09060 | Retrofitting | Suuply of UPS laboratory antivirus toner 12 for Asansol Laboratory |  |  | BILL/00210/2024-2025 | 91/24-25 | 13/06/2024 | 13/06/2024 | SHARMA ENGINEERING WORKS | 0.08 | 0 | 0 | 0
21 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-B) | SM/09060 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Ukhra Area (Phase-II) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. (Part-E) | Assistant Engineer 2 | Junior Engineer | ORD/000373/2021-2022 | 2333/RCD-I | 17/12/2021 | 16/01/2022 | TARAPRASAD SARKAR | 14.37 | 10.48 | 72.96 | 100
22 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-B) | SM/09060 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Ukhra Area (Phase-II) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. (Part-D) | Assistant Engineer 2 | Junior Engineer | ORD/000372/2021-2022 | 2332/RCD-I | 17/12/2021 | 16/01/2022 | RELIABLE ENGINEERS CO-OP CONSTRUCTION SOCIETY LTD. | 14.44 | 7.14 | 49.48 | 0
23 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-B) | SM/09060 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Chanchani (Sansad-XII) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000368/2021-2022 | 2326/RCD-I | 16/12/2021 | 15/01/2022 | M/S B.K. CONSTRUCTION | 25.7 | 17.19 | 66.91 | 100
24 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-B) | SM/09060 | Retrofitting | Acceptance cum work order for Sinking of 02 (Two) nos. river bed tube wells including collecting main and other allied works at Narayankuri H/W site at Damodar river under Narayankuri Water Supply Scheme under RCFA Division-I PHE Dte. (Part-B) | Assistant Engineer 2 | Junior Engineer | ORD/000215/2023-2024 | 2243/RCD-1 | 17/07/2023 | 16/08/2023 | MS KALYAN ENTERPRISE | 13.23 | 11.39 | 86.09 | 100
Total | [13 empty] | 326.94 | 234.95 | 71.87