## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Madantore PWSS for providing FHTC within Jamuria Block of Paschim Bardhaman District under RCFA Division-I. | SM/09061 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000006/2023-2024 | 1857/RCD-I | 31/05/2023 | 31/05/2023 | Resource Division | 1.76 | 0 | 0 | 0
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Madantore PWSS for providing FHTC within Jamuria Block of Paschim Bardhaman District under RCFA Division-I. | SM/09061 | Retrofitting | Acceptance cum work order for Additional Providing FHTC of retrofitting at Kumardiha village (left out portion) of Kumardiha Mouza, Retrofitting of Madantore PWSS for providing FHTC under RCFA Division-I PHE Dte. |  |  | ORD/000281/2024-2025 | 2619/RCD-I | 14/11/2024 | 04/12/2024 | D.S.C. CONCERN | 6.57 | 0 | 0 | 0
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Madantore PWSS for providing FHTC within Jamuria Block of Paschim Bardhaman District under RCFA Division-I. | SM/09061 | Retrofitting | Acceptance cum work order for supplying, aligning, laying of PVC & HDPE Pipeline, Construction of Sluice valve chamber and supplying, aligning, laying of G.I Pipe under Retrofitting of Madantore PWSS scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000784/2022-2023 | 405/RCD-I | 30/01/2023 | 14/02/2023 | M/S S.K. ENTERPRISE | 5.17 | 5.17 | 100 | 0
4 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Madantore PWSS for providing FHTC within Jamuria Block of Paschim Bardhaman District under RCFA Division-I. | SM/09061 | Retrofitting | Acceptance cum work order Sinking of 5 (Five nos. 200mm dia river bed tube wells including collecting main instead of defunct tube well at river Damodar (intake well Site ) Kalajharia Under Omprovement of RCFS part-II W/S Scheme under RCFA Division-I PHE Dte. (Part-G). | Assistant Engineer 2 | Junior Engineer | ORD/000789/2022-2023 | 402/RCDI | 30/01/2023 | 14/02/2023 | DURGADAS MONDAL | 8.43 | 7.68 | 91.05 | 0
5 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Madantore PWSS for providing FHTC within Jamuria Block of Paschim Bardhaman District under RCFA Division-I. | SM/09061 | Retrofitting | Acceptance cum work order Repairing & shifting work of DI pipes, repairing of 350 mm dia MS pipe and allied repairing at Madanpur W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000940/2022-2023 | 1278/ RCD I | 27/03/2023 | 11/04/2023 | MD. JAWED KHAN | 4.78 | 4.69 | 98.2 | 100
6 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Madantore PWSS for providing FHTC within Jamuria Block of Paschim Bardhaman District under RCFA Division-I. | SM/09061 | Retrofitting | Acceptance cum work order for Repairing and restoration of pipe line including supply of valve, construction of valve chamber, restoration of FHTC etc. at Bathan Bari, Sidhabari, Kalyaneswari and adjoining area Retrofitting of Madantore PWSS for providing FHTC within Jamuria Block under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000516/2024-2025 | 116/RCD-I | 08/01/2025 | 22/02/2025 | DIP CONSTRUCTION | 13.76 | 0 | 0 | 100
Total | [13 empty] | 40.47 | 17.54 | 43.33