## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Madantore PWSS for providing FHTC within Jamuria Block of Paschim Bardhaman District under RCFA Division-I. | SM/09061 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000006/2023-2024 | 1857/RCD-I | 31/05/2023 | 31/05/2023 | Resource Division | 1.76 | 0 | 0 | 0
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Madantore PWSS for providing FHTC within Jamuria Block of Paschim Bardhaman District under RCFA Division-I. | SM/09061 | Retrofitting | Acceptance cum work order for Additional Providing FHTC of retrofitting at Kumardiha village (left out portion) of Kumardiha Mouza, Retrofitting of Madantore PWSS for providing FHTC under RCFA Division-I PHE Dte. |  |  | ORD/000281/2024-2025 | 2619/RCD-I | 14/11/2024 | 04/12/2024 | D.S.C. CONCERN | 6.57 | 0 | 0 | 0
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Madantore PWSS for providing FHTC within Jamuria Block of Paschim Bardhaman District under RCFA Division-I. | SM/09061 | Retrofitting | Acceptance cum work order for supplying, aligning, laying of PVC & HDPE Pipeline, Construction of Sluice valve chamber and supplying, aligning, laying of G.I Pipe under Retrofitting of Madantore PWSS scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000784/2022-2023 | 405/RCD-I | 30/01/2023 | 14/02/2023 | M/S S.K. ENTERPRISE | 5.17 | 5.17 | 100 | 0
4 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Madantore PWSS for providing FHTC within Jamuria Block of Paschim Bardhaman District under RCFA Division-I. | SM/09061 | Retrofitting | Acceptance cum work order Sinking of 5 (Five nos. 200mm dia river bed tube wells including collecting main instead of defunct tube well at river Damodar (intake well Site ) Kalajharia Under Omprovement of RCFS part-II W/S Scheme under RCFA Division-I PHE Dte. (Part-G). | Assistant Engineer 2 | Junior Engineer | ORD/000789/2022-2023 | 402/RCDI | 30/01/2023 | 14/02/2023 | DURGADAS MONDAL | 8.43 | 7.68 | 91.05 | 0
5 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Madantore PWSS for providing FHTC within Jamuria Block of Paschim Bardhaman District under RCFA Division-I. | SM/09061 | Retrofitting | Acceptance cum work order Repairing & shifting work of DI pipes, repairing of 350 mm dia MS pipe and allied repairing at Madanpur W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000940/2022-2023 | 1278/ RCD I | 27/03/2023 | 11/04/2023 | MD. JAWED KHAN | 4.78 | 4.69 | 98.2 | 100
Total | [13 empty] | 26.7 | 17.54 | 65.67