## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Roshna PWSS for providing FHTC within Barabani Block of Paschim Bardhaman District under RCFA Division-I. | SM/09062 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Roshna (Part) Block-Barabani under Roshna Water supply scheme under RCFA Division-I, P.H.E. Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000189/2021-2022 | 1863/RCD-I | 28/10/2021 | 27/11/2021 | SRI KRISHNA ENTERPRISE | 12.81 | 0 | 0 | 0
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Roshna PWSS for providing FHTC within Barabani Block of Paschim Bardhaman District under RCFA Division-I. | SM/09062 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Parulberia Mouza Block-Barabani under Roshna Water supply scheme under RCFA Division-I, P.H.E. Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000190/2021-2022 | 1864/RCD-I | 28/10/2021 | 27/11/2021 | MAK CONSTRUCTION CO. | 20.28 | 0 | 0 | 0
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Roshna PWSS for providing FHTC within Barabani Block of Paschim Bardhaman District under RCFA Division-I. | SM/09062 | Retrofitting | Extension of different dia HDPE pipe line for providing FHTC at Parulberia and allied villages (Part-B) under Roshna W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000138/2022-2023 | 1432/RCD I | 27/06/2022 | 11/08/2022 | MD SARFARAZ ALAM | 4.98 | 0 | 0 | 0
4 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Roshna PWSS for providing FHTC within Barabani Block of Paschim Bardhaman District under RCFA Division-I. | SM/09062 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Daskeary Village Block-Barabani under Roshna Water supply scheme under RCFA Division-I, P.H.E. Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000188/2021-2022 | 1862/RCD-I | 28/10/2021 | 27/11/2021 | M/S MONI TRADERS | 39.47 | 0 | 0 | 0
5 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Roshna PWSS for providing FHTC within Barabani Block of Paschim Bardhaman District under RCFA Division-I. | SM/09062 | Retrofitting | Supplying, aligning & Laying of different dia HDPE pipe line for providing FHTC at Parulberia and allied villages (Part-A) under Roshna W/S Scheme under RCFA Division-I PHE Dte. (Sl No. 03) | Assistant Engineer 1 | Junior Engineer | ORD/000140/2022-2023 | 1434/RCD I | 27/06/2022 | 11/08/2022 | MD AAMIR KHAN | 5 | 0 | 0 | 0
6 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Roshna PWSS for providing FHTC within Barabani Block of Paschim Bardhaman District under RCFA Division-I. | SM/09062 | Retrofitting | Extension of different dia HDPE pipe line for providing FHTC at Roshna & Baspahari villages under Roshna W/S Scheme under RCFA Division-I PHE Dte. (Sl No. 07) | Assistant Engineer 1 | Junior Engineer | ORD/000144/2022-2023 | 1438/RCD I | 27/06/2022 | 11/08/2022 | SHREE DURGA ENTERPRISE | 3.22 | 0 | 0 | 0
7 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Roshna PWSS for providing FHTC within Barabani Block of Paschim Bardhaman District under RCFA Division-I. | SM/09062 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000007/2021-2022 | 438/RCD-I | 21/02/2022 | 21/02/2022 | Resource Division | 8.25 | 0 | 0 | 0
8 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Roshna PWSS for providing FHTC within Barabani Block of Paschim Bardhaman District under RCFA Division-I. | SM/09062 | Retrofitting | Car bill may 23 and june 23 |  |  | BILL/00518/2023-2024 | 234/2/23-24 | 05/09/2023 | 05/09/2023 | NIRMALA TRADERS | 0.78 | 0 | 0 | 0
9 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Roshna PWSS for providing FHTC within Barabani Block of Paschim Bardhaman District under RCFA Division-I. | SM/09062 | Retrofitting | Acceptance cum work order for Additional work for Distribution Network including supply of Hume pipe, G.I. pipe Sluice Valve and allied works for Augmentation of Roshna PWS (Part-D) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000237/2023-2024 | 2251/RCD-1 | 17/07/2023 | 16/08/2023 | JYOGOMAYA ENTERPRISE | 10.86 | 0 | 0 | 100
Total | [13 empty] | 105.65 | 0 | 0