## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Gourbazar PWSS for providing FHTC within Barabani Block of Paschim Bardhaman District under RCFA Division-I. | SM/09063 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Gourbazar Village, Block-Barabani under Gourbazar Water supply scheme under RCFA Division-I, P.H.E. Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000191/2021-2022 | 1865/RCD-I | 28/10/2021 | 27/11/2021 | M/S S.K. ENTERPRISE | 13.17 | 12.21 | 92.7 | 0
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Gourbazar PWSS for providing FHTC within Barabani Block of Paschim Bardhaman District under RCFA Division-I. | SM/09063 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Putulia (Part), Block-Barabani under Gourbazar Water supply scheme under RCFA Division-I, P.H.E. Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000192/2021-2022 | 1866/RCD-I | 28/10/2021 | 27/11/2021 | VISUVIOUS | 12.85 | 10.95 | 85.17 | 0
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Gourbazar PWSS for providing FHTC within Barabani Block of Paschim Bardhaman District under RCFA Division-I. | SM/09063 | Retrofitting | Extension of different dia HDPE pipe line for providing FHTC at Putulia (Part), Kharboni, Jamjuri and allied villages under Gourbazar W/S Scheme under RCFA Division-I PHE Dte. (Sl No. 06) | Assistant Engineer 1 | Junior Engineer | ORD/000143/2022-2023 | 1437/RCD I | 27/06/2022 | 11/08/2022 | VISUVIOUS | 2.75 | 0 | 0 | 0
4 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Gourbazar PWSS for providing FHTC within Barabani Block of Paschim Bardhaman District under RCFA Division-I. | SM/09063 | Retrofitting | Extension of different dia HDPE pipe line for providing FHTC at Gourbazar, Bindudihi, Hosenpara villages under Gourbazar W/S Scheme under RCFA Division-I PHE Dte. (Sl NO. 05) | Assistant Engineer 1 | Junior Engineer | ORD/000142/2022-2023 | 1436/RCD I | 27/06/2022 | 11/08/2022 | M/S S.K. ENTERPRISE | 4.97 | 4.48 | 90.17 | 0
5 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Gourbazar PWSS for providing FHTC within Barabani Block of Paschim Bardhaman District under RCFA Division-I. | SM/09063 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000008/2021-2022 | 437/RCD-I | 21/02/2022 | 21/02/2022 | Resource Division | 2.75 | 0 | 0 | 0
6 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Gourbazar PWSS for providing FHTC within Barabani Block of Paschim Bardhaman District under RCFA Division-I. | SM/09063 | Retrofitting | Installation of Jio Fiber connection for Six months under RCFA Division-I PHE Dte. |  |  | BILL/00329/2024-2025 | 153/24-25 | 19/07/2024 | 19/07/2024 | MUKHERJEE TRADERS | 0.07 | 0 | 0 | 0
7 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Gourbazar PWSS for providing FHTC within Barabani Block of Paschim Bardhaman District under RCFA Division-I. | SM/09063 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000006/2025-2026 | 2545/RCD-I | 01/09/2025 | 01/09/2025 | Resource Division | 1.09 | 0 | 0 | 0
Total | [13 empty] | 37.67 | 27.65 | 73.39