## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Churulia PWSS for providing FHTC within Jamuria Block. | SM/09064 | Retrofitting | Acceptance cum work order for Supply and delivery of C.I. Sluice valve and D.I Specials under Improvement of RCFA part-I Piped water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000055/2023-2024 | 1729/RCD-1 | 08/05/2023 | 18/05/2023 | SSPR VALVE MANUFACTURING PVT LTD | 45.31 | 45.31 | 100 | 100
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Churulia PWSS for providing FHTC within Jamuria Block. | SM/09064 | Retrofitting | Acceptance cum work order for Requirement of different type water regulating apparatus including water leakage protection apparatus etc. for Kendra Khottamdihi Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000056/2023-2024 | 1730/RCD-1 | 08/05/2023 | 18/05/2023 | MAKALI ENGINEERING CORPORATION | 45.99 | 45.99 | 100 | 0
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Churulia PWSS for providing FHTC within Jamuria Block. | SM/09064 | Retrofitting | Acceptance cum work order Construction of stand post on emergency basis at Rupnarayanpur, Rangamati area of Rupnarayanpur Zone under 4 Nos. retrofitting PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000987/2022-2023 | 1266/RCD-1 | 27/03/2023 | 11/04/2023 | B.B. CONSTRUCTION | 2.8 | 2.78 | 99.62 | 0
4 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Churulia PWSS for providing FHTC within Jamuria Block. | SM/09064 | Retrofitting | Acceptance cum work order for Additional work for laying of 450 mm dia distribution main under Lalganj Bridge by concrete conduit and allied MS work in connection to distribution network of Zone-XI (Part-1) for Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000251/2023-2024 | 2237/RCD-1 | 17/07/2023 | 16/08/2023 | R B ENTERPRISE | 16.06 | 13.45 | 83.74 | 100
5 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Churulia PWSS for providing FHTC within Jamuria Block. | SM/09064 | Retrofitting | Acceptance cum work order Additional work for laying & pushing of 600 to 1000 mm dia RCC (NP3) Hume pipe by adopting trench less technology (e.g. Jack Pushing Method etc) and MS pipe including supply of collar and allied work at Ethora Nuni more Panchgachiya and Lalganj more in connection to rising main Part-B under Improvement of RCFA Part-I (Zone-11, Part-9) PWSS under RCFA Division-I PHE Dte | Assistant Engineer 2 | Junior Engineer | ORD/000218/2023-2024 | 2224/RCD-I | 17/07/2023 | 16/08/2023 | M/S MONDAL ENTERPRISE | 30.17 | 25.6 | 84.85 | 100
6 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Churulia PWSS for providing FHTC within Jamuria Block. | SM/09064 | Retrofitting | Acceptance cum work order for Route Survey and Preparation of DPR for Augmentation of Churulia Piped Water Supply Scheme, Retrofitting of Churulia PWSS for providing FHTC within Jamuria Block., District-Paschim Bardhaman. | Assistant Engineer 2 | Junior Engineer,Junior Engineer 12 | ORD/000716/2023-2024 | 3373/RCD-1 | 21/11/2023 | 06/12/2023 | APEX ENGINEERING | 3.61 | 3.61 | 100 | 100
Total | [13 empty] | 143.94 | 136.75 | 95