## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Churulia PWSS for providing FHTC within Jamuria Block. | SM/09064 | Retrofitting | Acceptance cum work order for Supply and delivery of C.I. Sluice valve and D.I Specials under Improvement of RCFA part-I Piped water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000055/2023-2024 | 1729/RCD-1 | 08/05/2023 | 18/05/2023 | SSPR VALVE MANUFACTURING PVT LTD | 45.31 | 45.31 | 100 | 100
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Churulia PWSS for providing FHTC within Jamuria Block. | SM/09064 | Retrofitting | Acceptance cum work order for Requirement of different type water regulating apparatus including water leakage protection apparatus etc. for Kendra Khottamdihi Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000056/2023-2024 | 1730/RCD-1 | 08/05/2023 | 18/05/2023 | MAKALI ENGINEERING CORPORATION | 45.99 | 45.99 | 100 | 0
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Churulia PWSS for providing FHTC within Jamuria Block. | SM/09064 | Retrofitting | Acceptance cum work order Construction of stand post on emergency basis at Rupnarayanpur, Rangamati area of Rupnarayanpur Zone under 4 Nos. retrofitting PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000987/2022-2023 | 1266/RCD-1 | 27/03/2023 | 11/04/2023 | B.B. CONSTRUCTION | 2.8 | 2.78 | 99.62 | 0
Total | [13 empty] | 94.1 | 94.09 | 99.99