## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Bagdiha & adjoining mouzas for providing FHTC within Jamuria Block. | SM/09065 | Retrofitting | Acceptance cum Work Order for Laying 200 mm dia MS water pipe line with 600 mm dia MS casing pipe for railway crossing in between Jamuria (JMA) and Barabani (BBI) at KM 25/2-3 in Asansol Division under JJM of Retrofitting of Bagdiha & adjoining mouzas for providing FHTC within Jamuria Block under RCFA Division-I PHE Dte. | Assistant Engineer 1 | Junior Engineer | ORD/001124/2023-2024 | 931/RCD-I | 15/03/2024 | 14/04/2024 | SOMNATH SAMANTA | 23.15 | 22.61 | 97.69 | 100
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Bagdiha & adjoining mouzas for providing FHTC within Jamuria Block. | SM/09065 | Retrofitting | Fuel bill in faver of Ranajit auto for the month of October 2024 for one no vechile for office of the deputy superitending enginer RCFA W/S Circle PHE dte govt of west bengal |  |  | BILL/00992/2024-2025 |  | 04/12/2024 | 04/12/2024 | RANAJIT AUTO | 0.11 | 0 | 0 | 0
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Bagdiha & adjoining mouzas for providing FHTC within Jamuria Block. | SM/09065 | Retrofitting | acceptance cum work order Repairing of 450 mm dia DI pipe line at Baidyanathpur, Barachak, Jagaridih area of ASTA rising main of ASTA Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000946/2022-2023 | 1282/RCD-I | 27/03/2023 | 11/04/2023 | SIMA ENTERPRISE | 2.66 | 2.66 | 100 | 0
4 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Bagdiha & adjoining mouzas for providing FHTC within Jamuria Block. | SM/09065 | Retrofitting | Continuation work order for Hiring of SUV (A.C) (Non Airconditioned) Bharat Stage-IV/BS-IV purchased on or after 01.01.2022 with Diesel/LPG/CNG Engine. for the Office Use of the Deputy Superintending Engineer, RCFA W/S Circle, Public Health Engineering Directorate, Govt. of West Bengal (w.e.f. 01.09.2024 to 28.02.2025) (Sl No. 02) | Assistant Engineer 2 | Junior Engineer 12 | ORD/000160/2024-2025 | 2164_RCD-I | 30/08/2024 | 28/02/2025 | SHYAMAL MAJI | 0.9 | 0.33 | 36.73 | 33
5 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of Bagdiha & adjoining mouzas for providing FHTC within Jamuria Block. | SM/09065 | Retrofitting | Acceptance cum Providing FHTC of retrofitting at Kumardihi village (left out portion) of kumardihi Mouza, GP Ratibati, Block-Raniganj of Ratibati Water Supply Sceme under RCFA Division -I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000775/2022-2023 | 806/RCD-I | 06/03/2023 | 26/03/2023 | M/S MONDAL CONSTRUCTION | 13.78 | 12.41 | 90.07 | 100
Total | [13 empty] | 40.6 | 38.01 | 93.63