## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | RETROFITTING OF BAHULA MOUZA UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN PANDABESWAR BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | SM/09388 | Retrofitting | Formal work order for Providing FHTC through Retrofitting at Bahula (CT) (JL no. 30, Block - Pandabeswar) of RCFA Pt-II W/S Scheme under RCFA Division-I, PHE Dte. (Part-A) | Assistant Engineer 2 | Junior Engineer | ORD/000316/2021-2022 | 2143/RCD-I | 29/11/2021 | 29/03/2022 | GITA CONSTRUCTION | 81.14 | 61.82 | 76.18 | 0
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | RETROFITTING OF BAHULA MOUZA UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN PANDABESWAR BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | SM/09388 | Retrofitting | Formal work order for Providing FHTC through Retrofitting at Bahula (CT) (JL no. 30, Block - Pandabeswar) of RCFA Pt-II W/S Scheme under RCFA Division-I, PHE Dte. (Part-B) | Assistant Engineer 2 | Junior Engineer | ORD/000317/2021-2022 | 2144/RCD-I | 29/11/2021 | 29/03/2022 | MD AAMIR KHAN | 81 | 59.89 | 73.94 | 0
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | RETROFITTING OF BAHULA MOUZA UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN PANDABESWAR BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | SM/09388 | Retrofitting | Hiring of Maxi Cab (Non Air-conditioned)(Bharat stage-III/BS-III purchased on or after 01.05.2008 with Diesel/LPG/CNG Engine. as when required basis for supervision of FHTC related works under JJM) of RCFA Div-I, PHE Dte Govt, of West Bengal (w.e.f 16.08.2022 to 15.08.2023) | Assistant Engineer 2 | Junior Engineer | ORD/000204/2022-2023 | 1907/RCDI | 12/08/2022 | 24/08/2022 | PRAMIT CHATTERJEE | 1.8 | 0.79 | 44.12 | 0
4 | PASCHIM BARDHAMAN |  | RCFA Division -I | RETROFITTING OF BAHULA MOUZA UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN PANDABESWAR BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | SM/09388 | Retrofitting | Acceptance cum work order Repairing laying PVC pipe line and allied work at Asansol District Hospital under RCFA Division-I PHE Dte. (Sl. No. 34) | Assistant Engineer 2 | Junior Engineer | ORD/000060/2023-2024 | 1751/RCD I | 12/05/2023 | 27/05/2023 | UNITED CONSTRUCTION | 3.23 | 3.23 | 99.99 | 0
5 | PASCHIM BARDHAMAN |  | RCFA Division -I | RETROFITTING OF BAHULA MOUZA UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN PANDABESWAR BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | SM/09388 | Retrofitting | Cleaning compound premises, painting works and preparing approched road with sand and stone dust and other allied works at Kalyaneswari Inspection bunglow under Bahual Retrofitting under RCFA Division-I PHE Dte. (Sl No. 13) | Assistant Engineer 2 | Junior Engineer | ORD/000511/2021-2022 | 225/RCDI | 01/02/2022 | 08/02/2022 | JYOGOMAYA ENTERPRISE | 1.81 | 1.81 | 99.99 | 100
6 | PASCHIM BARDHAMAN |  | RCFA Division -I | RETROFITTING OF BAHULA MOUZA UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN PANDABESWAR BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | SM/09388 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000001/2021-2022 | 2280/RCD-I | 12/12/2021 | 12/12/2021 | Resource Division | 20.23 | 0 | 0 | 0
7 | PASCHIM BARDHAMAN |  | RCFA Division -I | RETROFITTING OF BAHULA MOUZA UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN PANDABESWAR BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | SM/09388 | Retrofitting | Fuel bill for WB37D0482 for the month of Sept 2023 |  |  | BILL/00755/2023-2024 | 339/1/23-24 | 17/10/2023 | 17/10/2023 | RANAJIT AUTO | 0.22 | 0 | 0 | 0
8 | PASCHIM BARDHAMAN |  | RCFA Division -I | RETROFITTING OF BAHULA MOUZA UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN PANDABESWAR BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | SM/09388 | Retrofitting |  |  |  | BILL/00327/2023-2024 | 149/1/23-24 | 21/07/2023 | 21/07/2023 | RANAJIT AUTO | 0.17 | 0 | 0 | 0
9 | PASCHIM BARDHAMAN |  | RCFA Division -I | RETROFITTING OF BAHULA MOUZA UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN PANDABESWAR BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | SM/09388 | Retrofitting | Hire charges and fuel bill for Executive Engineer RCFA Division-I PHE Dte |  |  | BILL/00823/2023-2024 | 291/23-24 | 10/10/2023 | 10/10/2023 | NIRMALA TRADERS | 0.06 | 0 | 0 | 0
10 | PASCHIM BARDHAMAN |  | RCFA Division -I | RETROFITTING OF BAHULA MOUZA UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN PANDABESWAR BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | SM/09388 | Retrofitting | Fuel bill of Ranajit auto against vehicle no WB 37D 0482 for the month of May |  |  | BILL/00265/2023-2024 | 116/1/23-24 | 03/07/2023 | 03/07/2023 | RANAJIT AUTO | 0.23 | 0 | 0 | 0
11 | PASCHIM BARDHAMAN |  | RCFA Division -I | RETROFITTING OF BAHULA MOUZA UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN PANDABESWAR BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | SM/09388 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Bhaluka & Sonepur Bazari under Kendra Khottamdih Water Supply Scheme under RCFA Division-I PHE Dte. |  |  | BILL/00619/2023-2024 | 204/23-24 | 18/08/2023 | 18/08/2023 | MACHINO TECHNO | 19.87 | 0 | 0 | 0
12 | PASCHIM BARDHAMAN |  | RCFA Division -I | RETROFITTING OF BAHULA MOUZA UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN PANDABESWAR BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | SM/09388 | Retrofitting | Hire charges and fuel bill for the month of July 2023 to Sept 2023 |  |  | BILL/00756/2023-2024 | 338/23-24 | 17/10/2023 | 17/10/2023 | NIRMALA TRADERS | 1.2 | 0 | 0 | 0
13 | PASCHIM BARDHAMAN |  | RCFA Division -I | RETROFITTING OF BAHULA MOUZA UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN PANDABESWAR BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | SM/09388 | Retrofitting | April 2023 |  |  | BILL/00559/2023-2024 | 77/23-24 | 06/06/2023 | 06/06/2023 | SHYAMAL MAJI | 0.15 | 0 | 0 | 0
14 | PASCHIM BARDHAMAN |  | RCFA Division -I | RETROFITTING OF BAHULA MOUZA UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN PANDABESWAR BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | SM/09388 | Retrofitting | fuel bill april 2023 shyamal maji |  |  | BILL/00560/2023-2024 | 77/1/23-24 | 06/06/2023 | 06/06/2023 | RANAJIT AUTO | 0.2 | 0 | 0 | 0
15 | PASCHIM BARDHAMAN |  | RCFA Division -I | RETROFITTING OF BAHULA MOUZA UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN PANDABESWAR BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | SM/09388 | Retrofitting | Hire charge and fuel bill for the month of July 2023 to September 2023 |  |  | BILL/00754/2023-2024 | 339/23-24 | 17/10/2023 | 17/10/2023 | SHYAMAL MAJI | 0.15 | 0 | 0 | 0
16 | PASCHIM BARDHAMAN |  | RCFA Division -I | RETROFITTING OF BAHULA MOUZA UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN PANDABESWAR BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | SM/09388 | Retrofitting | Arrangement of brakfast and lunch box, etc. for DWSM meeting held on 22.06.2024 at ADDA conference hall |  |  | BILL/00256/2024-2025 | 121/24-25 | 03/07/2024 | 03/07/2024 | MUKHERJEE TRADERS | 0.28 | 0 | 0 | 0
17 | PASCHIM BARDHAMAN |  | RCFA Division -I | RETROFITTING OF BAHULA MOUZA UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN PANDABESWAR BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | SM/09388 | Retrofitting | Acceptance cum work order Supply and installation of sluice valve, shifting of household connection instead of old AC pipe line to distribution branch and etc allied works at Baidyanathpur Namopara, Bouripara and adjacent area under Baidyanathpur W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000926/2022-2023 | 1258/ RCD I | 27/03/2023 | 11/04/2023 | SOMNATH SAMANTA | 2.5 | 2.49 | 99.59 | 0
18 | PASCHIM BARDHAMAN |  | RCFA Division -I | RETROFITTING OF BAHULA MOUZA UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN PANDABESWAR BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | SM/09388 | Retrofitting | Hiring of SUV (A.C) (Non-Air conditioned) Bharat Stage-IV/BS-IV purchased on or after 01.01.2022 with Diesel/LPG/CNG Engine. For the office Use of the Deputy Superintending Engineer Engineer, RCFA W/S Circle, PHE Dte Govt. of West Bengal (w.e.f 01.02.2023 to 31.07.2023) | Assistant Engineer 2 | Junior Engineer | ORD/000872/2022-2023 | 455/RCDI | 31/01/2023 | 31/07/2023 | SHYAMAL MAJI | 0.9 | 0.3 | 33.33 | 80
19 | PASCHIM BARDHAMAN |  | RCFA Division -I | RETROFITTING OF BAHULA MOUZA UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN PANDABESWAR BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | SM/09388 | Retrofitting | Acceptance cum work order Laying of 90 mm dia HDPE pipe line and etc allied works at Baidyanathpur Namopara, Bouripara under Baidyanathpur W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000929/2022-2023 | 1264/RCD-I | 27/03/2023 | 11/04/2023 | SOMNATH SAMANTA | 2.72 | 2.59 | 95.28 | 0
20 | PASCHIM BARDHAMAN |  | RCFA Division -I | RETROFITTING OF BAHULA MOUZA UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN PANDABESWAR BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | SM/09388 | Retrofitting | Acceptance cum work order Laying of different dia distribution pipe line at Baidyanathpur Namopara, Bouripara and adjacent area under Baidyanathpur W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000942/2022-2023 | 1276/RCD-I | 27/03/2023 | 11/04/2023 | SOMNATH SAMANTA | 3.61 | 3.48 | 96.53 | 0
21 | PASCHIM BARDHAMAN |  | RCFA Division -I | RETROFITTING OF BAHULA MOUZA UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN PANDABESWAR BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | SM/09388 | Retrofitting | Construction of guard wall on emergency basis near Kalyaneswari I.B. gate under Retrofitting Bahula mouza RCFA Division-I PHE Dte. (Sl No. 12) | Assistant Engineer 2 | Junior Engineer | ORD/000064/2022-2023 | 1111/RCDI | 13/05/2022 | 12/06/2022 | R B ENTERPRISE | 4.7 | 4.47 | 95.16 | 100
22 | PASCHIM BARDHAMAN |  | RCFA Division -I | RETROFITTING OF BAHULA MOUZA UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN PANDABESWAR BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | SM/09388 | Retrofitting | Emergency basis construction of culvert near Kalyaneswari I.B. gate under Retrofitting Bahula mouza W/S Scheme under RCFA Division-I PHE Dte. (Sl No. 17) | Assistant Engineer 2 | Junior Engineer | ORD/000069/2022-2023 | 1116/RCDI | 13/05/2022 | 27/06/2022 | R B ENTERPRISE | 4.93 | 4.92 | 99.74 | 100
23 | PASCHIM BARDHAMAN |  | RCFA Division -I | RETROFITTING OF BAHULA MOUZA UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN PANDABESWAR BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | SM/09388 | Retrofitting | Continuation work order for Probable Office expenditure of office of the Executive Engineer to meet up day to day various office & site expenses under RCFA Div-I PHE Dte (w.e.f 01.02.2023 to 31.07.2023) | Assistant Engineer 2 | Junior Engineer | ORD/000969/2022-2023 | 3439/RCD-I | 30/12/2022 | 30/06/2023 | M/S KALYANI ENTERPRISE | 4.51 | 4.51 | 99.85 | 100
24 | PASCHIM BARDHAMAN |  | RCFA Division -I | RETROFITTING OF BAHULA MOUZA UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN PANDABESWAR BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | SM/09388 | Retrofitting | Supply of Computer and accessories for Office use under RCFA Division-I PHE Dte. District - Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | ORD/000309/2023-2024 | 2040/RCD-I | 30/06/2023 | 07/07/2023 | MUKHERJEE TRADERS | 0.86 | 0.86 | 100 | 100
25 | PASCHIM BARDHAMAN |  | RCFA Division -I | RETROFITTING OF BAHULA MOUZA UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN PANDABESWAR BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | SM/09388 | Retrofitting | Acceptance cum work order Cleaning compound premises of Ballavpur Hospital & Unionpara Head Works Site under RCFA Part-II W/S Scheme under RCFA Div-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000330/2023-2024 | 2452/RCD-I | 18/08/2023 | 02/09/2023 | SWATI CORPORATION | 0.97 | 0.96 | 99.32 | 100
26 | PASCHIM BARDHAMAN |  | RCFA Division -I | RETROFITTING OF BAHULA MOUZA UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN PANDABESWAR BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | SM/09388 | Retrofitting | Emergent sinking of one no 200 X 165 mm dia rig bore tube well at ESI Hospital, Asansole, Paschim Bardhaman under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000441/2023-2024 | Camp-2-ESI-Hospital-AE-II | 27/09/2023 | 30/09/2023 | M/S CHANDI CHARAN ROY | 7.84 | 7.68 | 98.02 | 100
27 | PASCHIM BARDHAMAN |  | RCFA Division -I | RETROFITTING OF BAHULA MOUZA UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN PANDABESWAR BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | SM/09388 | Retrofitting | Emergent sinking of one no 200 X 165 mm dia rig bore tube well at Health World Hospital, Asansole, Paschim Bardhaman under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000440/2023-2024 | Camp-02-Health-World-Hosp | 27/09/2023 | 30/09/2023 | M/S CHANDI CHARAN ROY | 7.77 | 7.65 | 98.39 | 100
Total | [13 empty] | 253.06 | 167.47 | 66.18