## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR DAKHIN KHANDA MOUZA (Jl No. 36) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | SM/09389 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Dakshin Khanda (Jl No. 36) Block ¿ Andal of RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. (Part ¿ A) | Assistant Engineer 2 | Junior Engineer | ORD/000299/2021-2022 | 2124/RCD-I | 29/11/2021 | 29/12/2021 | A.K.CONSTRUCTION | 14.4 | 0 | 0 | 0
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR DAKHIN KHANDA MOUZA (Jl No. 36) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | SM/09389 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Dakshin Khanda (Jl No. 36) Block ¿ Andal of RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. (Part ¿ B) | Assistant Engineer 2 | Junior Engineer | ORD/000300/2021-2022 | 2125/RCD-I | 29/11/2021 | 29/12/2021 | UNITED CONSTRUCTION | 14.36 | 0 | 0 | 0
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR DAKHIN KHANDA MOUZA (Jl No. 36) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | SM/09389 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Dakshin Khanda (Jl No. 36) Block ¿ Andal of RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. (Part ¿ C) | Assistant Engineer 2 | Junior Engineer | ORD/000301/2021-2022 | 2126/RCD-I | 29/11/2021 | 29/12/2021 | DURGADAS MONDAL | 14.37 | 0 | 0 | 0
4 | PASCHIM BARDHAMAN |  | RCFA Division -I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR DAKHIN KHANDA MOUZA (Jl No. 36) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | SM/09389 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Dakshin Khanda (Jl No. 36) Block ¿ Andal of RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. (Part ¿ D) | Assistant Engineer 2 | Junior Engineer | ORD/000302/2021-2022 | 2127/RCD-I | 29/11/2021 | 29/12/2021 | SIMA ENTERPRISE | 14.42 | 0 | 0 | 0
5 | PASCHIM BARDHAMAN |  | RCFA Division -I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR DAKHIN KHANDA MOUZA (Jl No. 36) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | SM/09389 | Retrofitting | Acceptance cum work for Providing FHTC through Retrofitting at Dakshin Khanda (Jl No. 36) Block ¿ Andal of RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. (Part ¿ E) | Assistant Engineer 2 | Junior Engineer | ORD/000303/2021-2022 | 2128/RCD-I | 29/11/2021 | 29/12/2021 | M/S KALYANI ENTERPRISE | 14.45 | 0 | 0 | 0
6 | PASCHIM BARDHAMAN |  | RCFA Division -I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR DAKHIN KHANDA MOUZA (Jl No. 36) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | SM/09389 | Retrofitting | Laying of 25 mm dia PVC pipe line at Ukhra Adarsha Hindi High School and installation of Street stand post and etc. allied works at Dakshin Khanda area under RCFA Division-I PHE Dte. (Sl No. 12) | Assistant Engineer 2 | Junior Engineer | ORD/000510/2021-2022 | 224/RCD I | 01/02/2022 | 16/02/2022 | UNITED CONSTRUCTION | 4.63 | 0 | 0 | 0
7 | PASCHIM BARDHAMAN |  | RCFA Division -I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR DAKHIN KHANDA MOUZA (Jl No. 36) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | SM/09389 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Dakshin Khanda (Jl No. 36) Block ¿ Andal of RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. (Part ¿ F) | Assistant Engineer 2 | Junior Engineer | ORD/000304/2021-2022 | 2129/RCD-I | 29/11/2021 | 29/12/2021 | M/S SUBHRADEEP | 16.51 | 0 | 0 | 0
8 | PASCHIM BARDHAMAN |  | RCFA Division -I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR DAKHIN KHANDA MOUZA (Jl No. 36) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | SM/09389 | Retrofitting | Sub Soil Investigation for 200 cum capacity RCC Over Head Reservoir of Barabani Block for Augmentation of Jamgram Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | ORD/000526/2022-2023 | 3139/RCDI | 12/12/2022 | 19/12/2022 | P.K TEWARY DRILLING CO. | 0.55 | 0 | 0 | 100
9 | PASCHIM BARDHAMAN |  | RCFA Division -I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR DAKHIN KHANDA MOUZA (Jl No. 36) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | SM/09389 | Retrofitting | Sub Soil Investigation for 350 cum capacity RCC Over Head Reservoir of Barabani Block for Augmentation of Panuria Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | ORD/000529/2022-2023 | 3142/RCDI | 12/12/2022 | 19/12/2022 | P.K TEWARY DRILLING CO. | 0.55 | 0 | 0 | 100
10 | PASCHIM BARDHAMAN |  | RCFA Division -I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR DAKHIN KHANDA MOUZA (Jl No. 36) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | SM/09389 | Retrofitting | Sub Soil Investigation for 300 cum capacity RCC Over Head Reservoir of Barabani Block for Augmentation of Sarisatali Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | ORD/000528/2022-2023 | 3141/RCDI | 12/12/2022 | 19/12/2022 | P.K TEWARY DRILLING CO. | 0.55 | 0 | 0 | 100
11 | PASCHIM BARDHAMAN |  | RCFA Division -I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR DAKHIN KHANDA MOUZA (Jl No. 36) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | SM/09389 | Retrofitting | Sub Soil Investigation for 200 cum capacity RCC Over Head Reservoir of Jamuria Block for Augmentation of Churulia Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | ORD/000531/2022-2023 | 3144/RCDI | 12/12/2022 | 19/12/2022 | P.K TEWARY DRILLING CO. | 0.55 | 0 | 0 | 100
12 | PASCHIM BARDHAMAN |  | RCFA Division -I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR DAKHIN KHANDA MOUZA (Jl No. 36) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | SM/09389 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000002/2021-2022 | 2281/RCD-I | 12/12/2021 | 12/12/2021 | Resource Division | 10.17 | 0 | 0 | 0
13 | PASCHIM BARDHAMAN |  | RCFA Division -I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR DAKHIN KHANDA MOUZA (Jl No. 36) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | SM/09389 | Retrofitting | Arrangeme of tiffin packets for DWSM meeting held on 27.07.2024 at ADDA Conferene hall, Asansol, Paschim Bardhaman |  |  | BILL/00936/2024-2025 | 241/24-25 | 23/08/2024 | 23/08/2024 | BLESSING ENTERPRISE | 0.09 | 0 | 0 | 0
14 | PASCHIM BARDHAMAN |  | RCFA Division -I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR DAKHIN KHANDA MOUZA (Jl No. 36) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | SM/09389 | Retrofitting | Installation of quick Heal Anti Viru for 3 years under RCFA Diivison-I PHE Dte. |  |  | BILL/00937/2024-2025 | 245/24-25 | 27/08/2024 | 27/08/2024 | MUKHERJEE TRADERS | 0.09 | 0 | 0 | 0
15 | PASCHIM BARDHAMAN |  | RCFA Division -I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR DAKHIN KHANDA MOUZA (Jl No. 36) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | SM/09389 | Retrofitting | Arrangement of breakfast (Tea with snacks) for DWSM meeting held on 27.07.2024 at ADDA Conference hall, Asansol Paschim Bardhaman under RCFA Division-I PHE Dte. |  |  | BILL/00935/2024-2025 | 240/24-25 | 23/08/2024 | 23/08/2024 | BLESSING ENTERPRISE | 0.08 | 0 | 0 | 0
16 | PASCHIM BARDHAMAN |  | RCFA Division -I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR DAKHIN KHANDA MOUZA (Jl No. 36) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | SM/09389 | Retrofitting | Acceptance cum work order for Laying and interconnection work of different dia HDPE pipe line unde Dakshin Khanda area Khandra Zone under RCFA Pt-II W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000489/2021-2022 | 118/RCD-I | 20/01/2022 | 19/02/2022 | UNITED CONSTRUCTION | 13.96 | 0 | 0 | 0
Total | [13 empty] | 119.73 | 0 | 0