## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Hiring of maxi cab (Non-airconditioned)Bharat stage-II/BS-II purchased on or after 01.05.2008 with diesel/LPG/CNG engine for the office use of the Assistant Engineer, RCFA Div-I, PHE dte, Govt of West Bengal (w.e.f 01.09.2021 to 31.08.2022) | Assistant Engineer 1 | Junior Engineer | ORD/000194/2021-2022 | 1541/RCD I | 31/08/2021 | 31/08/2022 | KHEPI MAA TRADERS | 1.73 | 1.14 | 65.65 | 0
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order for Repairing and renovation of Rupnarayanpur OHR of Capacity 1135 cum staging height 20 mtr under RCFA Part-I W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000163/2021-2022 | 1588/RCD-I | 07/09/2021 | 07/10/2021 | BKB INFRA PROJECTS PVT LTD | 37.48 | 37.45 | 99.92 | 0
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Engagement of 01 (One) person under control of 02 (Two) nos Assistant Engineers of RCFA Division-I for day to day report and return of FHTC as per scheme wise, Panchayet wise and updation of JJM and verification of FHTC connection of School Aganawadi and Heath Centre and monitoring of report return of training of Asha Karmi under Health Department as per direction of EIC. under RCFA Division-I PHE Dte. (w.e.f. 01.01.2022 to 31.12.2022) (Sl no 03) | Assistant Engineer 1 | Junior Engineer | ORD/000453/2021-2022 | 2456/RCD I | 31/12/2021 | 31/12/2022 | MUKHERJEE TRADERS | 1.73 | 0.87 | 50 | 0
4 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Engagement of 01 (One) person under control of 02 (Two) nos Assistant Engineers of RCFA Division-I for day to day report and return of FHTC as per scheme wise, Panchayet wise and updation of JJM and verification of FHTC connection of School Aganawadi and Heath Centre and monitoring of report return of training of Asha Karmi under Health Department as per direction of EIC. under RCFA Division-I PHE Dte. (w.e.f. 01.01.2022 to 31.12.2022)(Sl no 03) | Assistant Engineer 1 | Junior Engineer | ORD/000838/2021-2022 | 2456/RCD- 1 | 31/12/2021 | 31/12/2022 | MUKHERJEE TRADERS | 1.73 | 0.87 | 50 | 0
5 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order for Urgent basis repairing work of Churulia OHR of capacity 100000 gallons and 20 mtr staging height under Churulia Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000293/2021-2022 | 2025/RCD-I | 24/11/2021 | 24/12/2021 | ASHA CONSTRUCTION | 15.47 | 15.33 | 99.13 | 0
6 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order for Construction of CWR (90 cum) at Surjanagar Head Works Site to replace existing damaged CWR under Improvement of RCFA (Part-I) Piped Water Supply Scheme. |  |  | ORD/000939/2021-2022 | 376_RCD_I | 15/02/2022 | 17/03/2022 | MD AAMIR KHAN | 0 | 0 | NAN | 0
7 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order for Construction of CWR (90 cum) at Surjanagar Head Works Site to replace existing damaged CWR under Improvement of RCFA (Part-I) Piped Water Supply Scheme. | Assistant Engineer 2 | Junior Engineer | ORD/000490/2021-2022 | 376/RCD-I | 15/02/2022 | 17/03/2022 | MD AAMIR KHAN | 22.72 | 10.42 | 45.84 | 100
8 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum Work Order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone - XI (Part-6 Distribution Segment) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000541/2021-2022 | 496/RCD-I | 24/02/2022 | 15/02/2025 | UMA ENTERPRISE | 63.83 | 50.69 | 79.42 | 70
9 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum Work Order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone - XI (Part-2 Distribution Segment) under RCFA Division-I PHE Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000532/2021-2022 | 492/RCD-I | 24/02/2022 | 25/05/2022 | SNEHA ELECTRIC | 25.78 | 25.39 | 98.48 | 75
10 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum Work Order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone - XI (Part-7 Distribution Segment) under RCFA Division-I PHE Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000542/2021-2022 | 497/RCD-I | 24/02/2022 | 25/05/2022 | UNITED CONSTRUCTION | 23.75 | 23.72 | 99.88 | 80
11 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum Work Order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone - XI (Part-8 Distribution Segment) under RCFA Division-I PHE Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000543/2021-2022 | 498/RCD-I | 24/02/2022 | 25/05/2022 | SIMA ENTERPRISE | 30.98 | 29.26 | 94.45 | 81
12 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum Work Order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone - XI (Part-9 Distribution Segment) under RCFA Division-I PHE Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000544/2021-2022 | 499/RCD-I | 24/02/2022 | 25/05/2022 | SOMNATH SAMANTA | 39.28 | 38.73 | 98.61 | 98
13 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum Work Order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone - XI (Part-3 Distribution Segment) under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000533/2021-2022 | 493/RCD-I | 24/02/2022 | 01/04/2023 | VISUVIOUS | 25.41 | 23.7 | 93.28 | 100
14 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum Work Order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone - XI (Part-5 Distribution Segment) under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000538/2021-2022 | 495/RCD-I | 24/02/2022 | 01/03/2025 | M/S B.K. CONSTRUCTION | 44.11 | 37.17 | 84.27 | 100
15 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-VI under RCFA Division-I PHE Dte. (Part-A) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000002/2022-2023 | 932/RCD-I | 26/04/2022 | 01/01/2024 | DIP CONSTRUCTION | 61.83 | 51.53 | 83.35 | 100
16 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-VI under RCFA Division-I PHE Dte. (Part-B) | Assistant Engineer 1 | Junior Engineer | ORD/000003/2022-2023 | 933/RCD-I | 26/04/2022 | 25/07/2022 | M/S K & KONAR CONSTRUCTION | 75.35 | 69.5 | 92.23 | 90
17 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-IX under RCFA Division-I PHE Dte. (Part-A) | Assistant Engineer 1 | Junior Engineer | ORD/000004/2022-2023 | 934/RCD-I | 26/04/2022 | 25/07/2022 | SRI KRISHNA ENTERPRISE | 86.98 | 30.45 | 35 | 65
18 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-IX under RCFA Division-I PHE Dte. (Part-B) | Assistant Engineer 1 | Junior Engineer | ORD/000005/2022-2023 | 935/RCD-I | 26/04/2022 | 25/07/2022 | KHEPI MAA TRADERS | 71.89 | 67.45 | 93.82 | 75
19 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-XIII under RCFA Division-I PHE Dte. (Part-A) | Assistant Engineer 1 | Junior Engineer | ORD/000006/2022-2023 | 936/RCD-I | 26/04/2022 | 25/07/2022 | M/S MONI TRADERS | 75.17 | 40.2 | 53.47 | 70
20 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Formal Work Order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone - I (Dendua OHR Site) under RCFA Division-I PHE Dte. (Part - A) | Assistant Engineer 1,Assistant Engineer 2,Assistant Engineer 7 | Junior Engineer | ORD/000013/2022-2023 | 1038/RCD-I | 10/05/2022 | 01/08/2025 | ASHA CONSTRUCTION | 147.65 | 58.28 | 39.47 | 100
21 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-XIII under RCFA Division-I PHE Dte. (Part-D) (2nd Call) | Assistant Engineer 1 | Junior Engineer | ORD/000011/2022-2023 | 1007/RCD-I | 05/05/2022 | 03/08/2022 | GITASREE FABRICATION | 77.41 | 66.72 | 86.18 | 85
22 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Formal Work Order for Distribution Network for Improvement RCFA Part-I Water Supply within command area of Zone-VI under RCFA Division-I PHE Dte. (Part ¿ C) | Assistant Engineer 1 | Junior Engineer | ORD/000096/2022-2023 | 1214/RCD-I | 30/05/2022 | 28/08/2022 | RANJIB GHATAK | 100.72 | 90.61 | 89.96 | 90
23 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Formal Work Order for Improvement of RCFA Part-I Water Supply Scheme within command area of Zone-VIII with LDS & FHTC Work | Assistant Engineer 1 | Junior Engineer | ORD/000105/2022-2023 | 1329/RCD-I | 09/06/2022 | 06/12/2022 | SWATI CORPORATION | 399.2 | 327.2 | 81.97 | 100
24 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-XIII under RCFA Division-I PHE Dte. (Part-B) (2nd Call) | Assistant Engineer 2 | Junior Engineer | ORD/000010/2022-2023 | 1006/RCD-I | 05/05/2022 | 04/07/2022 | M/S SANTANU PALIT & CO. | 93.2 | 0 | 0 | 70
25 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order for Rising Main for Improvement RCFA Part-I Water Supply Scheme for Salanpur and Barabani Block under RCFA Div-I PHE Dte. (Part B) | Assistant Engineer 1 | Junior Engineer | ORD/000001/2022-2023 | 931/RCD-I | 26/04/2022 | 01/05/2024 | M/S MONDAL ENTERPRISE | 82.94 | 61.98 | 74.73 | 100
26 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Formal Work Order for Distribution Network for Improvement RCFA Part-I Water Supply within command area of Zone-IX under RCFA Division-I PHE Dte. (Part C) | Assistant Engineer 1,Assistant Engineer 3,Assistant Engineer 4 | Junior Engineer | ORD/000095/2022-2023 | 1213/RCD-I | 30/05/2022 | 01/12/2025 | T M CONCRETE CREATION PRIVATE LIMITED | 131.44 | 108.9 | 82.85 | 100
27 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-XIII under RCFA Division-I PHE Dte. (Part-C) | Assistant Engineer 1 | Junior Engineer | ORD/000119/2022-2023 | 1605/RCD-I | 06/07/2022 | 04/10/2022 | PINKI ENTERPRISE | 78.73 | 37.76 | 47.96 | 80
28 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-VII under RCFA Division-I PHE Dte. (Part-C) | Assistant Engineer 1 | Junior Engineer | ORD/000126/2022-2023 | 1612/RCD-I | 06/07/2022 | 04/10/2022 | PINKI ENTERPRISE | 60.85 | 21.88 | 35.96 | 65
29 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-VII under RCFA Division-I PHE Dte. (Part-B) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000125/2022-2023 | 1611/RCD-I | 06/07/2022 | 01/04/2026 | UNITED CONSTRUCTION | 55.84 | 16.36 | 29.3 | 75
30 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-VII under RCFA Division-I PHE Dte. (Part-E) | Assistant Engineer 1 | Junior Engineer | ORD/000128/2022-2023 | 1614/RCD-I | 06/07/2022 | 04/10/2022 | TARA CONSTRUCTION | 88.3 | 43.84 | 49.64 | 70
31 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order for Providing FHTC work for the Command area of Zone-XI (Part-7 Segment) for Improvement of RCFA Part-I Water Supply Scheme under RCFA Division-I PHE Dte | Assistant Engineer 1 | Junior Engineer | ORD/000130/2022-2023 | 1702/RCD-I | 14/07/2022 | 28/08/2022 | UNITED CONSTRUCTION | 20.25 | 19.99 | 98.73 | 5
32 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order for Construction of 250 cum capacity 20 Mtr staging height RCC Over Head Reservoir (Pipe connection and cost of pipes, specials at (Zone-VI) for Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 1 | Junior Engineer | ORD/000205/2022-2023 | 1874/RCD-I | 04/08/2022 | 16/08/2022 | KAMIRUL SK & CO | 76.6 | 68.94 | 90 | 100
33 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order for Providing FHTC work for the Command area of Zone-XI (Part-8 Segment) for Improvement of RCFA Part-I Water Supply Scheme under RCFA Division-I PHE Dte | Assistant Engineer 2 | Junior Engineer | ORD/000163/2022-2023 | 1712/RCD-I | 15/07/2022 | 29/08/2022 | SIMA ENTERPRISE | 24.13 | 0 | 0 | 5
34 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order for Providing FHTC work for the Command area of Zone-XI (Part-5 Segment) for Improvement of RCFA Part-I Water Supply Scheme under RCFA Division-I PHE Dte | Assistant Engineer 1 | Junior Engineer | ORD/000158/2022-2023 | 1707/RCD-I | 14/07/2022 | 28/08/2022 | M/S B.K. CONSTRUCTION | 32.05 | 20.27 | 63.25 | 100
35 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Distribution Network for Improvement of RCFA Part-II Water Supply Scheme Under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000294/2022-2023 | 2451/RCD-I | 13/10/2022 | 11/04/2023 | SINGHA ROY & CO. | 270.57 | 65.85 | 24.34 | 0
36 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Formal Work Oder for Construction of 900 cum capacity 20 Mtr staging height RCC Over Head Reservoir (Pipe connection and cost of pipes, specials at (Zone-XI) for Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 1 | Junior Engineer | ORD/000380/2022-2023 | 2005/RCD-I | 25/08/2022 | 25/08/2023 | AMAR CONSTRUCTION | 181 | 162.9 | 90 | 100
37 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order of Construction of CWR (Clear Water Reservoir) of Capacity 500 cum and allied work at Dendua under Improvement of RCFA Part-I Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000302/2022-2023 | 2484/RCD I | 18/10/2022 | 15/02/2023 | D.S. ENTERPRISE | 61.78 | 43.72 | 70.77 | 96
38 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Sub Soil Investigation for 900 cum capacity RCC Over Head Reservoir (Zone-XI) of Barabani Block for Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | ORD/000530/2022-2023 | 3143/RCDI | 12/12/2022 | 19/12/2022 | P.K TEWARY DRILLING CO. | 0.55 | 0 | 0 | 100
39 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Hiring of SUV (A.C) (Non-Air conditioned) Bharat Stage-VI/BS-VI purchased on or after 01.01.2022 with Diesel/LPG/CNG Engine. For the office Use of the Executive Engineer, RCFA Div-I, PHE Dte Govt. of West Bengal (w.e.f 01.06.2022 to 30.11.2022) | Assistant Engineer 2 | Junior Engineer | ORD/000596/2022-2023 | Spot/NIQ/Camp-02/Office/A | 31/05/2022 | 06/06/2022 | PRASENJIT DEY | 0.9 | 0 | 0 | 0
40 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Formal Work Order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-VII under RCFA Division-I PHE Dte. (Part-F) | Assistant Engineer 1 | Junior Engineer | ORD/000327/2022-2023 | 2404/RCD-I | 30/09/2022 | 29/03/2023 | GITA CONSTRUCTION | 201.57 | 131.66 | 65.32 | 67
41 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Hiring of SUV (A.C) (Non-Air conditioned) Bharat Stage-VI/BS-VI purchased on or after 01.01.2022 with Diesel/LPG/CNG Engine. For the office Use of the Executive Engineer, RCFA Div-I, PHE Dte Govt. of West Bengal (w.e.f 01.06.2022 to 30.11.2022) | Assistant Engineer 2 | Junior Engineer | ORD/000595/2022-2023 | SpotNIQ.Camp-02/Office/AE | 31/05/2022 | 30/11/2022 | PRASENJIT DEY | 0.9 | 0 | 0 | 0
42 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Continuation work order for Hiring of SUV (A.C) (Non-Air conditioned) Bharat Stage-VI/BS-VI purchased on or after 01.01.2022 with Diesel/LPG/CNG Engine, for the office Use of the Executive Engineer, RCFA Division-I PHE Dte. (w.e.f. 01.12.2022 to 31.05.2023) | Assistant Engineer 2 | Junior Engineer | ORD/000955/2022-2023 | 3057/RCD-I | 30/11/2022 | 31/05/2023 | PRASENJIT DEY | 0.9 | 0 | 0 | 0
43 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Formal work order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone - I (Dendua OHR Site) under RCFA Division-I PHE Dte. (Part - B) | Assistant Engineer 1 | Junior Engineer | ORD/000012/2022-2023 | 1020/RCD-I | 06/05/2022 | 02/11/2022 | SWATI CORPORATION | 149.9 | 63.87 | 42.61 | 85
44 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum Work Order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone - XI (Part-4 Distribution Segment) under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000536/2021-2022 | 494/RCD-I | 24/02/2022 | 01/01/2025 | DAWN CONSTRUCTION | 68.87 | 65.56 | 95.19 | 100
45 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-VII under RCFA Division-I PHE Dte. (Part-D) | Assistant Engineer 1 | Junior Engineer | ORD/000127/2022-2023 | 1613/RCD-I | 06/07/2022 | 04/10/2022 | KONAR CONSTRUCTION | 64.73 | 23.94 | 36.98 | 75
46 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum Work Order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone - XI (Part-1 Distribution Segment) under RCFA Division-I PHE Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000531/2021-2022 | 491/RCD-I | 24/02/2022 | 25/05/2022 | R B ENTERPRISE | 27.59 | 26.92 | 97.56 | 85
47 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Repalcing of old and damaged C.I. spiral stairs and other allied minor repairing works at Panchgachia OHR (Capacity 55000 gallon staging height 10 mtr under RCFA Part-I W/S Scheme under RCFA Division-I PHE Dte.(Sl no 06) | Assistant Engineer 1 | Junior Engineer | ORD/000612/2021-2022 | 635/RCD 1 | 09/03/2022 | 24/03/2022 | RUBY CONSTRUCTION | 3.87 | 3.83 | 99.02 | 0
48 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Formal Work Order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone - I (Dendua OHR Site) under RCFA Division-I PHE Dte. (Part - C) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000014/2022-2023 | 1039/RCD-I | 10/05/2022 | 01/08/2025 | DAS & CHAKRABORTY | 130.86 | 56.55 | 43.21 | 100
49 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Laying of Rising Main (Part-B) at Mohismura Culvat crossing by constructing concrete piller, MS work and allied works under Improvement of RCFA Part-I W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000581/2022-2023 | 3289/RCD I | 20/12/2022 | 06/01/2023 | M/S MONDAL ENTERPRISE | 10.26 | 8.52 | 83.02 | 100
50 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Formal Work Order for Improvement of RCFA Part-I Water Supply Scheme within command area of Zone-V with LDS & FHTC work | Assistant Engineer 1,Assistant Engineer 3 | Junior Engineer | ORD/000117/2022-2023 | 1379/RCD-I | 17/06/2022 | 14/12/2022 | MRITYUNJOY MUKHERJEE & CO. | 466.46 | 346.89 | 74.37 | 80
51 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-VII under RCFA Division-I PHE Dte. (Part-A) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer,Junior Engineer 12 | ORD/000124/2022-2023 | 1610/RCD-I | 06/07/2022 | 22/03/2025 | RELIABLE ENGINEERS CO-OP CONSTRUCTION SOCIETY LTD. | 64.62 | 18.73 | 28.99 | 100
52 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order for Providing FHTC work for the Command area of Zone-XI (Part-9 Segment) for Improvement of RCFA Part-I Water Supply Scheme under RCFA Division-I PHE Dte | Assistant Engineer 2 | Junior Engineer | ORD/000131/2022-2023 | 1703/RCD-I | 14/07/2022 | 28/08/2022 | SOMNATH SAMANTA | 28.67 | 0 | 0 | 5
53 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Formal Work order for Rising Main for Improvement RCFA Part-I Water Supply Scheme for Salanpur and Barabani Block under RCFA Division-I PHE Dte. (Part ¿ A) | Assistant Engineer 1 | Junior Engineer | ORD/000016/2022-2023 | 1073/RCD-I | 13/05/2022 | 01/05/2024 | MD AAMIR KHAN | 115.25 | 75.01 | 65.08 | 90
54 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Construction of 900 cum capacity 20 Mtr staging height RCC Over Head Reservoir (Pipe connection and cost of pipes, specials at (Zone VII) for Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman (2nd Call) | Assistant Engineer 1 | Junior Engineer | ORD/000298/2022-2023 | 2453/RCD-I | 13/10/2022 | 13/10/2023 | SINGHA ROY & CO. | 181.16 | 181.16 | 100 | 100
55 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Providing And Installation of Electro-Mechanical Equipments and Allied Works at Dendua Boosting Station under Augmentation of RCFA Part-I Water Supply Scheme, Block-Salanpur, Dist.-Paschim Bardhaman. | Assistant Engineer-I | Junior Engineer-3 | ORD/000418/2022-2023 | 1951/AMD | 22/12/2022 | 31/01/2025 | EASTERN INDIA SALES AND SERVICE | 129.01 | 72.34 | 56.08 | 100
56 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Extension of different dia HDPE pipe line for providing FHTC at Putulia (Part), Kharboni, Jamjuri and allied villages under Gourbazar W/S Scheme under RCFA Division-I PHE Dte. (Sl No. 06) | Assistant Engineer 1 | Junior Engineer | ORD/000143/2022-2023 | 1437/RCD I | 27/06/2022 | 11/08/2022 | VISUVIOUS | 2.75 | 2.35 | 85.21 | 0
57 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Supply of Computer and accessories for Office use under RCFA Division-I PHE Dte. District - Paschim Bardhaman (Sl No. 01) | Assistant Engineer 1 | Junior Engineer | ORD/000207/2022-2023 | 1908/RCD-I | 12/08/2022 | 19/08/2022 | SHARMA ENGINEERING WORKS | 1.3 | 1.3 | 100 | 0
58 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Formal Work Order for Construction of 350 cum capacity 20 Mtr staging height RCC Over Head Reservoir (Pipe connection and cost of pipes, specials at (Zone-IX) for Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman (2nd Call) | Assistant Engineer 1 | Junior Engineer | ORD/000324/2022-2023 | 2403/RCD-I | 30/09/2022 | 30/09/2023 | MALLICK ENTERPRISE | 107.64 | 107.64 | 100 | 95
59 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order for Laying & Pushing of 800 mm dia RCC (NP3) Hume pipe by adopting trench less technology (e.g. Jack Pushing Method etc.) of Water Pipe Lines including supplying and laying of 400 mm dia MS Pipe line at Alladi More on Sitarampur Chittaranjan Road in connection to rising main (Part-A) under Improvement of RCFA Part-I PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000580/2022-2023 | 3288/RCD I | 20/12/2022 | 04/01/2023 | MAK CONSTRUCTION CO. | 16.45 | 16.38 | 99.55 | 0
60 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order for dedicated bypass line from Prantapally Durga Mandir to Kalyan Gram under Jitpur Uttarrampur GP under Improvement of RCFA Part-I Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000584/2022-2023 | 3292/RCD I | 20/12/2022 | 04/01/2023 | ASHA CONSTRUCTION | 11.77 | 11.48 | 97.53 | 0
61 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Construction of 450 cum capacity 20 Mtr staging height RCC Over Head Reservoir (Pipe connection and cost of pipes, specials at Barabani (Zone-XIII) for Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman [Rf Drwaing no. PC-I/OHR/04/2012(Sheet 1& 2) under RCFA Division-I PHE Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000291/2022-2023 | 2448/RCD-I | 13/10/2022 | 13/10/2023 | JOY HIND TUBEWELLS | 122.44 | 122.44 | 100 | 0
62 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order for Urgent basis repairing work of D P Colony (OHR) at D P Colony W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000618/2021-2022 | 712/RCD-I | 24/03/2022 | 23/04/2022 | RUBY CONSTRUCTION | 15.72 | 15.13 | 96.28 | 0
63 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000011/2021-2022 | 677/RCD-I | 21/03/2022 | 21/03/2022 | Resource Division | 57.29 | 0 | 0 | 0
64 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000005/2021-2022 | 301/RCD-I | 02/02/2022 | 02/02/2022 | Resource Division | 676.57 | 0 | 0 | 0
65 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000006/2021-2022 | 392/RCD-I | 16/02/2022 | 16/02/2022 | Resource Division | 2340.25 | 0 | 0 | 0
66 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000015/2022-2023 | 2626/RCD-I | 17/11/2022 | 17/11/2022 | Resource Division | 27.66 | 0 | 0 | 0
67 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000008/2022-2023 | 2352/RCD-I | 28/09/2022 | 28/09/2022 | Resource Division | 92.4 | 0 | 0 | 0
68 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000013/2022-2023 | 2644/RCD-I | 28/10/2022 | 28/10/2022 | Resource Division | 64.5 | 0 | 0 | 0
69 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Hire charges bill for vehicle no WB 37 D 0482 for the month of March 2022 |  |  | VCH/000121/2022-2023 | 518/22-23 | 29/09/2022 | 29/09/2022 | SHYAMAL MAJI | 0.19 | 0 | 0 | 0
70 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Payment for sample PT test bill no 376/21-22 dt. 25.06.2021 |  |  | VCH/000011/2022-2023 | 545/22-23 | 01/11/2022 | 01/11/2022 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
71 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Payment for furniture |  |  | VCH/000668/2022-2023 | 433/22-23 | 21/09/2022 | 21/09/2022 | VYAS & CO. | 2.35 | 0 | 0 | 0
72 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Submission of Quarterly regular return for non-salary 26Q3 & 26Q4 Regular Return for Salary 24Q3 & 24Q4 for the F.Y 2021-2022 and creation of Form 16 Part A & B 26Q2 for the F.Y 202021-22 Revised return for non salary return for the quarter 26Q3 & 26Q4 for the financial 2021-22 includes GST return for the month of April 2021 to March 2022 and April 2022 to May 2022 |  |  | VCH/000366/2022-2023 | 383/22-23 | 17/08/2022 | 17/08/2022 | SHRESTHA & ASSOCIATES | 0.58 | 0 | 0 | 0
73 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order for Different dia HDPE pipe line including extra cutting Laterate /sandstone and concrete cutting of distribution of pipe line Zone-I (Part-B) at Improvement of RCFA Part-I Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000682/2022-2023 | 370/RCD I | 30/01/2023 | 14/02/2023 | SWATI CORPORATION | 25.76 | 11.14 | 43.25 | 95
74 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order for Repairing and renovation of Panchagachia OHR of Capacity 1000 cum staging height 15 mtr under Improvement of RCFA Part-I Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000777/2022-2023 | 399/RCD I | 30/01/2023 | 30/04/2023 | RUBY CONSTRUCTION | 20.33 | 11.62 | 57.14 | 100
75 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Accepatance cum work order for construction of chlorine room of size (4.50 X 3.50m) at (Zone-IX) of Baraboni Block for Improvement of RCFA Part-I piped water supply scheme under RCFA Div-I, PHE Dte., in the District Paschim Bardhaman. | Assistant Engineer 2 | Junior Engineer | ORD/000737/2022-2023 | 676/RCDI | 24/02/2023 | 11/03/2023 | ZEROTH CONTROL SYSTEM | 4.61 | 2.91 | 63.24 | 100
76 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order Laying & Pushing of 500 mm dia RCC (NP3) Hume pipe by adopting trench less technology (e.g. Jack Pushing Method etc) of water pipe lines including supplying and laying of 200 mm dia 250 mm dia MS pipe line at different location on Asansol Chittanrajan Road, Kalyaneswari Dendua road within command area of rising main (Part-A) under Improvement of RCFA Part-I PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000834/2022-2023 | 1060/RCD-I | 23/03/2023 | 07/04/2023 | MAK CONSTRUCTION CO. | 40.5 | 39.62 | 97.83 | 100
77 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order for Dismanting of existing Drain and reconstruction the same, Construction of RCC pipe carring structur and other allied work at Alladih more and Rupnarayanpur Railway Station Site of improvement of RCFA Part -I in Connection of Rising main Part-A under RCFA Division-I PHE Dte.(Sl No. 06) | Assistant Engineer 1 | Junior Engineer | ORD/000838/2022-2023 | 1066/RCD I | 23/03/2023 | 22/04/2023 | MAK CONSTRUCTION CO. | 31.64 | 29.75 | 94.03 | 100
78 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order Additional work for the laying of Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-XI (Part-7 Distribution Segment) under RCFA Division-I PHE Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000878/2022-2023 | 1138/RCD-I | 24/03/2023 | 23/04/2023 | UNITED CONSTRUCTION | 24.64 | 17.12 | 69.46 | 90
79 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order Pipe line crossing by adopting trench less technology (e.g. Jack Pushing Method etc) at 7 nos location at Zone-V area Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000837/2022-2023 | 1065/RCD-I | 23/03/2023 | 22/04/2023 | MRITYUNJOY MUKHERJEE & CO. | 45.79 | 45.79 | 100 | 50
80 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order for Additional work for the laying of Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-VI under RCAF Division-I PHE Dte. (Part-C) (Sl. No. 17) | Assistant Engineer 1 | Junior Engineer | ORD/000893/2022-2023 | 1143/ RCD I | 24/03/2023 | 23/04/2023 | RANJIB GHATAK | 26.19 | 12.65 | 48.29 | 90
81 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum Work Order for Road crossing by open cut near to Nuni more including construction of drain, laterite cutting, concrete and bitumen road cutting and allied works at Ethora and adjacent area for laying of Rising Main (Part-B) for Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 08) | Assistant Engineer 1 | Junior Engineer | ORD/000898/2022-2023 | 1152/RCD-1 | 24/03/2023 | 08/04/2023 | M/S MONDAL ENTERPRISE | 5.09 | 4.7 | 92.33 | 100
82 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order for additional work for laying of distribution network for Improvement RCFA Part-I Piped Water Supply Scheme within command area of Zone-XI (Part-9 Distribution Segment) under RCFA Div-I, PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000831/2022-2023 | 1035/RCDI | 23/03/2023 | 02/04/2024 | SOMNATH SAMANTA | 42.19 | 20.02 | 47.46 | 100
83 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order Additional work for the laying of Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-XI (Part-4 Distribution Segment) under RCFA Division-I PHE Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000875/2022-2023 | 1136/RCD-I | 24/03/2023 | 23/04/2023 | DAWN CONSTRUCTION | 56.15 | 31.27 | 55.7 | 90
84 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Formal work order for Supplying aligning and laying of different dia HDPE pipe line instead of DI pipe line within distribution network within command are of Zone-I (Dendua OHR Site) of Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000036/2023-2024 | 1610/RCD I | 25/04/2023 | 24/07/2023 | SWATI CORPORATION | 114.21 | 98.16 | 85.94 | 86
85 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Formal work order for 200 mm, 160 mm & 90 mm dia HDPE PE-80 distribution network of RCFA Part-I Water Supply Scheme command area of Zone-IX under RCFA Div-I PHE Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000034/2023-2024 | 1612/RCD I | 25/04/2023 | 24/07/2023 | KHEPI MAA TRADERS | 149.55 | 53.69 | 35.9 | 90
86 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order Construction of drain at Dabor mouzas under RCFA Part-I W/S Scheme within command area of Zone-VII (Part-E) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000106/2023-2024 | 1865/RCD-1 | 01/06/2023 | 31/07/2023 | TARA CONSTRUCTION | 10.11 | 10 | 98.88 | 85
87 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Continuation work order for Pipe line crossing by adopting trench less technology (e.g. Jack Pushing Method etc) at 7 Nos. location at Zone-V area Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer 3 | Junior Engineer | ORD/000164/2023-2024 | 1911/RCD-I | 14/06/2023 | 14/07/2023 | MRITYUNJOY MUKHERJEE & CO. | 19.62 | 15.26 | 77.78 | 80
88 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Continuation work order for Laying & Pushing of 600 mm dia MS Water Carrier pipe and road Crossing by adopting trench less technology at Dendua more to Kalyaneswari road of Improvement of RCFA Part-I in connection of rising main (Part-A) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000158/2023-2024 | 1883/1/RCD-I | 07/06/2023 | 22/06/2023 | MD AAMIR KHAN | 66.19 | 66.19 | 99.99 | 0
89 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order for Additional work laying of 180 mm dia HDPE pipe line at Alladi More to Jemnari Bus Stand and Railway crossing at Rupnarayanpur village in connection with Improvement of RCFA Part-I Water Supply Scheme within command area of (Zone-V) with LDS & FHTC work under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer 3 | Junior Engineer | ORD/000227/2023-2024 | 2212/RCD-I | 17/07/2023 | 16/08/2023 | MACHINO TECHNO | 54.74 | 10.58 | 19.32 | 100
90 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order Balance work in connection with Improvement of RCFA Part-I Water Supply Scheme within command area of Zone-V with LDS & FHTC work under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer 3,Assistant Engineer 4 | Junior Engineer | ORD/000250/2023-2024 | 2239/RCD-I | 17/07/2023 | 01/04/2024 | MRITYUNJOY MUKHERJEE & CO. | 88.68 | 0 | 0 | 100
91 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order Laying & Pushing of 600 mm dia RCC (NP3) Hume Pipe by adopting trench less technology (e.g. Jack Pushing Method etc) at Kelejhora Health Centre More under Improvement of RCFA Part-I (Zone-11) PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000242/2023-2024 | 2233/RCD-I | 17/07/2023 | 16/08/2023 | SNEHA ELECTRIC | 29.11 | 16.38 | 56.27 | 55
92 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order for Additional works of Dismantling & concrete works & extra cutting Laterate/sandstone at distribution network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-VIII under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000229/2023-2024 | 2248/RCD-1 | 17/07/2023 | 16/08/2023 | SWATI CORPORATION | 12.73 | 9.93 | 77.96 | 80
93 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order Laying & Pushing of 600 mm dia RCC (NP3) Hume Pipe by adopting trench less technology (e.g. Jack Pushing Method etc) at 3 (Three) nos. location at Lalganj Domohani Road under Improvement of RCFA Part-I (Zone-11) PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000234/2023-2024 | 2230/RCD-I | 17/07/2023 | 16/08/2023 | R B ENTERPRISE | 42.66 | 26.2 | 61.41 | 65
94 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order for Balance work in connection with Improvement of RCFA Part-I Water Supply Scheme within command area of Zone-V under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer 3 | Junior Engineer | ORD/000217/2023-2024 | 2211/RCD-I | 17/07/2023 | 16/08/2023 | MACHINO TECHNO | 19.71 | 11.22 | 56.9 | 60
95 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order for Additional work for the laying of DI pipe, MS work, making valve chamber and other allied works for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-XI (Part-2 Distribution Segment) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000295/2023-2024 | 2366/RCD-I | 04/08/2023 | 03/09/2023 | SNEHA ELECTRIC | 51.75 | 50.2 | 97.01 | 98
96 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order for Construction of Boundary wall including land development, approach road (Length-65 mtr) and drain (Length-160 mtr) at Malbahal OHR site of Improvement of RCFA Part-I Piped Water Supply Scheme under Salanpur Block under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000431/2023-2024 | 2662/RCD-I | 26/09/2023 | 01/05/2025 | AMAR CONSTRUCTION | 35.5 | 0 | 0 | 100
97 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Providing And Installation of Electro-Mechanical Equipments and Sub-Stations Equipments at Ethora Boosting Station under Improvement of RCFA Part-I Water Supply Scheme, Block-Salanpur, Dist.-Paschim Bardhaman. | Assistant Engineer-I | Junior Engineer-3,Junior Engineer-5 | ORD/000437/2023-2024 | 2012/AMD | 06/11/2023 | 06/02/2027 | NEW ALIGNMENT | 267.24 | 181.05 | 67.75 | 93
98 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order for Additional extra cutting Laterate/sandstone of distribution of pipe line at Improvement of RCFA Part-I W/S Scheme within command area of Zone-VIII under RCFA Division-I PHE Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000687/2022-2023 | 375/RCD I | 30/01/2023 | 14/02/2023 | SWATI CORPORATION | 3.12 | 3.07 | 98.15 | 0
99 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance work order for Laying & Pushing of 800 mm dia RCC (NP3) Hume pipe by adopting trench less technology (e.g. Jack Pushing Method etc) of water pipe lines including supplying and laying of 450 mm dia MS pipe line at Mohismura More on NH Madhaichak Road in connection to rising main (Part-B) under Improvement of RCFA Part-I PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000643/2022-2023 | 341/RCD I | 30/01/2023 | 14/02/2023 | M/S MONDAL ENTERPRISE | 8.69 | 8.51 | 97.94 | 0
100 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Providing and installation of Gaseous Chlorination system at OHR Site at under Zone-VI under Augmentation of RCFA Part-I Water Supply Scheme, Dist.- Paschim Bardhaman. | Assistant Engineer-I | Junior Engineer-5 | ORD/000415/2022-2023 | 364/AMD | 09/02/2023 | 27/08/2025 | MAHADEV ENTERPRISE | 20.86 | 18.56 | 88.97 | 100
101 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Providing and installation of Gaseous Chlorination system at OHR Site under Zone-VII under Augmentation of RCFA Part-I water Supply Scheme, Block-Salanpur, Dist.- Paschim Bardhaman. | Assistant Engineer-I | Junior Engineer-5 | ORD/000416/2022-2023 | 365/AMD | 09/02/2023 | 12/09/2027 | ORIENTAL ENGINEERING CO. | 20.75 | 18.34 | 88.39 | 80
102 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order for Supply and delivery of CI sluice valve and C.I/D.I specials under improvement of RCFA part-I piped water supply scheme under RCFA div-I, PHE Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000701/2022-2023 | 613/RCD I | 23/02/2023 | 05/03/2023 | MAKALI ENGINEERING CORPORATION | 28.49 | 28.49 | 100 | 0
103 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Providing and installation of Gaseous Chlorination system at OHR Site under Zone-XI under Augmentation of RCFA Part-I water Supply Scheme, Dist.- Paschim Bardhaman. | Assistant Engineer-I | Junior Engineer-5 | ORD/000421/2022-2023 | 418/AMD | 16/02/2023 | 23/08/2025 | MACHINE SUPPLIERS SYNDICATE(P) LTD. | 20.56 | 18.28 | 88.95 | 100
104 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order for Additional extra cutting Laterate/sandstone of distribution of pipe line at Improvement of RCFA Part-I W/S Scheme within command area of Zone-VIII under RCFA Division-I PHE Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000686/2022-2023 | 374/RCD I | 30/01/2023 | 14/02/2023 | SWATI CORPORATION | 3.75 | 3.69 | 98.51 | 0
105 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order for Laying & Pushing of 800 mm dia RCC (NP3) Hume Pipe by adopting trench less technology (e.g. Jack Pushing Method etc) of Water Pipe Lines including supplying and laying of 450 mm dia MS Pipe Line at Hunuman Mandir on Mohismura Ethora Road near Ethora OHR inconnection to rising main (Part-B) under Augmentation of RCFA Part-I PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000676/2022-2023 | 360/RCD I | 30/01/2023 | 14/02/2023 | M/S MONDAL ENTERPRISE | 11.17 | 11.09 | 99.29 | 0
106 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Providing and installation of Gaseous Chlorination system at Dendua Boosting Station under Augmentation of RCFA Part-I water Supply Scheme, Block-Salanpur, Dist.- Paschim Bardhaman. | Assistant Engineer-I | Junior Engineer-3 | ORD/000414/2022-2023 | 363/AMD | 09/02/2023 | 07/02/2025 | EASTERN INDIA SALES AND SERVICE | 20.86 | 18.44 | 88.43 | 100
107 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Providing and installation of Gaseous Chlorination system at OHR Site under Zone-IX under Augmentation of RCFA Part-I water Supply Scheme, Block-Salanpur, Dist.- Paschim Bardhaman. | Assistant Engineer-I | Junior Engineer-5 | ORD/000417/2022-2023 | 366/AMD | 09/02/2023 | 16/08/2025 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 20.85 | 18.55 | 89 | 100
108 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum Work Order for Dismantling of existing guard room and store room for construction of 500 cum CWR at Dendua Boosting station of Improvement of RCFA Part-I under RCFA Division-I PHE Dte. (Sl No. 09) | Assistant Engineer 1 | Junior Engineer | ORD/000901/2022-2023 | 1153/RCD-1 | 24/03/2023 | 03/04/2023 | D.S. ENTERPRISE | 1.02 | 1.02 | 99.57 | 0
109 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order Construction of drain at Ethora and its adjoining mouzas under Improvement of RCFA Part-I W/S Scheme within command area of Zone-VIII under RCFA Division-I PHE Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000849/2022-2023 | 1086/RCD-I | 23/03/2023 | 22/05/2023 | SWATI CORPORATION | 23.95 | 23.94 | 99.96 | 0
110 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order Laying & Pushing of 400 mm dia RCC (NP3) Hume pipe by adopting trench less technology (e.g. Jack Pushing Method etc) of water pipe lines at Sandi More (Node point 137) Sandi Masimura More (Node point 85) and Lalganj Domhani Road (Node point 5-26) under Augmentation of RCFA Part-I PWSS within command area of Zone-VIII under RCFA Division-I PHE Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000857/2022-2023 | 1093/RCD-I | 23/03/2023 | 22/04/2023 | SWATI CORPORATION | 19.65 | 19.65 | 100 | 0
111 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order for Additional work for the laying of Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-XI (Part-6 Distribution Segment) under RCAF Division-I PHE Dte. (SL No. 16) | Assistant Engineer 1,Assistant Engineer 2,Assistant Engineer 7 | Junior Engineer | ORD/000895/2022-2023 | 1142/ RCD I | 24/03/2023 | 01/01/2024 | UMA ENTERPRISE | 76.17 | 32.7 | 42.94 | 100
112 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Additional extra cutting laterate/sandstone of distribution network for improvement of Part-I W/S Scheme within command area of Zone VII under RCFA Div-I, PHE Dte(Part-E) | Assistant Engineer 1 | Junior Engineer | ORD/000747/2022-2023 | 695/RCD I | 02/03/2023 | 09/03/2023 | TARA CONSTRUCTION | 0.83 | 0.79 | 94.95 | 0
113 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order for Supplying aligning and laying of HDPE Pipe line for restoration of pipe line towards MSPL at Kalyaneswari Dendua Road and supplying CI/DI specials in connection to aligning of rising main Part-A for Improvement of RCFA Part-I Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000762/2022-2023 | 389/RCD I | 30/01/2023 | 09/02/2023 | MD AAMIR KHAN | 21.01 | 20.7 | 98.52 | 0
114 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Providing and installation of Gaseous Chlorination system at OHR Site under Zone-XIII under Augmentation of RCFA Part-I water Supply Scheme, Dist.- Paschim Bardhaman. (2nd Call). | Assistant Engineer-I | Junior Engineer-5 | ORD/000506/2022-2023 | 608/AMD | 03/03/2023 | 02/01/2026 | M/S SAJAHAN CHOWDHURY | 20.86 | 18.56 | 88.96 | 100
115 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order for additional dedicated line to Sen Raleigh (Block-B) under Panchgachiya Distribution zone including laying of UPVC pipe line and allied works under Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Div-I, PHE Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000833/2022-2023 | 1054/RCD I | 23/03/2023 | 07/04/2023 | RUBY CONSTRUCTION | 11.13 | 11.11 | 99.81 | 0
116 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order Additional work for the laying of Distribution Network for Improvement RCFA Part-I Water Supply within command area of Zone-VI under RCFA Division-I PHE Dte. (Part-B) | Assistant Engineer 1 | Junior Engineer | ORD/000874/2022-2023 | 1134/RCD-I | 24/03/2023 | 23/04/2023 | M/S K & KONAR CONSTRUCTION | 30.49 | 19 | 62.31 | 100
117 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order for Laying & Pushing of 600 mm dia RCC (NP3) Hume pipe by adopting trench less technology (e.g. Jack Pushing Method etc.) at Lalganj more and Nuni more in related to laying of rising main (Part-B) under Improvement of RCFA Part-I PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000883/2022-2023 | 1127/ RCD I | 24/03/2023 | 08/04/2023 | M/S MONDAL ENTERPRISE | 23.75 | 23.62 | 99.46 | 0
118 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order Additional work for laying of 200 mm dia Rising Main under Lalganj Bridge by concrete conduit and allied MS work including adopting trench less technology (e.g. Jack Pushing Method etc) of 04 (Four) nos. location at Barabani & near Kelejora Health Centre in connection to rising main (Part-B) for Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000248/2023-2024 | 2235/RCD-I | 17/07/2023 | 16/08/2023 | M/S MONDAL ENTERPRISE | 50.86 | 50.09 | 98.48 | 100
119 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order Laying & Pushing of 600 mm dia RCC (NP3) Hume Pipe by adopting trench less technology (e.g. Jack Pushing Method etc) at Gowalabathan More towards Jamuria Road, Gowala para more towards Domohani Village, Goshala More towards Domohani village under Improvement of RCFA Part-I (Zone-11, Part-5) PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000239/2023-2024 | 2232/RCD-I | 17/07/2023 | 16/08/2023 | M/S B.K. CONSTRUCTION | 19.77 | 19.76 | 99.97 | 100
120 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Laying & Pushing of 800 mm dia RCC (NP3) Hume pipe by adopting trench less technology (e.g. Jack Pushing Method etc) of Water Pipe Lines including supplying and laying of 500 mm dia and 150 mm dia MS pipe line at different location on Asansol Chittaranjan Road within command area of Zone-I (Dendua OHR) Distribution system (Part-B) under Improvement of RCFA Part-I PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000861/2022-2023 | 1095/RCD-I | 23/03/2023 | 22/04/2023 | SWATI CORPORATION | 25.75 | 25.59 | 99.38 | 0
121 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum Work Order for Laying & Pushing of 400 mm dia RCC (NP3) Hume pipe by adopting trench less technology (e.g. jack Pushing Method etc) of Water Pipe Lines at Dabor More (Node point 334) Youth club (Node point 398) and Jaya hotel (Node point 228) Augmentation of RCFA Part-I PWSS within command area of Zone-VII under RCFA Division-I PHE Dte. (Part-E) (Sl No. 28) | Assistant Engineer 1 | Junior Engineer | ORD/000862/2022-2023 | 1094 / RCD-I | 23/03/2023 | 22/04/2023 | TARA CONSTRUCTION | 23.59 | 23.59 | 100 | 0
122 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order for Additional work for the laying of Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-XI (Part-8 Distribution Segment) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000236/2023-2024 | 2216/RCD-I | 17/07/2023 | 16/08/2023 | SIMA ENTERPRISE | 16.68 | 15.96 | 95.67 | 100
123 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order Additional work for the laying of Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-XI (Part-5 Distribution Segment) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000252/2023-2024 | 2238/RCD-I | 17/07/2023 | 16/08/2023 | M/S B.K. CONSTRUCTION | 39.57 | 24.47 | 61.86 | 100
124 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order for Additional work for the laying of distribution network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-XI (Part-5 Distribution Segment) under RCFA Division-I PHE Dte. (Part-B) | Assistant Engineer 2 | Junior Engineer | ORD/000207/2023-2024 | 2208/RCD-I | 17/07/2023 | 16/08/2023 | M/S B.K. CONSTRUCTION | 12.78 | 11.55 | 90.38 | 100
125 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order for Additional Laying & Pushing of 400 mm dia RCC (NP3) Hume pipe by adopting trench less technology (e.g. Jack Pushing Method etc) of Water Pipe Lines and Supplying Aligning Laying MS pipe (including carring loading & unloading at work site) Head Works Site (node point R1-1) and Lalganj Hat of Improvement RCFA Part-I PWSS within command area of Zone-VIII under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000223/2023-2024 | 2246/RCD-1 | 17/07/2023 | 16/08/2023 | TARA CONSTRUCTION | 17.17 | 15.58 | 90.72 | 100
126 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptation cum work order for Additional work for allied work in connection with Improvement of RCFA Part-I Water Supply Scheme within command area of Zone-V with LDS and FHTC work under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000246/2023-2024 | 2254/RCD-I | 17/07/2023 | 16/08/2023 | MACHINO TECHNO | 99.31 | 71.44 | 71.94 | 100
127 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order Laying & Pushing of 600 mm dia RCC (NP3) Hume pipe by adopting trench less technology (e.g. Jack Pushing Method etc) at Dabor More (250 mm dia Water Carrier 02 nos) and Dendua road to Chittaranjan road 01 no 450 mm dia Water Carrier and 02 nos 450 mm dia Water Carrier Pipe on Bonjemary Road of Salanpur Block under Improvement of RCFA Part-I (Part-A Rising Main) PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000249/2023-2024 | 2236/RCD-I | 17/07/2023 | 16/08/2023 | MD AAMIR KHAN | 51.47 | 51.44 | 99.95 | 100
128 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order for Laying & Pushing of 600mm dia ms water Carrer pipe and road Crossing by adopting trenchless technology at Dendua more to Kalyaneswri road of improvement of RCFA Part-I in connection of rasing main (part-A) under RCFA Division-I PHE Dte.(Sl No. 07) | Assistant Engineer 1 | Junior Engineer | ORD/000007/2023-2024 | 1405/RCD-1 | 12/04/2023 | 03/04/2024 | MD AAMIR KHAN | 90.31 | 68.18 | 75.5 | 100
129 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order for Additional works of Dismantling & concrete works & extra cutting Laterate/sandstone at distribution network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-VII under RCFA Division-I PHE Dte. (Part-E) | Assistant Engineer 2 | Junior Engineer | ORD/000225/2023-2024 | 2247/RCD-1 | 17/07/2023 | 16/08/2023 | TARA CONSTRUCTION | 10.06 | 9.8 | 97.38 | 100
130 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order for the additional work for the laying of different dia (315 mm , 280 mm, 225 mm ) dia HDPE pipe instead of different dia (300 mm , 250 mm, 200 mm) dia DJ pipe of distribution network for improvement RCA Part-I Water Supply Scheme within command area of Zone VI under RCFA Div-I, PHE Dte (Part-A) | Assistant Engineer 1 | Junior Engineer | ORD/000832/2022-2023 | 1051/RCD I | 23/03/2023 | 22/04/2023 | DIP CONSTRUCTION | 98.08 | 89.82 | 91.57 | 100
131 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order for construction of Chlorine Room of Size (4.50 x 3.50 m) at (Zone-VI) of Salanpur Block for Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District Paschim Bardhaman | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000658/2022-2023 | 357/RCDI | 30/01/2023 | 14/02/2023 | DAS & SARKAR ENTERPRISE | 4.6 | 3.75 | 81.44 | 100
132 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order for Repairing and restoration of concrete road due to FHTC work at Samdi and surrounding villages within Samdi Gram Panchayat under Improvement of RCFA Part-I water Supply scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000653/2023-2024 | 3450/RCD-I | 24/11/2023 | 09/12/2023 | RELIABLE ENGINEERS CO-OP CONSTRUCTION SOCIETY LTD. | 3.39 | 3.35 | 98.78 | 100
133 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000028/2022-2023 | 19/RCD-I | 05/01/2023 | 05/01/2023 | Resource Division | 121.92 | 0 | 0 | 0
134 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000030/2022-2023 | 54/RCD-I | 11/01/2023 | 11/01/2023 | Resource Division | 180.92 | 0 | 0 | 0
135 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000002/2023-2024 | 1637/RCD-I | 27/04/2023 | 27/04/2023 | Resource Division | 127.23 | 0 | 0 | 0
136 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Deposition of way leave Fees for Railway crossing for pipeline. |  |  | BILL/00150/2022-2023 | 946/22-23 | 09/03/2023 | 09/03/2023 | EASTERN RAILWAY | 6.08 | 0 | 0 | 0
137 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Deposition of way leave fee for pipeline crossing of Railway track in between Jamuria (JMA) and barabani (BBI) station of Asansol Division, Eastern Railway |  |  | BILL/00011/2023-2024 | 30/23-24 | 03/05/2023 | 03/05/2023 | EASTERN RAILWAY | 0.53 | 0 | 0 | 0
138 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Quotation Money for New Connection of Load at Dhonudi. |  |  | BILL/00029/2023-2024 | BP-2023-24-10 | 19/05/2023 | 19/05/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.34 | 0 | 0 | 0
139 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Shifting of High Tension Line and Street Light from the Proposed WTP plant area in Kalyaneswari Campus under Improvement of RCFA I Water Supply Scheme |  |  | BILL/00682/2023-2024 | BP-2023-24-59 | 26/12/2023 | 26/12/2023 | CHIEF ACCOUNTS OFFICER, DAMODAR VALLEY CORPORATION | 0.24 | 0 | 0 | 0
140 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Quotation Money for New Connection of Load at Lalganj |  |  | BILL/00030/2023-2024 | BP-2023-24-11 | 19/05/2023 | 19/05/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.48 | 0 | 0 | 0
141 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Vehicle bill |  |  | BILL/00704/2022-2023 | 1166/22-23 | 31/03/2023 | 31/03/2023 | KHEPI MAA TRADERS | 2.21 | 0 | 0 | 0
142 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Desposition of way leave Fees for Railway crossing for pipeline. |  |  | BILL/00147/2022-2023 | 947/22-23 | 09/03/2023 | 09/03/2023 | EASTERN RAILWAY | 5.04 | 0 | 0 | 0
143 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Deposition of way leave fee for pipeline crossing of Railway track in between Salanpur (SLS) and Rupnarayanpur (RNPR) km post 23/15-17 to 231/16-18 of Asansol Division, Eastern Railway |  |  | BILL/00059/2023-2024 | 64/23-24 | 25/05/2023 | 25/05/2023 | EASTERN RAILWAY | 5.12 | 0 | 0 | 0
144 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | fuel bill For WB 37D 0482 Nov 2022 |  |  | BILL/00432/2022-2023 | 821/22-23 | 20/01/2023 | 20/01/2023 | RANAJIT AUTO | 0.27 | 0 | 0 | 0
145 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Quotation Money for Enhanacement of Load at Dendua. |  |  | BILL/00027/2023-2024 | BP-2023-24-9 | 19/05/2023 | 19/05/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.88 | 0 | 0 | 0
146 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | ER-ASN-2023-WL-28 (Salanpur SLS to Rupnarayanpur RNPR) |  |  | BILL/00278/2023-2024 | 130/23-24 | 10/07/2023 | 10/07/2023 | EASTERN RAILWAY | 5.7 | 0 | 0 | 0
147 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | VEHICLE BILL |  |  | BILL/00705/2022-2023 | 1165/22-23 | 30/03/2023 | 30/03/2023 | PRAMIT CHATTERJEE | 1.2 | 0 | 0 | 0
148 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Supply of computer for Assistant Enginner-II |  |  | BILL/00708/2022-2023 | 944/22-23 | 30/03/2023 | 30/03/2023 | MUKHERJEE TRADERS | 0.42 | 0 | 0 | 0
149 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Engagement of 01 (One) no person under control of 2 (Two) nos AE/RCFA Div-I day to day report and return of FHTC as per scheme wise panchayet wise and updation of JJm |  |  | BILL/00761/2023-2024 | 320/23-24 | 16/10/2023 | 16/10/2023 | MUKHERJEE TRADERS | 0.49 | 0 | 0 | 0
150 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Restoration amount for unauthorised execavation and damaged at Ethora Nuni Road [Road connecting FR 10 and FR 19 (FR 13) under Asansol highwa |  |  | BILL/00039/2022-2023 | Asn-Highway-PWD | 11/01/2023 | 11/01/2023 | EXECUTIVE ENGINEER, ASANSOL HIGHWAY DIVISION, PW (ROADS) DIRECTT. | 10.45 | 0 | 0 | 0
151 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | VEHICLE BILL |  |  | BILL/00707/2022-2023 | 1113/22-23 | 30/03/2023 | 30/03/2023 | SHYAMAL MAJI | 0.19 | 0 | 0 | 0
152 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | IT GST FILLING |  |  | BILL/00706/2022-2023 | 1206/22-23 | 30/03/2023 | 30/03/2023 | SHRESTHA & ASSOCIATES | 0.5 | 0 | 0 | 0
153 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Meter Shifting Charge of Ethora Water tank under Improvement of RCFA (Part-I) Piped Water Supply Scheme |  |  | BILL/00564/2023-2024 | BP-2023-24-53 | 29/11/2023 | 29/11/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.02 | 0 | 0 | 0
154 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | DEPOSITION OF WAY LEAVE FEE (ER-ASN-2023-WL-17) |  |  | BILL/00017/2023-2024 | 41/23-24 | 10/05/2023 | 10/05/2023 | EASTERN RAILWAY | 5.37 | 0 | 0 | 0
155 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | June 2022 to Novemeber & December 2022 to Feburary 2023 |  |  | BILL/00030/2023-2024 | 19/23-24 | 18/04/2023 | 18/04/2023 | PRASENJIT DEY | 3.6 | 0 | 0 | 0
156 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Hiring of Maxi Cab (Non Air-conditioned) Bharat Stage-II/BS-III purchased on or after 01.05.2008 with Diesel/LPG/CNG Engine. for the Office use of the Assistant Engineer, RCFA Division-I, Public Health Engineering Directorate, Govt. of West Bengal (w.e.f. 01.07.2022 to 30.06.2023)(sl no 01) |  |  | BILL/00703/2022-2023 | 1210/22-23 | 31/03/2023 | 31/03/2023 | NIRMALA TRADERS | 2.8 | 0 | 0 | 0
157 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Deposition of way leave fee for pipeline crossing of Railway track in between Jamuria (JMA) and Barabani stan (BBI) km post 25/02-25/03 of Asansol Division |  |  | BILL/00058/2023-2024 | 65/23-24 | 25/05/2023 | 25/05/2023 | EASTERN RAILWAY | 4.63 | 0 | 0 | 0
158 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Quotation Money for New Connection of Load at Tabadi (Adibasi Para) |  |  | BILL/00028/2023-2024 | BP-2023-24-9 | 19/05/2023 | 19/05/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.34 | 0 | 0 | 0
159 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Quotation for Earnest money deposit for Bulk Power Supply at Ethora boosting Station Under Improvement of RCFA Part I WS Scheme. |  |  | BILL/00452/2023-2024 | BP-2023-24-31 | 13/09/2023 | 13/09/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.05 | 0 | 0 | 0
160 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum work order for Construction of 1 (One) no. Chlorine Room including Plinth protection, drain for 900 cum and 250 cum OHR at Baliapur under Improvement of RCFA (Part-I) Piped Water Supply Scheme. under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000115/2024-2025 | 2138/RCD-I | 27/08/2024 | 26/10/2024 | AMAR CONSTRUCTION | 9.01 | 0 | 0 | 100
161 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Allied Works Corresponding to "Providing And Installation of Electro-Mechanical Equipments and Sub-Stations Equipments at Ethora Boosting Station under Improvement of RCFA Part-I Block:- Salanpur, Dist -Paschim Bardhaman. | Assistant Engineer-I | Junior Engineer-5 | ORD/000452/2024-2025 | 2121/AMD | 16/12/2024 | 07/05/2025 | NEW ALIGNMENT | 8.12 | 0 | 0 | 70
162 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Acceptance cum Work Order for Construction of RCC column and M.S Structural Bridge for laying of 200 m dia MS pipe and other allied work for distribution network for Improvement of RCFA Part-I water supply scheme within command area of Zone-VII under RCFA Division ¿I PHE Dte | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/001172/2023-2024 | 1012/RCD-I | 16/03/2024 | 15/04/2024 | UNITED CONSTRUCTION | 6.54 | 6.47 | 98.97 | 100
163 | PASCHIM BARDHAMAN |  | RCFA Division -I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Wall writing IEC message along with logo picture etc. of multiple colour as will be supplied by the PHE Dte. on smooth durable wall surface preferably of Govt. premises boundary wall under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001164/2023-2024 | Camp-02-Wall-Writing-AE-I | 18/01/2024 | 17/02/2024 | MUKHERJEE TRADERS | 6.61 | 6.59 | 99.81 | 100
164 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Providing & fitting, fixing of lighting luminaries, electrical wiring of pump house & Substation Buliding with Yard lighting arrangement and other allied works at Ethora Boosting Station under " improvement of RCFA Part-I" Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-5 | ORD/000437/2024-2025 | 2095/AMD | 12/12/2024 | 03/01/2026 | PREMNATH MITRA | 23.48 | 0 | 0 | 100
165 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Providing & fitting, fixing of lighting luminaries, electrical wiring of pump house with yard lighting arrangement and other allied works at Dendua Pump House under Improvement R.C.F.A. PART-I Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-3 | ORD/000067/2024-2025 | 1198/AMD | 07/08/2024 | 21/09/2024 | EASTERN INDIA SALES AND SERVICE | 5.46 | 0 | 0 | 100
166 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Service connection and Security Deposit charge at Ethora Boosting Station under Improvement of RCFA Part-I W/S Scheme. |  |  | BILL/00778/2023-2024 | BP-2023-24-67 | 11/01/2024 | 11/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 25.69 | 0 | 0 | 0
167 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Providing and Installation of LT PDB Panel at Kalyaneswari Head works site under improvement of RCFA Part-I Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-4 | ORD/000751/2024-2025 | 601/AMD | 12/03/2025 | 12/05/2026 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 91.78 | 0 | 0 | 75
168 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Providing and installation of Gaseous chlorination system at Malladi OHR Site under Augmentation of RCFA Part-I Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-4 | ORD/000056/2025-2026 | 992/AMD | 23/05/2025 | 22/06/2025 | P.K.ENGINEERING | 28.7 | 0 | 0 | 0
169 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Installation of yard lighting arrangement, electrical wiring of chlorine room with lighting luminaries of Tabadi O.H.R. premises under Improvement of RCFA Part-I W/S Scheme. | Assistant Engineer-I | Junior Engineer-5 | ORD/000034/2025-2026 | 954/AMD | 16/05/2025 | 04/12/2025 | P.K.ENGINEERING | 4.23 | 0 | 0 | 100
170 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Installation of yard lighting arrangement, electrical wiring of chlorine room of Lalganj O.H.R.(Zone-IX & XI) premises under Improvement of RCFA Part-I W/S Scheme. | Assistant Engineer-I | Junior Engineer-5 | ORD/000037/2025-2026 | 956/AMD | 16/05/2025 | 04/12/2025 | P.K.ENGINEERING | 7.92 | 0 | 0 | 100
171 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Additional Electrical and illumination works and installation of 1 Ton Capacity mono rail at Dendua Boosting Station Pump House, under Improvement of RCFA (Part-I) Piped Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-3,Junior Engineer-4 | ORD/000028/2025-2026 | 948/AMD | 16/05/2025 | 15/06/2025 | EASTERN INDIA SALES AND SERVICE | 7.91 | 0 | 0 | 100
172 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | Augmentation | Additional quotation for drawl of HT line to avoid ROW issue for Ethora Boosting Station under Improvement of RCFA Part-I Water supply scheme. |  |  | BILL/01137/2024-2025 | BP-2024-25-96 | 28/03/2025 | 28/03/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.74 | 0 | 0 | 0
Total | [13 empty] | 10829.07 | 4711.75 | 43.51