## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF PANURIA PIPED WATER SUPPLY SCHEME | SM/10165 | Augmentation | Preparation of DPR for Augmentation of Panuria Piped Water Supply Scheme Block - Barabani, Dist - Paschim Bardhaman under RCFA Division-I PHE Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000449/2021-2022 | 2345/RCD-I | 17/12/2021 | 01/01/2022 | STEELCONC AND ASSOCIATES | 3.02 | 3.02 | 100 | 0
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF PANURIA PIPED WATER SUPPLY SCHEME | SM/10165 | Augmentation | Formal Work Order for Distribution System at Katapahari, Alipur, Baradanga village and surrounding area (Part-B) under Augmentation of Panuria Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000585/2021-2022 | 598/RCD-I | 07/03/2022 | 06/05/2022 | GITA CONSTRUCTION | 78.27 | 70.11 | 89.57 | 91
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF PANURIA PIPED WATER SUPPLY SCHEME | SM/10165 | Augmentation | Formal Work Order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone - I (Dendua OHR Site) under RCFA Division-I PHE Dte. (Part - A) | Assistant Engineer 1,Assistant Engineer 2,Assistant Engineer 7 | Junior Engineer | ORD/000013/2022-2023 | 1038/RCD-I | 10/05/2022 | 01/08/2025 | ASHA CONSTRUCTION | 147.65 | 26.38 | 17.87 | 100
4 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF PANURIA PIPED WATER SUPPLY SCHEME | SM/10165 | Augmentation | Acceptance cum work order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-VII under RCFA Division-I PHE Dte. (Part-B) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000125/2022-2023 | 1611/RCD-I | 06/07/2022 | 01/04/2026 | UNITED CONSTRUCTION | 55.84 | 10.08 | 18.06 | 75
5 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF PANURIA PIPED WATER SUPPLY SCHEME | SM/10165 | Augmentation | Acceptance cum work order for Providing FHTC work at Baradanga, Alipur and Kanta Pahari Villages under Augmentation of Panuria Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000240/2022-2023 | 2015/RCD-I | 26/08/2022 | 10/10/2022 | GITA CONSTRUCTION | 44.01 | 24.63 | 55.96 | 40
6 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF PANURIA PIPED WATER SUPPLY SCHEME | SM/10165 | Augmentation | Formal Work Order for Distribution System at Panuria village at surrounding area (Part-C) under Augmentation of Panuria Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000586/2021-2022 | 599/RCD-I | 07/03/2022 | 06/05/2022 | A. CONSTRUCTION CO. | 76.15 | 76.13 | 99.97 | 100
7 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF PANURIA PIPED WATER SUPPLY SCHEME | SM/10165 | Augmentation | Acceptance cum work order Providing FHTC work at Panuria (Part) and adjacent Habitation under Augmentation of Panuria Water Supply Scheme under RCFA Div-I, PHE Dte. | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000295/2022-2023 | 2468/RCDI | 14/10/2022 | 28/11/2022 | A. CONSTRUCTION CO. | 69.99 | 65.36 | 93.39 | 100
8 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF PANURIA PIPED WATER SUPPLY SCHEME | SM/10165 | Augmentation | Acceptance cum work order for Distribution System surrounding OHR near Panuria under Agumentation of Panuria PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000242/2022-2023 | 2151/RCD-I | 02/09/2022 | 02/10/2022 | A. CONSTRUCTION CO. | 28.88 | 26.24 | 90.84 | 100
9 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF PANURIA PIPED WATER SUPPLY SCHEME | SM/10165 | Augmentation | Acceptance cum work order for new pipe line of 200 mm, 90 mm and 75 mm dia at Panuria Bazar under Panuria GP under Augmentation of Panuria Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000576/2022-2023 | 3285/RCD I | 20/12/2022 | 18/02/2023 | SRI KRISHNA ENTERPRISE | 12.15 | 12.08 | 99.42 | 0
10 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF PANURIA PIPED WATER SUPPLY SCHEME | SM/10165 | Augmentation | Acceptance cum work order for construction of C.W.R. (Clear water Reservoir) of capacity 200 Cu.m & allied Work at Panuria under Augmentation of Panuria Piped Water Supply Scheme under RCFA Divn.-I. P.H.E. Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000594/2022-2023 | 3276/RCDI | 20/12/2022 | 20/03/2023 | SAMIR KUMAR ROY CHOWDHURY | 22.05 | 20.65 | 93.64 | 70
11 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF PANURIA PIPED WATER SUPPLY SCHEME | SM/10165 | Augmentation | Plumbing works, sanitary fitting, flooring and other allied works of staff Quarter (Group A Type) and other allied works at Kalyaneswari township under RCFA Division-I PHE Dte.(Sl no 03) | Assistant Engineer 2 | Junior Engineer | ORD/000018/2022-2023 | 1077/RCDI | 13/05/2022 | 12/06/2022 | R B ENTERPRISE | 3.89 | 3.82 | 98.14 | 100
12 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF PANURIA PIPED WATER SUPPLY SCHEME | SM/10165 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000013/2021-2022 | 696/RCD-I | 23/03/2022 | 23/03/2022 | Resource Division | 92.44 | 0 | 0 | 0
13 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF PANURIA PIPED WATER SUPPLY SCHEME | SM/10165 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000007/2022-2023 | 2347/RCD-I | 28/09/2022 | 28/09/2022 | Resource Division | 21.56 | 0 | 0 | 0
14 | PASCHIM BARDHAMAN |  | Asansol Mechanical | AUGMENTATION OF PANURIA PIPED WATER SUPPLY SCHEME | SM/10165 | Augmentation | Providing and Installation of Electro-Mechanical Equipments and Allied Works at Panuria under Augmentation of Panuria Itapara Water Supply Scheme, Block-Baraboni, Dist.-Paschim Bardhaman. | Assistant Engineer-I | Junior Engineer-3 | ORD/000433/2022-2023 | 488/AMD | 22/02/2023 | 02/08/2026 | BENGAL CONSTRUCTION | 180 | 60.38 | 33.54 | 68
15 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF PANURIA PIPED WATER SUPPLY SCHEME | SM/10165 | Augmentation | Acceptance cum work order Laying & Pushing of 600 mm dia RCC (NP3) Hume Pipe by adopting trench less technology (e.g. Jack Pushing Method etc) at Bhtas more, ardanga more on Asansol Runakuraghat Road, including supply of MS pipe and left out laying of HDPE pipe at Gourandi Bazar and allied works under Augmentation of Panuria PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000224/2023-2024 | 2227/RCD-I | 17/07/2023 | 16/08/2023 | GITA CONSTRUCTION | 43.42 | 39.5 | 90.99 | 91
16 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF PANURIA PIPED WATER SUPPLY SCHEME | SM/10165 | Augmentation | Formal work order for construction of 350 cum capacity 20 mtr staging height RCC over Head Reservoir (Piped connection and cost of pipes, specials at Gourandi H/W site for Augmentation of Panuria Piped Water Supply Scheme under RCFA Div-I, PHE dte in the District of Pachim Bardhaman. | Assistant Engineer 1 | Junior Engineer | ORD/000618/2022-2023 | 102/RCD I | 20/01/2023 | 20/08/2023 | A. CONSTRUCTION CO. | 115.99 | 115.99 | 100 | 100
17 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF PANURIA PIPED WATER SUPPLY SCHEME | SM/10165 | Augmentation | Acceptance cum work order Proposed Pump House including Toilet of Augmentation Panuria Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000836/2022-2023 | 1064/RCD-I | 23/03/2023 | 19/09/2023 | RUBY CONSTRUCTION | 31.13 | 31.12 | 99.96 | 100
18 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF PANURIA PIPED WATER SUPPLY SCHEME | SM/10165 | Augmentation | Acceptance cum work order for Repairing and renovation of existing culvert, Pump House, Staff Quarter under Augmentation of Panuria Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 24) | Assistant Engineer 1 | Junior Engineer | ORD/000891/2022-2023 | 1167/RCD I | 24/03/2023 | 22/06/2023 | R B ENTERPRISE | 5.94 | 5.88 | 98.96 | 0
19 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF PANURIA PIPED WATER SUPPLY SCHEME | SM/10165 | Augmentation | acceptance cum work order Laying & Pushing of 600 mm dia RCC (NP3) Hume Pipe by adopting trench less technology (e.g. Jack Pushing Method etc) at Tematha Panuria Bazar, Gourandi Bazar, Aliganj Road including supply of MS pipe and left out laying of HDPE pipe at Gourandi Bazar and allied works under Augmentation of Panuria PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000222/2023-2024 | 2226/RCD-I | 17/07/2023 | 16/08/2023 | A. CONSTRUCTION CO. | 30.14 | 29.86 | 99.08 | 100
20 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF PANURIA PIPED WATER SUPPLY SCHEME | SM/10165 | Augmentation | Acceptence cum work order for Laying of different dia distribution pipe line and etc. work at Tanti para, Camp para, Sasan para etc. under Khandra area under RCFA Part-II Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000405/2023-2024 | 2587/RCD-I | 07/09/2023 | 22/09/2023 | D.S.ENTERPRISE | 7.48 | 7.42 | 99.25 | 100
21 | PASCHIM BARDHAMAN |  | Asansol Mechanical | AUGMENTATION OF PANURIA PIPED WATER SUPPLY SCHEME | SM/10165 | Augmentation | QUOTATION MONEY FOR NEW CONNECTION AT PANURIA |  |  | BILL/00026/2023-2024 | BP-2023-24-7 | 19/05/2023 | 19/05/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.17 | 0 | 0 | 0
22 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF PANURIA PIPED WATER SUPPLY SCHEME | SM/10165 | Augmentation | Acceptance cum Work Order for Construction of road at Runakuraghat H/W site including earth filling,treeguard making including repairing and restoration of rising main including collecting main under Augmentation of Panuria PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000006/2024-2025 | 1432/RCD-I | 06/06/2024 | 21/07/2024 | SRI KRISHNA ENTERPRISE | 58.57 | 57.74 | 98.58 | 100
23 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF PANURIA PIPED WATER SUPPLY SCHEME | SM/10165 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000002/2024-2025 | 1179/RCD-I | 03/04/2024 | 03/04/2024 | Resource Division | 37.47 | 0 | 0 | 0
Total | [13 empty] | 1172.2 | 686.38 | 58.55