## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | WATER SUPPLY CONNECTION TO SCHOOL(419) AND ANGANWARI(1281) THROUGH RETROFITTING FROM EXISTING AND ONGOING PIPED WATER SUPPLY SCHEMES UNDER RCFA DIVISION-I, P.H.E DTE. | SM/10287 | School | Preparation of DPR for Augumentation of Itapara Piped Water Supply Scheme Block - Barabani, Dist - Paschim Bardhaman under RCFA Division-I PHE Dte. (Sl No. 02) | Assistant Engineer 1 | Junior Engineer | ORD/000482/2021-2022 | 2346/RCD I | 17/12/2021 | 01/01/2022 | STEELCONC AND ASSOCIATES | 2.82 | 0 | 0 | 0
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | WATER SUPPLY CONNECTION TO SCHOOL(419) AND ANGANWARI(1281) THROUGH RETROFITTING FROM EXISTING AND ONGOING PIPED WATER SUPPLY SCHEMES UNDER RCFA DIVISION-I, P.H.E DTE. | SM/10287 | School | Providing FHTC of different ICDS centre & extension of HDPE line under Raniganj Block of different Water Supply Scheme under RCFA Division-I PHE Dte.(Sl no 02) | Assistant Engineer 2 | Junior Engineer | ORD/000210/2022-2023 | 1979/RCDI | 24/08/2022 | 08/09/2022 | MS KALYAN ENTERPRISE | 4.76 | 3.84 | 80.68 | 0
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | WATER SUPPLY CONNECTION TO SCHOOL(419) AND ANGANWARI(1281) THROUGH RETROFITTING FROM EXISTING AND ONGOING PIPED WATER SUPPLY SCHEMES UNDER RCFA DIVISION-I, P.H.E DTE. | SM/10287 | School | Water Supply Connection to Anganwari through Retrofitting from existing near by PWSS at Baidyanathpur GP under Pandabeswar Block under RCFA Div-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000337/2022-2023 | 2851/RCDI | 02/11/2022 | 17/11/2022 | SOMNATH SAMANTA | 2.31 | 0 | 0 | 0
4 | PASCHIM BARDHAMAN |  | RCFA Division -I | WATER SUPPLY CONNECTION TO SCHOOL(419) AND ANGANWARI(1281) THROUGH RETROFITTING FROM EXISTING AND ONGOING PIPED WATER SUPPLY SCHEMES UNDER RCFA DIVISION-I, P.H.E DTE. | SM/10287 | School | Water Supply Connection to Anganwari through Retrofitting from existing near by PWSS at Nabagram GP under Pandabeswar Block under RCFA Div-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000336/2022-2023 | 2850/RCDI | 02/11/2022 | 17/11/2022 | SOMNATH GOSWAMI | 5.07 | 0 | 0 | 0
5 | PASCHIM BARDHAMAN |  | RCFA Division -I | WATER SUPPLY CONNECTION TO SCHOOL(419) AND ANGANWARI(1281) THROUGH RETROFITTING FROM EXISTING AND ONGOING PIPED WATER SUPPLY SCHEMES UNDER RCFA DIVISION-I, P.H.E DTE. | SM/10287 | School | Water Supply Connection to Anganwari through Retrofitting from existing near by PWSS at Bahula GP under Pandabeswar Block under RCFA Div-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000338/2022-2023 | 2852/RCDI | 02/11/2022 | 17/11/2022 | SIMA ENTERPRISE | 10.22 | 0 | 0 | 0
6 | PASCHIM BARDHAMAN |  | RCFA Division -I | WATER SUPPLY CONNECTION TO SCHOOL(419) AND ANGANWARI(1281) THROUGH RETROFITTING FROM EXISTING AND ONGOING PIPED WATER SUPPLY SCHEMES UNDER RCFA DIVISION-I, P.H.E DTE. | SM/10287 | School | Water Supply Connection to Anganwari through Retrofitting from existing near by PWSS at Chhora GP under Pandabeswar Block under RCFA Div-I PHE Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000333/2022-2023 | 2847/RCD I | 02/11/2022 | 17/11/2022 | DHRUBA ENTERPRISE | 5.69 | 4.22 | 74.09 | 0
7 | PASCHIM BARDHAMAN |  | RCFA Division -I | WATER SUPPLY CONNECTION TO SCHOOL(419) AND ANGANWARI(1281) THROUGH RETROFITTING FROM EXISTING AND ONGOING PIPED WATER SUPPLY SCHEMES UNDER RCFA DIVISION-I, P.H.E DTE. | SM/10287 | School | Water Supply Connection to Anganwari through Retrofitting from existing near by PWSS at Haripur GP under Pandabeswar Block under RCFA Div-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000334/2022-2023 | 2848/RCDI | 02/11/2022 | 17/11/2022 | N.R. CONSTRUCTION | 4.61 | 0 | 0 | 100
8 | PASCHIM BARDHAMAN |  | RCFA Division -I | WATER SUPPLY CONNECTION TO SCHOOL(419) AND ANGANWARI(1281) THROUGH RETROFITTING FROM EXISTING AND ONGOING PIPED WATER SUPPLY SCHEMES UNDER RCFA DIVISION-I, P.H.E DTE. | SM/10287 | School | Water Supply Connection to Anganwari through Retrofitting from existing near by PWSS at Kendra GP under Pandabeswar Block under RCFA Div-I PHE Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000335/2022-2023 | 2849/RCD I | 02/11/2022 | 17/11/2022 | GOPAL CONSTRUCTION | 4.74 | 1.29 | 27.17 | 0
9 | PASCHIM BARDHAMAN |  | RCFA Division -I | WATER SUPPLY CONNECTION TO SCHOOL(419) AND ANGANWARI(1281) THROUGH RETROFITTING FROM EXISTING AND ONGOING PIPED WATER SUPPLY SCHEMES UNDER RCFA DIVISION-I, P.H.E DTE. | SM/10287 | School | Water Supply Connection to School and Anganwari through Retrofitting from existing near by PWSS at Ondal, Srirampur & Madanpur GP under Ondal Block under RCFA Div-I PHE Dte. | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000339/2022-2023 | 2853/RCD I | 02/11/2022 | 01/10/2025 | MD SARFARAZ ALAM | 14.61 | 9.16 | 62.66 | 80
10 | PASCHIM BARDHAMAN |  | RCFA Division -I | WATER SUPPLY CONNECTION TO SCHOOL(419) AND ANGANWARI(1281) THROUGH RETROFITTING FROM EXISTING AND ONGOING PIPED WATER SUPPLY SCHEMES UNDER RCFA DIVISION-I, P.H.E DTE. | SM/10287 | School | Water Supply Connection to Anganwari through Retrofitting from existing near by PWSS at Khandra GP under Ondal Block under RCFA Div-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000341/2022-2023 | 2855/RCD I | 02/11/2022 | 17/11/2022 | M/S MONDAL CONSTRUCTION | 4.81 | 1.76 | 36.48 | 80
11 | PASCHIM BARDHAMAN |  | RCFA Division -I | WATER SUPPLY CONNECTION TO SCHOOL(419) AND ANGANWARI(1281) THROUGH RETROFITTING FROM EXISTING AND ONGOING PIPED WATER SUPPLY SCHEMES UNDER RCFA DIVISION-I, P.H.E DTE. | SM/10287 | School | Providing FHTC of different ICDS centre & extension of HDPE line under Jamuria Block of different Water Supply Scheme under RCFA Division-I PHE Dte.(sl no 01) | Assistant Engineer 1 | Junior Engineer | ORD/000209/2022-2023 | 1978/RCD I | 24/08/2022 | 08/09/2022 | MS KALYAN ENTERPRISE | 4.98 | 4.94 | 99.11 | 0
12 | PASCHIM BARDHAMAN |  | RCFA Division -I | WATER SUPPLY CONNECTION TO SCHOOL(419) AND ANGANWARI(1281) THROUGH RETROFITTING FROM EXISTING AND ONGOING PIPED WATER SUPPLY SCHEMES UNDER RCFA DIVISION-I, P.H.E DTE. | SM/10287 | School | Water supply connection to School and Anganwari through Retrofitting from existing near by PWSS at Ukhra Area under Andal Block under RCFA Div-I PHE Dte. (Sl No. 19) | Assistant Engineer 1 | Junior Engineer | ORD/000517/2021-2022 | 231/RCD I | 01/02/2022 | 11/02/2022 | RANJIB GHATAK | 4.5 | 3.61 | 80.26 | 0
13 | PASCHIM BARDHAMAN |  | RCFA Division -I | WATER SUPPLY CONNECTION TO SCHOOL(419) AND ANGANWARI(1281) THROUGH RETROFITTING FROM EXISTING AND ONGOING PIPED WATER SUPPLY SCHEMES UNDER RCFA DIVISION-I, P.H.E DTE. | SM/10287 | School | Aligning laying of pipe line connection including construction of platform of different ICDS Center & extension of HDPE line under Raniganj Block of different W/S Scheme under RCFA Division-I PHE Dte. (Sl No. 06) | Assistant Engineer 1 | Junior Engineer | ORD/000214/2022-2023 | 1983/RCD I | 24/08/2022 | 08/09/2022 | MS KALYAN ENTERPRISE | 3.51 | 3.51 | 100 | 0
14 | PASCHIM BARDHAMAN |  | RCFA Division -I | WATER SUPPLY CONNECTION TO SCHOOL(419) AND ANGANWARI(1281) THROUGH RETROFITTING FROM EXISTING AND ONGOING PIPED WATER SUPPLY SCHEMES UNDER RCFA DIVISION-I, P.H.E DTE. | SM/10287 | School | Aligning laying of pipe line connection including construction of platform of different ICDS Center & extension of HDPE line under Raniganj Block of different W/S Scheme under RCFA Division-I PHE Dte. (Part-B) (Sl No. 07) | Assistant Engineer 1 | Junior Engineer | ORD/000217/2022-2023 | 1984/RCD I | 24/08/2022 | 08/09/2022 | MS KALYAN ENTERPRISE | 3.7 | 3.66 | 98.76 | 0
15 | PASCHIM BARDHAMAN |  | RCFA Division -I | WATER SUPPLY CONNECTION TO SCHOOL(419) AND ANGANWARI(1281) THROUGH RETROFITTING FROM EXISTING AND ONGOING PIPED WATER SUPPLY SCHEMES UNDER RCFA DIVISION-I, P.H.E DTE. | SM/10287 | School | Laying of different dia UPVC pipe line and connection to 4 nos ICDS at Dhandadihi Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 12) | Assistant Engineer 1 | Junior Engineer | ORD/000221/2022-2023 | 1989/RCD I | 24/08/2022 | 08/09/2022 | MD. JAWED KHAN | 3.03 | 0 | 0 | 0
16 | PASCHIM BARDHAMAN |  | RCFA Division -I | WATER SUPPLY CONNECTION TO SCHOOL(419) AND ANGANWARI(1281) THROUGH RETROFITTING FROM EXISTING AND ONGOING PIPED WATER SUPPLY SCHEMES UNDER RCFA DIVISION-I, P.H.E DTE. | SM/10287 | School | Supplying, laying and aligning distribution branch and pipe line connection to ICDS centre under Egara GP under RCFA Division-I PHE Dte. (Raniganj Block)(Sl No. 11) | Assistant Engineer 1 | Junior Engineer | ORD/000628/2022-2023 | 2228/RCD-1 | 15/09/2022 | 30/09/2022 | DIP CONSTRUCTION | 4.9 | 4.9 | 100 | 0
17 | PASCHIM BARDHAMAN |  | RCFA Division -I | WATER SUPPLY CONNECTION TO SCHOOL(419) AND ANGANWARI(1281) THROUGH RETROFITTING FROM EXISTING AND ONGOING PIPED WATER SUPPLY SCHEMES UNDER RCFA DIVISION-I, P.H.E DTE. | SM/10287 | School | Water Supply connection to School and Anganwari through retrofitting from existing nearby PWSS Ondal, Srirampur, Madanpur GP under Ondal Block under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer,Junior Engineer 11 | ORD/000583/2022-2023 | 3291/RCDI | 20/12/2022 | 19/01/2023 | ALOKESH BANERJEE | 12.6 | 12.49 | 99.09 | 100
18 | PASCHIM BARDHAMAN |  | RCFA Division -I | WATER SUPPLY CONNECTION TO SCHOOL(419) AND ANGANWARI(1281) THROUGH RETROFITTING FROM EXISTING AND ONGOING PIPED WATER SUPPLY SCHEMES UNDER RCFA DIVISION-I, P.H.E DTE. | SM/10287 | School | Water Supply Connection to Anganwari through Retrofitting from existing near by PWSS at Dakshin Khanda GP under Ondal Block under RCFA Div-I PHE Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000340/2022-2023 | 2854/RCD I | 02/11/2022 | 17/11/2022 | DAS & SARKAR ENTERPRISE | 4.27 | 1.61 | 37.82 | 0
19 | PASCHIM BARDHAMAN |  | RCFA Division -I | WATER SUPPLY CONNECTION TO SCHOOL(419) AND ANGANWARI(1281) THROUGH RETROFITTING FROM EXISTING AND ONGOING PIPED WATER SUPPLY SCHEMES UNDER RCFA DIVISION-I, P.H.E DTE. | SM/10287 | School | Water supply connection to School and Anganwari through Retrofitting from existing near by PWSS at Baidyanathpur Area under Pandabeswar Block under RCFA Div-I PHE Dte. (Sl No. 16) | Assistant Engineer 1 | Junior Engineer | ORD/000514/2021-2022 | 228/RCD I | 01/02/2022 | 08/02/2022 | SOMNATH SAMANTA | 2.07 | 2.05 | 99.17 | 0
20 | PASCHIM BARDHAMAN |  | RCFA Division -I | WATER SUPPLY CONNECTION TO SCHOOL(419) AND ANGANWARI(1281) THROUGH RETROFITTING FROM EXISTING AND ONGOING PIPED WATER SUPPLY SCHEMES UNDER RCFA DIVISION-I, P.H.E DTE. | SM/10287 | School | Acceptance cum work order for Providing FHTC different ICDS Centre & extension of HDPE line under Jamuria Block of different Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000241/2022-2023 | 1956/RCD-I | 24/08/2022 | 08/10/2022 | D.S.C. CONCERN | 14.66 | 8.8 | 60.05 | 100
21 | PASCHIM BARDHAMAN |  | RCFA Division -I | WATER SUPPLY CONNECTION TO SCHOOL(419) AND ANGANWARI(1281) THROUGH RETROFITTING FROM EXISTING AND ONGOING PIPED WATER SUPPLY SCHEMES UNDER RCFA DIVISION-I, P.H.E DTE. | SM/10287 | School | Acceptance cum work order for Water Supply Connection to School and Anganwari through Retrofitting from existing near by PWSS under Barabani Block under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000685/2022-2023 | 373/RCDI | 30/01/2023 | 01/03/2023 | SRI KRISHNA ENTERPRISE | 12.66 | 0 | 0 | 0
22 | PASCHIM BARDHAMAN |  | RCFA Division -I | WATER SUPPLY CONNECTION TO SCHOOL(419) AND ANGANWARI(1281) THROUGH RETROFITTING FROM EXISTING AND ONGOING PIPED WATER SUPPLY SCHEMES UNDER RCFA DIVISION-I, P.H.E DTE. | SM/10287 | School | Acceptance cum work order for Water Water Supply connection to Anganwari through retrofitting from existing nearby PWSS at Harirpur GP under Pandabeswar Block under RCFA Division-I PHE Dte.( Sl No.-13) | Assistant Engineer 1 | Junior Engineer | ORD/000953/2022-2023 | 1157/ RCD I | 24/03/2023 | 23/04/2023 | SUKHENDU MAJUMDAR | 3.98 | 0 | 0 | 0
23 | PASCHIM BARDHAMAN |  | RCFA Division -I | WATER SUPPLY CONNECTION TO SCHOOL(419) AND ANGANWARI(1281) THROUGH RETROFITTING FROM EXISTING AND ONGOING PIPED WATER SUPPLY SCHEMES UNDER RCFA DIVISION-I, P.H.E DTE. | SM/10287 | School | Acceptance cum work order Water Supply connection to Anganwari through retrofitting from existing nearby PWSS at Baidyanathpur GP under Pandabeswar Block under RCFA Division-I PHE Dte. (Sl No. 16) | Assistant Engineer 1 | Junior Engineer | ORD/000899/2022-2023 | 1160/RCD-I | 24/03/2023 | 23/04/2023 | M/S KALYANI ENTERPRISE | 1.99 | 0 | 0 | 0
24 | PASCHIM BARDHAMAN |  | RCFA Division -I | WATER SUPPLY CONNECTION TO SCHOOL(419) AND ANGANWARI(1281) THROUGH RETROFITTING FROM EXISTING AND ONGOING PIPED WATER SUPPLY SCHEMES UNDER RCFA DIVISION-I, P.H.E DTE. | SM/10287 | School | Acceptance cum work order for Water Supply connection to Anganwari through retrofitting from existing nearby PWSS at Khandra GP under Ondal Block under RCFA Division-I PHE Dte. (Sl. No. 11) | Assistant Engineer 1,Assistant Engineer 8 | Junior Engineer | ORD/000905/2022-2023 | 1155/ RCD I | 24/03/2023 | 23/04/2023 | MOTIONMASS TECHNO (OPC) PRIVATE LIMITED | 4.13 | 3.31 | 80.04 | 80
25 | PASCHIM BARDHAMAN |  | RCFA Division -I | WATER SUPPLY CONNECTION TO SCHOOL(419) AND ANGANWARI(1281) THROUGH RETROFITTING FROM EXISTING AND ONGOING PIPED WATER SUPPLY SCHEMES UNDER RCFA DIVISION-I, P.H.E DTE. | SM/10287 | School | Acceptance cum work order for Water Supply connection to Anganwari through retrofitting from existing nearby PWSS at Dakhin Khanda GP under Ondal Block under RCFA Division-I PHE Dte. (Sl. No. 12) | Assistant Engineer 1 | Junior Engineer | ORD/000907/2022-2023 | 1156/ RCD I | 24/03/2023 | 23/04/2023 | GOPAL CONSTRUCTION | 3.66 | 0 | 0 | 0
26 | PASCHIM BARDHAMAN |  | RCFA Division -I | WATER SUPPLY CONNECTION TO SCHOOL(419) AND ANGANWARI(1281) THROUGH RETROFITTING FROM EXISTING AND ONGOING PIPED WATER SUPPLY SCHEMES UNDER RCFA DIVISION-I, P.H.E DTE. | SM/10287 | School | Acceptance cum Work Order for Water Supply connection to Anganwari through retrofitting from existing nearby PWSS at Chora GP under Pandabeswar Block under RCFA Division-I PHE Dte. (Sl No. 10) | Assistant Engineer 1 | Junior Engineer | ORD/000918/2022-2023 | 1154/RCD-1 | 24/03/2023 | 23/04/2023 | JUBILEE CONSTRUCTION | 4.91 | 0 | 0 | 0
27 | PASCHIM BARDHAMAN |  | RCFA Division -I | WATER SUPPLY CONNECTION TO SCHOOL(419) AND ANGANWARI(1281) THROUGH RETROFITTING FROM EXISTING AND ONGOING PIPED WATER SUPPLY SCHEMES UNDER RCFA DIVISION-I, P.H.E DTE. | SM/10287 | School | Acceptance cum work order of Water Supply Connection to School and Anganwari through Retrofitting from existing nearby PWSS at Samdi, Kallya, Jitpur-Uttarrampur, Fulberia Bolkunda GP under Salanpur Block under RCFA Division-I PHE Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000695/2022-2023 | 488/RCD I | 03/02/2023 | 05/03/2023 | SUBHADEEP DAS | 22.11 | 14.86 | 67.23 | 100
28 | PASCHIM BARDHAMAN |  | RCFA Division -I | WATER SUPPLY CONNECTION TO SCHOOL(419) AND ANGANWARI(1281) THROUGH RETROFITTING FROM EXISTING AND ONGOING PIPED WATER SUPPLY SCHEMES UNDER RCFA DIVISION-I, P.H.E DTE. | SM/10287 | School | Acceptance cum work order for Providing FHTC of different ICDS Centre & Extension of HDPE & PVC line under Raniganj Block of different Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000768/2022-2023 | 394/RCD I | 30/01/2023 | 01/03/2023 | MS KALYAN ENTERPRISE | 16.68 | 16.64 | 99.78 | 100
29 | PASCHIM BARDHAMAN |  | RCFA Division -I | WATER SUPPLY CONNECTION TO SCHOOL(419) AND ANGANWARI(1281) THROUGH RETROFITTING FROM EXISTING AND ONGOING PIPED WATER SUPPLY SCHEMES UNDER RCFA DIVISION-I, P.H.E DTE. | SM/10287 | School | Acceptance cum work order Water Supply connection to Anganwari through retrofitting from existing nearby PWSS at Kendra GP under Pandabeswar Block under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer 2,Assistant Engineer 4 | Junior Engineer | ORD/000912/2022-2023 | 1158/RCD-I | 24/03/2023 | 08/02/2026 | ANAMIKA CONSTRUCTION | 4.09 | 0 | 0 | 100
30 | PASCHIM BARDHAMAN |  | RCFA Division -I | WATER SUPPLY CONNECTION TO SCHOOL(419) AND ANGANWARI(1281) THROUGH RETROFITTING FROM EXISTING AND ONGOING PIPED WATER SUPPLY SCHEMES UNDER RCFA DIVISION-I, P.H.E DTE. | SM/10287 | School | Acceptance cum work order for Water Supply connection to Anganwari through retrofitting from existing nearby PWSS at Nabagram GP under Pandabeswar Block under RCFA Division-I PHE Dte. (Sl. No. 15) | Assistant Engineer 2 | Junior Engineer | ORD/000954/2022-2023 | 1159/RCDI | 24/03/2023 | 23/04/2023 | M/S SOUMYADWIP ENTERPRISE | 4.38 | 4.3 | 98.12 | 100
Total | [13 empty] | 196.46 | 104.93 | 53.41