## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SARSHATALI PIPED WATER SUPPLY SCHEME | SM/10605 | Augmentation | Preparation of DPR for Augumentation of Sarshatali Piped Water Supply Scheme Block - Barabani, Dist - Paschim Bardhaman under RCFA Division-I PHE Dte.(Sl No 04) | Assistant Engineer 1 | Junior Engineer | ORD/000480/2021-2022 | 2348/RCD I | 17/12/2021 | 01/01/2022 | STEELCONC AND ASSOCIATES | 2.88 | 2.88 | 100 | 0
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SARSHATALI PIPED WATER SUPPLY SCHEME | SM/10605 | Augmentation | Acceptance cum work order for Sinking of 2 (Two) no. 200 mm dia river bed tube well in the river Ajoy of Augmentation of Sarisatali Piped Water Supply Scheme under RCFA Division-I PHE Dte.(Sl No 07) | Assistant Engineer 1 | Junior Engineer | ORD/000113/2022-2023 | 1281/RCD I | 02/06/2022 | 02/07/2022 | MAA ENTERPRISE. | 11.06 | 10.81 | 97.79 | 0
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SARSHATALI PIPED WATER SUPPLY SCHEME | SM/10605 | Augmentation | Acceptance cum work order for Distribution Network for Augmentation of Sarisatali Piped Water Supply Scheme including FHTC work Block Barabani, Dist- Paschim Bardhaman under RCFA Div-I PHE,Dte. (Part-B) | Assistant Engineer 1 | Junior Engineer | ORD/000109/2022-2023 | 1278/RCD-I | 02/06/2022 | 31/08/2022 | MD. JAWED KHAN | 38.01 | 29.87 | 78.6 | 0
4 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SARSHATALI PIPED WATER SUPPLY SCHEME | SM/10605 | Augmentation | Acceptance cum work order for Supplying aligning & laying 225 mm dia HDPE pipe line in related to distribution Network for Augmentation of Sarisatali Piped W/S Scheme under RCFA Division-I PHE Dte. ( Sl No. 18) | Assistant Engineer 1 | Junior Engineer | ORD/000848/2022-2023 | 1085/RCD I | 23/03/2023 | 21/06/2023 | JAYANTA DATTA | 19.21 | 18.02 | 93.81 | 100
5 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SARSHATALI PIPED WATER SUPPLY SCHEME | SM/10605 | Augmentation | Acceptance cum work order for Distribution Network for Augmentation of Sarisatali Piped Water Supply Scheme including FHTC Work Block Barabani, Dist- Paschim Bardhaman under RCFA Div-I PHE,Dte.(Part-C) | Assistant Engineer 1 | Junior Engineer | ORD/000111/2022-2023 | 1279/RCD I | 02/06/2022 | 31/08/2022 | M/S B.K. CONSTRUCTION | 59.35 | 38.85 | 65.46 | 80
6 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SARSHATALI PIPED WATER SUPPLY SCHEME | SM/10605 | Augmentation | Emergent sinking of one no 200 X 165 mm dia rig bore tube well at District Magistrate bungalow, Asansole, Paschim Bardhaman under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000417/2023-2024 | Camp_2_DM_Office_AE_II_20 | 01/09/2023 | 04/09/2023 | M/S CHANDI CHARAN ROY | 7.87 | 7.74 | 98.42 | 100
7 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SARSHATALI PIPED WATER SUPPLY SCHEME | SM/10605 | Augmentation | Formal work order for Distribution network for augmentation of Sarisathali piped Water Supply scheme including FHTC work, Block-Baraboni, Dist-Paschim Bardhaman under RCFA Div-I, PHE Dte (Part-D) | Assistant Engineer 2 | Junior Engineer | ORD/000534/2022-2023 | 3231//RCDI | 19/12/2022 | 18/01/2023 | SRI KRISHNA ENTERPRISE | 133.36 | 14.98 | 11.23 | 50
8 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SARSHATALI PIPED WATER SUPPLY SCHEME | SM/10605 | Augmentation | Acceptance cum work order for Distribution Network for Augmentation of Sarisatali Piped Water Supply Scheme including FHTC Work Block Barabani, Dist- Paschim Bardhaman under RCFA Div-I PHE,Dte. (Part-A) | Assistant Engineer 1 | Junior Engineer | ORD/000108/2022-2023 | 1277/RCD-I | 02/06/2022 | 31/08/2022 | JAYANTA DATTA | 32.82 | 21.2 | 64.61 | 85
9 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SARSHATALI PIPED WATER SUPPLY SCHEME | SM/10605 | Augmentation | Acceptance cum Work Order for Construction of OHR (Capacity 300 cum, staging Height 20 mtrs) for Augmentation of Sarisathali Piped Water Supply Scheme under RCFA Division-I PHE Dte. Block-Barabani, Dist - Paschim Bardhaman. | Assistant Engineer 1 | Junior Engineer | ORD/000458/2022-2023 | 2933/RCD-I | 17/11/2022 | 29/11/2022 | M/S CHANDI CHARAN ROY | 85.83 | 81.54 | 95 | 100
10 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SARSHATALI PIPED WATER SUPPLY SCHEME | SM/10605 | Augmentation | Acceptance cum work order for Sinking of 2 (Two) nos 200 mm dia river bed tube well including collecting main in the river of Ajoy for Sarisatali Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000467/2023-2024 | 2859/RCD-I | 06/10/2023 | 21/10/2023 | MAA ENTERPRISE | 7.67 | 3.58 | 46.68 | 100
11 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SARSHATALI PIPED WATER SUPPLY SCHEME | SM/10605 | Augmentation | Repairing and renovation of staff quarter (Group A Type) and other allied works at Kalyaneswari Township under RCFA Division-I PHE Dte. (Sl No. 02) | Assistant Engineer 2 | Junior Engineer | ORD/000019/2022-2023 | 1078/RCDI | 13/05/2022 | 12/06/2022 | R B ENTERPRISE | 4.86 | 2.36 | 48.51 | 100
12 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SARSHATALI PIPED WATER SUPPLY SCHEME | SM/10605 | Augmentation | Acceptance cum work order Construction of Boundary wall including land development, approach road (Length-65 mtr) and drain (Length-160 mtr) at Sarisathali OHR site of Augmentation of Sarsathali Piped Water Supply Scheme under Barabani Block under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000206/2023-2024 | 2219/RCD-I | 17/07/2023 | 16/08/2023 | M/S CHANDI CHARAN ROY | 29.79 | 9.36 | 31.43 | 65
13 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SARSHATALI PIPED WATER SUPPLY SCHEME | SM/10605 | Augmentation | Acceptance cum work order Additional work for laying of distribution system including adopting trench less technology for one location near Khosnagar Health Centre and allied works under Augmentation of Sarishatali PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000285/2023-2024 | 2334/RCD-I | 01/08/2023 | 16/08/2023 | M/S B.K. CONSTRUCTION | 11.2 | 9.4 | 83.92 | 100
14 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SARSHATALI PIPED WATER SUPPLY SCHEME | SM/10605 | Augmentation | Acceptance cum Work Order for Trial run for operation distribution System including FHTC at Rashunpur and Domohani village under Augmentation of Sarsatali PWSS under RCFA Division I PHE Dte.6 (Six) Months. | Assistant Engineer 2 | Junior Engineer | ORD/001030/2023-2024 | 695/RCD-I | 29/02/2024 | 27/08/2024 | M/S B.K. CONSTRUCTION | 2.67 | 0 | 0 | 0
15 | PASCHIM BARDHAMAN |  | Asansol Mechanical | AUGMENTATION OF SARSHATALI PIPED WATER SUPPLY SCHEME | SM/10605 | Augmentation | Supply & Installation of submersible pumping machineries at 6 Nos Low Lift RBTWs at Shemalya pump House under Shemalya Piped Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-5 | ORD/000637/2023-2024 | 571/AMD | 14/03/2024 | 13/04/2024 | M/S SWAPAN BANERJEE | 13.34 | 0 | 0 | 0
16 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SARSHATALI PIPED WATER SUPPLY SCHEME | SM/10605 | Augmentation | Acceptance cum work order for Laying rising main including Guard room with Toilet including 12 (Twelve) nos Tube Well and Collecting main at River Ajoy under due to open cast mining activity of ECL Salanpur area for Sarisatali and Majiara Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000290/2023-2024 | 2339/RCD-I | 01/08/2023 | 30/10/2023 | MRITYUNJOY MUKHERJEE & CO. | 87.93 | 6.63 | 7.54 | 20
17 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SARSHATALI PIPED WATER SUPPLY SCHEME | SM/10605 | Augmentation | Acceptance cum Work Order for Construction of Chlorine room of size 4 mtr x 4 mtr x3.5 mtr (Ht) at Sarsatali under Augmentation of Sarsatali PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 1 | Junior Engineer | ORD/001085/2023-2024 | 875/RCD-I | 15/03/2024 | 14/05/2024 | JAI MAHARAJ ENTERPRISE | 4.04 | 1.99 | 49.41 | 0
18 | PASCHIM BARDHAMAN |  | Asansol Mechanical | AUGMENTATION OF SARSHATALI PIPED WATER SUPPLY SCHEME | SM/10605 | Augmentation | Providing & Installation of Low Lift Pumping Machineries at newly sunk Tube Wells at Kharabar river bed under Sarshatali Piped Water Supply scheme, Block : Baraboni, Dist : Paschim Bardhaman. | Assistant Engineer-I | Junior Engineer-4 | ORD/000041/2023-2024 | 1024/AMD | 19/04/2023 | 18/07/2023 | M/S. SOMA ENTERPRISE | 13.7 | 9.6 | 70.11 | 100
19 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SARSHATALI PIPED WATER SUPPLY SCHEME | SM/10605 | Augmentation | Acceptance cum Work Order for Additional work for laying Rising Main of Augmentation of Sarshatali Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000055/2024-2025 | 1745/RCD-I | 18/07/2024 | 17/08/2024 | M/S MONDAL ENTERPRISE | 28.19 | 0 | 0 | 0
20 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SARSHATALI PIPED WATER SUPPLY SCHEME | SM/10605 | Augmentation | Balance work of Supplying,laying and aligning of Distribution system includind FHTC for Shyamla W/S Scheme in Shyamla and Bhuri Mouza, Block jamuria, Dist-Paschim Bardhaman under Augmentation of Sarshatali Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000082/2024-2025 | Camp-02_Shyamla_AE-II/24- | 06/08/2024 | 05/09/2024 | TARA CONSTRUCTION | 12.5 | 6.2 | 49.62 | 100
Total | [13 empty] | 606.25 | 275.03 | 45.37