## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Jamuria (Rural) (Zone-II) PWSS. | SM/10640 | Augmentation | Formal work order for augmentation of Jamuria (Rural)(zone-I) piped water supply scheme including FHTC & allied work within Jamuria Block under RCFA Div-I, PHE Dte.(Part-B) |  |  | ORD/000599/2022-2023 | 16/RCD I | 05/01/2023 | 04/02/2023 | DIP CONSTRUCTION | 0 | 0 | NAN | 0
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Jamuria (Rural) (Zone-II) PWSS. | SM/10640 | Augmentation | Sub Soil Investigation for 200 cum capacity RCC Over Head Reservoir of Jamuria Block for Augmentation of Jamuria Rural-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | ORD/000524/2022-2023 | 3137/RCDI | 12/12/2022 | 19/12/2022 | P.K TEWARY DRILLING CO. | 0.55 | 0 | 0 | 0
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Jamuria (Rural) (Zone-II) PWSS. | SM/10640 | Augmentation | Preparation of DPR & Route Survey for Augmentation of Jamuria (Rural) (Zone-II) Piped Water Supply Scheme Block-Jamuria, Dist-Paschim Bardhaman under RCFA Division-I PHE Dte. (Sl No. 13) | Assistant Engineer 2 | Junior Engineer | ORD/000250/2022-2023 | 2230/RCD I | 15/09/2022 | 30/09/2022 | APEX ENGINEERING | 3.58 | 3.58 | 100 | 0
4 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Jamuria (Rural) (Zone-II) PWSS. | SM/10640 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000005/2022-2023 | 2345/RCD-I | 28/09/2022 | 28/09/2022 | Resource Division | 9.24 | 0 | 0 | 0
5 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Jamuria (Rural) (Zone-II) PWSS. | SM/10640 | Augmentation | Acceptance cum work order for Construction of High Lift Pump House at Riverside H/W site under Augmentation of Jamuria Rural (Zone I & II) Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000573/2022-2023 | 3282/RCDI | 20/12/2022 | 20/03/2023 | GLOBAL CONSTRUCTION | 31.24 | 27.01 | 86.48 | 90
6 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Jamuria (Rural) (Zone-II) PWSS. | SM/10640 | Augmentation | Acceptance cum work order for Distribution network for Augmentation of Jamuria Rural- II Piped Water Supply Scheme including FHTC work (Segment- I) under Jamuria Block in the district of Paschim Bardhaman Under RCFA Division - I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000100/2024-2025 | 2120/RCD-I | 27/08/2024 | 26/10/2024 | SIMA ENTERPRISE | 46.06 | 0 | 0 | 40
7 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Jamuria (Rural) (Zone-II) PWSS. | SM/10640 | Augmentation | Distribution network for Augmentation of Jamuria Rural-II Piped Water Scheme including FHTC work Block Jamuria, Dist Paschim Bardhaman under RCFA Div-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000292/2022-2023 | 2449/RCD-I | 13/10/2022 | 11/04/2023 | JOY HIND TUBEWELLS | 236.71 | 59.28 | 25.04 | 100
8 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Jamuria (Rural) (Zone-II) PWSS. | SM/10640 | Augmentation | Acceptance cum Work Order for Rising Main of Augmentation of Jamuria Rural (Zone-I & II) under RCFA Division-I PHE Dte (sl.no-14) | Assistant Engineer 2 | Junior Engineer | ORD/000773/2022-2023 | 805/RCD-I | 06/03/2023 | 05/05/2023 | M/S MONDAL ENTERPRISE | 22.77 | 8.18 | 35.93 | 40
9 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Jamuria (Rural) (Zone-II) PWSS. | SM/10640 | Augmentation | Acceptance cum work order for Additional work of Distribution Network for Augmentation of Jamuria (Rural) (Zone-II) Piped Water Supply Scheme including FHTC & allied work within Jamuria Block under RCFA Division-I PHE Dte. (Part- A) | Assistant Engineer 2 | Junior Engineer | ORD/000111/2024-2025 | 2133/RCD-I | 27/08/2024 | 20/01/2025 | M/S B.K. CONSTRUCTION | 20.94 | 10.82 | 51.67 | 65
10 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Jamuria (Rural) (Zone-II) PWSS. | SM/10640 | Augmentation | Acceptance cum work order for Distribution network for Augmentation of Jamuria Rural-II Piped Water Supply Scheme including FHTC work (Segment-III) under Jamuria Block in the the District of Paschim Bardhaman under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000112/2024-2025 | 2134/RCD-I | 27/08/2024 | 05/09/2025 | DAWN CONSTRUCTION | 95.92 | 20.33 | 21.2 | 40
11 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Jamuria (Rural) (Zone-II) PWSS. | SM/10640 | Augmentation | Acceptance cum work order for Distribution network for Augmentation of Jamuria Rural- II Piped Water Supply Scheme including FHTC work (Segment- II) under Jamuria Block in the district of Paschim Bardhaman under RCFA Division - I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000118/2024-2025 | 2117/RCD-I | 27/08/2024 | 09/11/2026 | MS SAMANTA CONSTRUCTION | 48.54 | 0 | 0 | 100
Total | [13 empty] | 515.54 | 129.2 | 25.06