## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Ondal (Phase-I) Water Supply Scheme | SM/10641 | Augmentation | Acceptance cum work order for Distribution Network for Augmentation of Ondal Phase-I Piped Water Supply Scheme including FHTC & allied work within Ondal Block under RCFA Division-I PHE Dte. (Part-A) | Assistant Engineer 2,Assistant Engineer 8 | Junior Engineer | ORD/000122/2022-2023 | 1608/RCD-I | 06/07/2022 | 28/05/2025 | AMAR CONSTRUCTION | 53.68 | 31.3 | 58.3 | 100
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Ondal (Phase-I) Water Supply Scheme | SM/10641 | Augmentation | Acceptance cum work order for Sinking of 5 (five) nos. 200 mm dia river bed tube well in river Damodar including laying of collecting main (HDPE & MS) of Augmentation of Ondal (Phase-I & Phase-II) piped Water Supply Scheme under RCFA Division-I PHE Dte.(SL NO 6) | Assistant Engineer 2 | Junior Engineer | ORD/000112/2022-2023 | 1287/RCD I | 03/06/2022 | 03/07/2022 | DAS & CHAKRABORTY | 75.11 | 36.68 | 48.83 | 100
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Ondal (Phase-I) Water Supply Scheme | SM/10641 | Augmentation | Acceptance cum work order for Distribution Network for Augmentation of Ondal Phase-I Piped Water Supply Scheme including FHTC & allied work within Ondal Block under RCFA Division-I PHE Dte. (Part-B) | Assistant Engineer 2 | Junior Engineer | ORD/000123/2022-2023 | 1609/RCD-I | 06/07/2022 | 04/10/2022 | UMA ENTERPRISE | 67.49 | 65.53 | 97.1 | 100
4 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Ondal (Phase-I) Water Supply Scheme | SM/10641 | Augmentation | Detailed Route Survey, Design Drawing & DPR Preparation for Ondal (Phase-I) Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 02) | Assistant Engineer 2 | Junior Engineer | ORD/000535/2021-2022 | 501/RCD-I | 24/02/2022 | 11/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.91 | 3.91 | 100 | 0
5 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Ondal (Phase-I) Water Supply Scheme | SM/10641 | Augmentation | Distribution Network for Augmentation of Ondal Phase-1 Piped Water Supply Scheme including FHTC & allied work within Ondal Block under RCFA Division-I PHE Dte. (Part-C) | Assistant Engineer 2 | Junior Engineer | ORD/000297/2022-2023 | 2452/RCD-I | 13/10/2022 | 11/04/2023 | M/S PIONEER CONSTRUCTION | 307.62 | 304.88 | 99.11 | 100
6 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Ondal (Phase-I) Water Supply Scheme | SM/10641 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000006/2022-2023 | 2346/RCD-I | 28/09/2022 | 28/09/2022 | Resource Division | 30.8 | 0 | 0 | 0
7 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Ondal (Phase-I) Water Supply Scheme | SM/10641 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000017/2022-2023 | 3132 | 09/12/2022 | 09/12/2022 | Resource Division | 40.44 | 0 | 0 | 0
8 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Ondal (Phase-I) Water Supply Scheme | SM/10641 | Augmentation | Acceptance cum work order for Emergency repairing and maintenance work of damaged RCC Elevated Reservoir including of capacity 700cum at Ramprasadpur of Augmentation of Ondal Phase-I W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000763/2022-2023 | 390/RCD I | 30/01/2023 | 31/03/2023 | SHILPA UDDOYG ENGINEERING CO-OP SOCIETY LTD. | 12.78 | 12.62 | 98.73 | 100
9 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Ondal (Phase-I) Water Supply Scheme | SM/10641 | Augmentation | Supply fitting fixing different dia valve and allied works in connection with laying distribution system including FHTC of Ondal Phase-I Water Supply Scheme (Part-B) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000338/2023-2024 | 2465/RCD-I | 18/08/2023 | 17/09/2023 | AMAR CONSTRUCTION | 0.62 | 0.62 | 99.16 | 100
10 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Ondal (Phase-I) Water Supply Scheme | SM/10641 | Augmentation | Acceptance cum work order for Additional for Distribution Network for Augmentation of Ondal (Phase-I) Piped Water Supply Scheme (Part-C) Block Andal, Dist-Paschim Bardhaman under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000233/2023-2024 | 2215/RCD-I | 17/07/2023 | 16/08/2023 | M/S UNIT CONSTRUCTION | 30.8 | 30.73 | 99.79 | 100
11 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Ondal (Phase-I) Water Supply Scheme | SM/10641 | Augmentation | Acceptance cum work order for additional work cutting hard rock,boulder concrete and others work including filling earth, removal rubbish of Augmentation of Ondal Phase-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000307/2023-2024 | 2382/RCD-I | 07/08/2023 | 06/09/2023 | M/S UNIT CONSTRUCTION | 89.75 | 81.28 | 90.56 | 100
12 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Ondal (Phase-I) Water Supply Scheme | SM/10641 | Augmentation | Acceptance cum work order for Emergency Repairing of 50 sqmm x 4 core Al Armoured damaged cable line provided of FHTC Pipe line near Dignala OHR Site under Andal W/S Scheme under RCFA Div-I, PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000480/2023-2024 | 2887/RCD-I | 06/10/2023 | 21/10/2023 | T R ENTERPRISE | 3.72 | 3.72 | 100 | 100
13 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Ondal (Phase-I) Water Supply Scheme | SM/10641 | Augmentation | Acceptance cum work order for Special repair and renovation of existing high lift Pump house, boundary Walls, Guard rooms, CWR, Switch Room etc, and allied works at H/W site of Ondal Phase-I Piped water Supply Scheme under RCFA Division-I PHE Dte. (Sl No 03) | Assistant Engineer 2 | Junior Engineer | ORD/000008/2023-2024 | 1404 RCD I | 12/04/2023 | 11/06/2023 | NATIONAL CONSTRUCTION | 13.75 | 12.12 | 88.17 | 100
14 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Ondal (Phase-I) Water Supply Scheme | SM/10641 | Augmentation | Acceptance cum work order Additional for Distribution Network for Augmentation of Ondal (Phase-I) Piped Water Supply Scheme (Part-A) Block Andal, Dist-Paschim Bardhaman under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000214/2023-2024 | 2222/RCD-I | 17/07/2023 | 16/08/2023 | M/S SUBHRADEEP | 16.33 | 15.89 | 97.36 | 100
15 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Ondal (Phase-I) Water Supply Scheme | SM/10641 | Augmentation | Acceptance cum work order for Additional for supplying, aligning and laying HDPE pipe, dismantling & concerting, supplying sluice valve and other allied works for Distribution Network for Augmentation of Ondal Phase-I Piped Water Supply Scheme including FHTC & allied work within Ondal Block under RCFA Division-I PHE Dte. (Part-B) | Assistant Engineer 2 | Junior Engineer | ORD/000647/2023-2024 | 3424/RCD-1 | 24/11/2023 | 24/12/2023 | M/S SUBHRADEEP | 34.89 | 34.51 | 98.91 | 100
16 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Augmentation of Ondal (Phase-I) Water Supply Scheme | SM/10641 | Augmentation | Lowering of Submersible Pumping machineries in the Newly sunk River Bed Tube Well No-11,12,13,14 & 15 and other allied works at Ramprasadpur HeadWorks Site under Andal Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-3 | ORD/000650/2023-2024 | 554/AMD | 14/03/2024 | 13/04/2024 | EASTERN INDIA SALES AND SERVICE | 6.62 | 6.58 | 99.39 | 100
17 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Augmentation of Ondal (Phase-I) Water Supply Scheme | SM/10641 | Augmentation | Providing & fitting, fixing of lighting luminaries of pump house with yard lighting arrangement and other allied works at Ramprasadpur Head Works Site under Andal Water Supply Scheme, Dist.- Paschim Bardhaman under Asansol Mechanical Division, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000450/2024-2025 | 2117/AMD | 16/12/2024 | 15/01/2025 | M/S JIT ENTERPRISE | 4.16 | 0 | 0 | 100
18 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Ondal (Phase-I) Water Supply Scheme | SM/10641 | Augmentation | Acceptance cum work order for Allied work for collecting main of River bed tube well in Damodar River for Augmentation of Ondal (Phase-I) Water Supply Scheme under JJM at Andal H/W Site under Andal Block under RCFA Division-I, PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000222/2024-2025 | 2543/RCD-I | 29/10/2024 | 28/11/2024 | MAA ENTERPRISE | 10.75 | 9.73 | 90.5 | 100
19 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Augmentation of Ondal (Phase-I) Water Supply Scheme | SM/10641 | Augmentation | Lowering of Submersible Pumping machineries in the Newly sunk River Bed Tube Well No-16, 17 & 18 and other allied works at Ramprasadpur Head Works Site under Andal Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-3 | ORD/000279/2024-2025 | 1674/AMD | 04/10/2024 | 05/05/2025 | EASTERN INDIA SALES AND SERVICE | 31.75 | 0 | 0 | 100
20 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Ondal (Phase-I) Water Supply Scheme | SM/10641 | Augmentation | Acceptance cum work order for Construction additional length of Boundary wall including land development and Pathway at Khas Kajora OHR site at Andal Block for Augmentation of Ondal (Phase-I) Water Supply Scheme under RCFA Division-I, PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000201/2024-2025 | 2467/RCD-I | 01/10/2024 | 15/11/2024 | M/S UNIT CONSTRUCTION | 21.86 | 17.76 | 81.24 | 100
21 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Ondal (Phase-I) Water Supply Scheme | SM/10641 | Augmentation | Acceptance cum work order for Laying of dedicated distribution line for Dignala village along the main road for Augmentation of Ondal (Phase-I) PWSS Andal Block, Dist-PaschimBardhaman under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000281/2025-2026 | 1385/RCD-I | 15/05/2025 | 09/06/2025 | UNITED CONSTRUCTION | 33.95 | 0 | 0 | 100
22 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Ondal (Phase-I) Water Supply Scheme | SM/10641 | Augmentation | Acceptance cum work order for Laying of rising main for Augmentation of Andal Phase-I (Dignala OHR) from Andal H/W Site under RCFA Div-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000505/2024-2025 | 131/RCD-I | 08/01/2025 | 22/02/2025 | UNITED CONSTRUCTION | 16.84 | 0 | 0 | 100
Total | [13 empty] | 907.61 | 667.85 | 73.58