## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Ondal (Phase-I) Water Supply Scheme | SM/10641 | Augmentation | Detailed Route Survey, Design Drawing & DPR Preparation for Ondal (Phase-I) Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 02) | Assistant Engineer 2 | Junior Engineer | ORD/000535/2021-2022 | 501/RCD-I | 24/02/2022 | 11/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.91 | 3.91 | 100 | 0
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Ondal (Phase-I) Water Supply Scheme | SM/10641 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000017/2022-2023 | 3132 | 09/12/2022 | 09/12/2022 | Resource Division | 40.44 | 0 | 0 | 0
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Ondal (Phase-I) Water Supply Scheme | SM/10641 | Augmentation | Acceptance cum work order for Sinking of 5 (five) nos. 200 mm dia river bed tube well in river Damodar including laying of collecting main (HDPE & MS) of Augmentation of Ondal (Phase-I & Phase-II) piped Water Supply Scheme under RCFA Division-I PHE Dte.(SL NO 6) | Assistant Engineer 2 | Junior Engineer | ORD/000112/2022-2023 | 1287/RCD I | 03/06/2022 | 03/07/2022 | DAS & CHAKRABORTY | 75.11 | 36.68 | 48.83 | 100
4 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Ondal (Phase-I) Water Supply Scheme | SM/10641 | Augmentation | Acceptance cum work order for additional work cutting hard rock,boulder concrete and others work including filling earth, removal rubbish of Augmentation of Ondal Phase-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000307/2023-2024 | 2382/RCD-I | 07/08/2023 | 06/09/2023 | M/S UNIT CONSTRUCTION | 89.75 | 81.28 | 90.56 | 100
5 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Ondal (Phase-I) Water Supply Scheme | SM/10641 | Augmentation | Supply fitting fixing different dia valve and allied works in connection with laying distribution system including FHTC of Ondal Phase-I Water Supply Scheme (Part-B) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000338/2023-2024 | 2465/RCD-I | 18/08/2023 | 17/09/2023 | AMAR CONSTRUCTION | 0.62 | 0.62 | 99.16 | 100
6 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Ondal (Phase-I) Water Supply Scheme | SM/10641 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000006/2022-2023 | 2346/RCD-I | 28/09/2022 | 28/09/2022 | Resource Division | 30.8 | 0 | 0 | 0
7 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Ondal (Phase-I) Water Supply Scheme | SM/10641 | Augmentation | Distribution Network for Augmentation of Ondal Phase-1 Piped Water Supply Scheme including FHTC & allied work within Ondal Block under RCFA Division-I PHE Dte. (Part-C) | Assistant Engineer 2 | Junior Engineer | ORD/000297/2022-2023 | 2452/RCD-I | 13/10/2022 | 11/04/2023 | M/S PIONEER CONSTRUCTION | 307.62 | 304.88 | 99.11 | 100
8 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Ondal (Phase-I) Water Supply Scheme | SM/10641 | Augmentation | Acceptance cum work order for Additional for Distribution Network for Augmentation of Ondal (Phase-I) Piped Water Supply Scheme (Part-C) Block Andal, Dist-Paschim Bardhaman under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000233/2023-2024 | 2215/RCD-I | 17/07/2023 | 16/08/2023 | M/S UNIT CONSTRUCTION | 30.8 | 30.73 | 99.79 | 100
9 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Augmentation of Ondal (Phase-I) Water Supply Scheme | SM/10641 | Augmentation | Lowering of Submersible Pumping machineries in the Newly sunk River Bed Tube Well No-11,12,13,14 & 15 and other allied works at Ramprasadpur HeadWorks Site under Andal Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-3 | ORD/000650/2023-2024 | 554/AMD | 14/03/2024 | 13/04/2024 | EASTERN INDIA SALES AND SERVICE | 6.62 | 6.58 | 99.39 | 100
10 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Ondal (Phase-I) Water Supply Scheme | SM/10641 | Augmentation | Acceptance cum work order for Distribution Network for Augmentation of Ondal Phase-I Piped Water Supply Scheme including FHTC & allied work within Ondal Block under RCFA Division-I PHE Dte. (Part-A) | Assistant Engineer 2 | Junior Engineer | ORD/000122/2022-2023 | 1608/RCD-I | 06/07/2022 | 28/05/2025 | AMAR CONSTRUCTION | 53.68 | 31.3 | 58.3 | 100
11 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Ondal (Phase-I) Water Supply Scheme | SM/10641 | Augmentation | Acceptance cum work order for Emergency repairing and maintenance work of damaged RCC Elevated Reservoir including of capacity 700cum at Ramprasadpur of Augmentation of Ondal Phase-I W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000763/2022-2023 | 390/RCD I | 30/01/2023 | 31/03/2023 | SHILPA UDDOYG ENGINEERING CO-OP SOCIETY LTD. | 12.78 | 12.62 | 98.73 | 100
12 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Ondal (Phase-I) Water Supply Scheme | SM/10641 | Augmentation | Acceptance cum work order for Distribution Network for Augmentation of Ondal Phase-I Piped Water Supply Scheme including FHTC & allied work within Ondal Block under RCFA Division-I PHE Dte. (Part-B) | Assistant Engineer 2 | Junior Engineer | ORD/000123/2022-2023 | 1609/RCD-I | 06/07/2022 | 04/10/2022 | UMA ENTERPRISE | 67.49 | 65.53 | 97.1 | 100
Total | [13 empty] | 719.62 | 574.12 | 79.78