## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF ITAPARA PIPED WATER SUPPLY SCHEME | SM/10844 | Augmentation | Preparation of DPR for Augumentation of Itapara Piped Water Supply Scheme Block - Barabani, Dist - Paschim Bardhaman under RCFA Division-I PHE Dte. (Sl No. 02) | Assistant Engineer 1 | Junior Engineer | ORD/000482/2021-2022 | 2346/RCD I | 17/12/2021 | 01/01/2022 | STEELCONC AND ASSOCIATES | 2.82 | 2.82 | 100 | 0
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF ITAPARA PIPED WATER SUPPLY SCHEME | SM/10844 | Augmentation | Construction of Pumping Station at Itapara new H/W Site of Itapara Water Supply Scheme under RCFA Division-I PHE Dte.(Sl no 01) | Assistant Engineer 1 | Junior Engineer | ORD/000127/2020-2021 | 14 / RCD I | 08/01/2021 | 22/02/2021 | RELIABLE ENGINEERS CO-OP CONSTRUCTION SOCIETY LTD. | 2.75 | 0 | 0 | 0
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF ITAPARA PIPED WATER SUPPLY SCHEME | SM/10844 | Augmentation | Acceptance cum work order for Providing FHTC work for the Command area of Zone-XI (Part-6 Segment) for augmentation of Itapara piped Water Supply Scheme under RCFA Division-I PHE Dte | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000161/2022-2023 | 1699/RCD-I | 13/07/2022 | 21/01/2025 | UMA ENTERPRISE | 44.47 | 16.76 | 37.69 | 45
4 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF ITAPARA PIPED WATER SUPPLY SCHEME | SM/10844 | Augmentation | Rising Main for Augmentation of Itapara Piped Water Supply Scheme at Baraboni Block Under RCFA - Div - I PHE Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000566/2022-2023 | 3277/RCD I | 20/12/2022 | 01/06/2024 | DURGADAS MONDAL | 34.74 | 19.21 | 55.3 | 80
5 | PASCHIM BARDHAMAN |  | Asansol Mechanical | AUGMENTATION OF ITAPARA PIPED WATER SUPPLY SCHEME | SM/10844 | Augmentation | Providing and Installation of Electro-Mechanical Equipments and Allied Works at Panuria under Augmentation of Panuria Itapara Water Supply Scheme, Block-Baraboni, Dist.-Paschim Bardhaman. | Assistant Engineer-I | Junior Engineer-3 | ORD/000433/2022-2023 | 488/AMD | 22/02/2023 | 02/08/2026 | BENGAL CONSTRUCTION | 180 | 62.07 | 34.49 | 68
6 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF ITAPARA PIPED WATER SUPPLY SCHEME | SM/10844 | Augmentation | Acceptance cum work order for Construction of approach road, land development, CWR painting, Cable trench slab, drainage system at Runakuraghat H/W campus under Augmentation of Itapara Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 24) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000859/2022-2023 | 1090/RCD-I | 23/03/2023 | 22/05/2023 | SRI KRISHNA ENTERPRISE | 37.83 | 35.84 | 94.75 | 100
7 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF ITAPARA PIPED WATER SUPPLY SCHEME | SM/10844 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000032/2022-2023 | 121/RCD-I | 24/01/2023 | 24/01/2023 | Resource Division | 222.41 | 0 | 0 | 0
8 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF ITAPARA PIPED WATER SUPPLY SCHEME | SM/10844 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000029/2022-2023 | 28/RCD-I | 10/01/2023 | 10/01/2023 | Resource Division | 92.01 | 0 | 0 | 0
9 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF ITAPARA PIPED WATER SUPPLY SCHEME | SM/10844 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000011/2023-2024 | 2207/RCD-I | 17/07/2023 | 17/07/2023 | Resource Division | 160.38 | 0 | 0 | 0
10 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF ITAPARA PIPED WATER SUPPLY SCHEME | SM/10844 | Augmentation | Acceptance cum work order for Construction of Guard Room with toilet at Dabor OHR site under Chotkara Kanskuli Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer 7 | Junior Engineer | ORD/000970/2023-2024 | 460/RCD-1 | 12/02/2024 | 12/05/2024 | RELIABLE ENGINEERS CO-OP CONSTRUCTION SOCIETY LTD. | 5.97 | 0 | 0 | 0
11 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF ITAPARA PIPED WATER SUPPLY SCHEME | SM/10844 | Augmentation | Continuation work order for Renovation of filter bed, changing of Media and allied works at Salanpur Dalmia OCP Project under RCFA Division-I PHE Dte. |  | Junior Engineer | ORD/001070/2023-2024 | 101_A_RCD-I | 09/01/2024 | 24/01/2024 | R B ENTERPRISE | 7.46 | 0 | 0 | 0
12 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF ITAPARA PIPED WATER SUPPLY SCHEME | SM/10844 | Augmentation | Acceptance cum Work Order for Additional work for raising height of tube well to encounter flood including surging of tube well, repairing work of collecting main at river Ajoy at Churulia under Augmentation of Itapara Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001087/2023-2024 | 876/RCD-I | 15/03/2024 | 30/03/2024 | MD AAMIR KHAN | 4.09 | 0 | 0 | 100
13 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF ITAPARA PIPED WATER SUPPLY SCHEME | SM/10844 | Augmentation | Acceptance cum work order for Construction of Guard Room with toilet at Malladihi OHR site under Chotkara Kanskuli Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000967/2023-2024 | 717-A/RCD-I | 01/03/2024 | 30/05/2024 | PINKI ENTERPRISE | 5.97 | 0 | 0 | 0
14 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF ITAPARA PIPED WATER SUPPLY SCHEME | SM/10844 | Augmentation | Acceptance cum work order for Supply of valves, construction of valve chamber, supplying laying HDPE/UPVC/GI pipe line and allied works at Putulia, Hosenpur and adjacent area under Augmentation of Itapara W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000972/2023-2024 | 461/RCD-1 | 12/02/2024 | 13/03/2024 | R B ENTERPRISE | 7.72 | 7.67 | 99.34 | 100
15 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF ITAPARA PIPED WATER SUPPLY SCHEME | SM/10844 | Augmentation | Acceptance cum work order for Construction of spout, repairing and restoration of pipe line, FHTC connection and allied land development works within distribution system under Malladihi OHR under Augmentation of Itapara PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000986/2023-2024 | 469/RCD-1 | 12/02/2024 | 27/02/2024 | ASHA CONSTRUCTION | 7.18 | 6.99 | 97.46 | 100
16 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF ITAPARA PIPED WATER SUPPLY SCHEME | SM/10844 | Augmentation | Continuation of work order for Conducting route survey , design rising main network and preparation & submission of source augmentation DPR for Itapara PWSS for Impementation of JJM at Barabani block under RCFA DIVISION-I P.H.E. Dte. | Assistant Engineer 2 |  | ORD/001009/2023-2024 | 74/A/RCD-I | 02/01/2024 | 17/01/2024 | RISHAN ENGINEERING CONSULTANCY | 4.97 | 4.97 | 100 | 100
Total | [13 empty] | 820.79 | 156.35 | 19.05