## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Madantor Water Supply Scheme | SM/10845 | Augmentation | Detailed Route Survey, Design Drawing & DPR Preparation for Madantor Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 4) | Assistant Engineer 2 | Junior Engineer | ORD/000539/2021-2022 | 503/RCD-I | 24/02/2022 | 11/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.04 | 0 | 0 | 0
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Madantor Water Supply Scheme | SM/10845 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000023/2022-2023 | 3130 | 09/12/2022 | 09/12/2022 | Resource Division | 12.9 | 0 | 0 | 0
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Madantor Water Supply Scheme | SM/10845 | Augmentation | Acceptance cum work order for repair and renovation works of GLR of capacity 90 cum for Augmentation of Madantor Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 23) | Assistant Engineer 2 | Junior Engineer | ORD/000889/2022-2023 | 1166/RCD I | 24/03/2023 | 20/09/2023 | A.K.CONSTRUCTION | 6.48 | 0 | 0 | 5
4 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Madantor Water Supply Scheme | SM/10845 | Augmentation | Acceptance cum work order Repairing & shifting work of DI pipes and allied repairing at Madanpur under Madanpur W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000928/2022-2023 | 1261/ RCD I | 27/03/2023 | 11/04/2023 | MAK CONSTRUCTION CO. | 3.22 | 0 | 0 | 100
5 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Madantor Water Supply Scheme | SM/10845 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000011/2022-2023 | 2351/RCD-I | 28/09/2022 | 28/09/2022 | Resource Division | 12.32 | 0 | 0 | 0
6 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Madantor Water Supply Scheme | SM/10845 | Augmentation | Acceptance cum work order for Repair and renovation works of Clear Water Reservoir of Capacity 150 cum for Augmentation of Madantore Piped water Supply scheme under RCFA division-I PHE dte. | Assistant Engineer 2 | Junior Engineer | ORD/000558/2023-2024 | 3187/RCD-I | 01/11/2023 | 29/04/2024 | A.K.CONSTRUCTION | 10.86 | 0 | 0 | 0
7 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Madantor Water Supply Scheme | SM/10845 | Augmentation | Acceptance cum Work Order for Additional works of Dismantling and concrete works supplying aligning and laying HDPE pipe and other allied works at distribution system network for Bagdiha (Part-D) Augmentation of Madantor Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000973/2023-2024 | 491/RCD-I | 12/02/2024 | 28/03/2024 | TARA MA ENTERPRISE | 18.79 | 0 | 0 | 75
8 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Madantor Water Supply Scheme | SM/10845 | Augmentation | Acceptance cum work order for Repair and renovation works of One no. RCC Elevated Reservoir of Capacity 250 cum at Madantore under Augmentation of Madantore Piped water Supply scheme under RCFA division-I PHE dte. | Assistant Engineer 2 | Junior Engineer | ORD/000557/2023-2024 | 3186/RCD-I | 01/11/2023 | 28/07/2024 | A.K.CONSTRUCTION | 10.95 | 0 | 0 | 100
9 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Madantor Water Supply Scheme | SM/10845 | Augmentation | Acceptance cum work order for Supply & Delivery of GI pipe including loading, unloading and carriage to Searsole Store under RCFA Part-II PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/001034/2023-2024 | 713/RCD-I | 29/02/2024 | 20/03/2024 | NEZONE TUBES LIMITED | 95.53 | 0 | 0 | 100
10 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Madantor Water Supply Scheme | SM/10845 | Augmentation | Acceptance cum work order for Additional supplying laying and aligning of distribution system including FHTC for Shyamla in Chatrisganda Mouza, Block Jamuria Paschim Bardhaman under Augmentation of Madantore PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000114/2024-2025 | 2137/RCD-I | 27/08/2024 | 11/10/2024 | DAWN CONSTRUCTION | 38 | 0 | 0 | 100
11 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Madantor Water Supply Scheme | SM/10845 | Augmentation | Laying of distribution system including FHTC work for Augmentation of Madantore Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000293/2022-2023 | 2450/RCD-I | 13/10/2022 | 11/04/2023 | JOY HIND TUBEWELLS | 246.41 | 0 | 0 | 100
12 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Madantor Water Supply Scheme | SM/10845 | Augmentation | Acceptance cum work order for Providing FHTC work for the Command area of Zone-XI (Part-4 Segment) for Augmentation of Madantore Piped Water Supply Scheme under RCFA Division-I PHE Dte | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000157/2022-2023 | 1708/RCD-I | 15/07/2022 | 12/12/2024 | DAWN CONSTRUCTION | 48.67 | 0 | 0 | 100
13 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Madantor Water Supply Scheme | SM/10845 | Augmentation | Construction of Pump House at Churulia under Madantore Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000572/2022-2023 | 3281/RCDI | 20/12/2022 | 20/03/2023 | M/S MONDAL ENTERPRISE | 30.24 | 0 | 0 | 100
14 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Madantor Water Supply Scheme | SM/10845 | Augmentation | Acceptance work order for Construction of Chlorine Room of Size (4.50 x 3.50 m) at Churulia for Augmentation of Madantore Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | ORD/000644/2022-2023 | 342/RCDI | 30/01/2023 | 14/02/2023 | ANAMIKA CONSTRUCTION | 4.6 | 0 | 0 | 100
15 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Augmentation of Madantor Water Supply Scheme | SM/10845 | Augmentation | Supply, delivery & installation of Pump Motor Set in the basis of "Augmentation of Madantor & Its Adjoining Mouzas "Piped Water Supply Scheme under Asansol Mechanical Division, P.H.E Dte. Block-Jamuria, District-Paschim Bardhaman. | Assistant Engineer-I | Junior Engineer-5 | ORD/000505/2022-2023 | 607/AMD | 03/03/2023 | 03/10/2024 | M/S. SOMA ENTERPRISE | 14.44 | 0 | 0 | 100
16 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Madantor Water Supply Scheme | SM/10845 | Augmentation | Acceptance cum work order for Sinking of 1 (One) no. 200 mm dia river bed tube well in the river Ajoy including 01 (One) no collecting main of Augmentation of Madantor Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 22) | Assistant Engineer 2 | Junior Engineer | ORD/000886/2022-2023 | 1165/RCD I | 24/03/2023 | 23/05/2023 | R B ENTERPRISE | 5.77 | 0 | 0 | 0
Total | [13 empty] | 563.21 | 0 | 0